## Sheet1
Cost Summary for Edinburgh Trams as at 2012/13 Period 6 Ending 15 September 2012
Cost headings | Cost prior to Settlement Agreement | Budget post Settlement Agreement | COWD to Date | Note (This column will include narrative on variances in future reports)
| £'m | £'m | £'m
Project Costs
On street infrastructure
Bilfinger Berger | 9.5 | 120.8 | 110.49 | 1
Siemens
Other | 0 | 0 | 0.18
TOTAL ON STREET | 9.5 | 120.8 | 110.67
Off street infrastructure
Bilfinger Berger | 129.59 | 229.06 | 166.89 | 1
Siemens
Other | 18.53 | 18.09 | 18.6
TOTAL OFF STREET | 148.12 | 247.15 | 185.49
Other Infraco
Bilfinger Berger | 0 | 0 | 0
Siemens | 0.27 | 3.2 | 0.66
Settlement of claims system wide | 49 | 49 | 49 | 1
TOTAL | 49.27 | 52.2 | 49.66
Utilities
MUDFA | 57.252 | 57.252 | 57.252
Post Settlement Agreement | 0 | 2.91 | 2.91
Other | 26.168 | 27.428 | 25.55
TOTAL | 83.42 | 87.59 | 85.712
Vehicles
Construction/Fabrication | 23.448 | 62.4 | 23.45
Vehicle design | 2.752 |  | 2.752
Manuals, special tools and spare parts | 4.403 |  | 4.403
Delivery of trams | 4.513 |  | 4.513
Other | 12.78 |  | 25.71
TOTAL | 47.9 | 62.4 | 60.83
Project Management
Management & Supervision | 52.68 | 60.96 | 63.94
Insurance | 4.05 | 4.84 | 4.962
Accommodation, And Support Costs | 12.47 | 17.31 | 14.218
TOTAL | 69.2 | 83.11 | 83.12
Land, Property & other costs | 28.85 | 36.05 | 34.38
Readiness for Operations
Transdev and Edinburgh Trams staff | 2.834 | 12.07 | 3.807
Lothian Buses recharges and other costs | 2.428 |  | 2.672
Ticketing machines | 0.144 |  | 0.145
Others | 0.094 |  | 0.176
TOTAL | 5.5 | 12.07 | 6.8
Comms & Stakeholder
External comms & media | 2.204 | 4.36 | 2.629
Stakeholder | 0.756 |  | 0.801
TOTAL | 2.96 | 4.36 | 3.43
Design | 27.18 | 29.05 | 26.69
Legal
DLA | 3.501 | 7.22 | 3.502
Post Mediation | 0 |  | 1.294
Other | 2.869 |  | 2.414
TOTAL | 6.37 | 7.22 | 7.21
Contingency | 0 | 34 | 15.1
TOTAL | 478.27 | 776 | 669.092
Notes
1. As members are aware from the confidential appendix to the 25 August 2011 Council report the negotiations with the BBS consortium led to a figure of approximately £360m for;
(a) off street work;
(b) settlement of claims in relation to off street;
(c) settlement of claims in relation to on street; and
(d) settlement of claims in relation to system wide work
In order to ascertain an allocation of that figure for the purposes of this summary we have calculated that;
(a) £204m relates to off street work;
(b) £25m relates to settlment of claims in relation to off street;
(c) £82m relates to settlement of claims in relation to on street; and
(d) £49m relates to settlement in relation to system wide work
Note on B3: Clive Arbuckle: 2011/12 P4 COWD
Note on C3: Clive Arbuckle: As at 2/9/11 per SFLA
Note on D3: Clive Arbuckle: 2012/13 P6 COWD
Note on D26: Alan Coyle: remainder of COWD from risk