## Analysis Summary
ANALYSIS SUMMARY
Ref. | Description | CUS AFP | tie Cert | Variance | tie Cert (Apr) | Variance to Current
1 to 50 | Change Controls 1 to 50 as separate register | 1194367.1931 | 1142296.9131 | -52070.28 | 1142296.9131 | 0
51 to 100 | Change Controls 51 to 100 as separate register | 602806.5113 | 602806.5113 | 0 | 602806.5113 | 0
101 to 132 | Change Controls 101 to 132 as separate register | 949981.9395 | 931513.4095 | -18468.53 | 931513.4095 | 0
133 to 164 | Change Controls 133 to 164 as separate register | 1103952.6815 | 1103952.6815 | 0 | 1113421.6607 | 9468.9792
165 to 196 | Change Controls 165 to 196 as separate register | 2219524.9683 | 2153151.2183 | -66373.75 | 2153898.0753 | 746.857
197 to 250 | Change Controls 197 to 250 as separate register | 702522.859 | 456141.5566 | -246381.3024 | 430289.2487 | -25852.3078
47 | WORK ORDER 1A-03-01 (Ocean Drive) - SEPARATE REGISTER | 258141.0198 | 258141.0198 | 0 | 258141.0198 | 0
48 | WORK ORDER 1B-01-01 (Leith Walk) - SEPARATE REGISTER | 525891.9374 | 386754.8677 | -139137.0697 | 387732.0677 | 977.2
48.24 | WORK ORDER RAT 1B/01 (Jane Street) - SEPARATE REGISTER | 76470.6778 | 76470.6778 | 0 | 76470.6778 | 0
69 | WORK ORDER 5A-08-02 (Roseburn) - SEPARATE REGISTER | 48296.7171 | 48296.7171 | 0 | 48296.7171 | 0
75 | WORK ORDER 6A-01-01 (Gogar MUDFA) - SEPARATE REGISTER | 30172.9203 | 30172.9203 | 0 | 30172.9203 | 0
89 | WORK ORDER 1C-01-02 (Princes St) - SEPARATE REGISTER | 4813.1505 | 4813.1505 | 0 | 4813.1505 | 0
90 | WORK ORDER 1D-05-02 (Princes St) - SEPARATE REGISTER | 27239.6885 | 27239.6885 | 0 | 27239.6885 | 0
99 | WORK ORDER 1C-01-01 (The Mound) - SEPARATE REGISTER | 820242.5139 | 661543.6563 | -158698.8576 | 661543.6563 | 0
100 | WORK ORDER 1C-02-01 (Princes St) - SEPARATE REGISTER | 43044.8485 | 43044.8485 | 0 | 43044.8485 | 0
103 | WORK ORDER 7A-02-01 (Gogarburn to Park & Ride) SEPARATE REGISTER | 10591.6337 | 10591.6337 | 0 | 10591.6337 | 0
107 | WORK ORDER 1B-01-02 (Balfour Street to Foot of the Walk) SEPARATE REGISTER | 381856.0251 | 291137.4204 | -90718.6047 | 287837.4204 | -3300
122 | WORK ORDER RAT 1C/01 (St Andrews Square BT Openreach) SEPARATE REGISTER | 108585.0027 | 91721.7726 | -16863.2301 | 89721.7726 | -2000
125 | WORK ORDER 1D-04-01 (Shandwick Place) | 703791.4837 | 612911.0348 | -90880.449 | 608396.7462 | -4514.2886
129 | WORK ORDER 1C-03-02 (York Place to South St Andrews St) | 235293.3275 | 187773.7326 | -47519.595 | 183071.7326 | -4702
144 | WORK ORDER (Gogar 800mm Water Main) as FA submission | 1860998.7145 | 1860998.7145 | 0 | 1860998.7145 | 0
149 | WORK ORDER 5B-01-01 (Broomhouse Rd to Edinburgh Park TS) | 31482.3181 | 31482.3181 | 0 | 31482.3181 | 0
153 | WORK ORDER 1A-01-01 (Constitution Street) | 500557.4578 | 348999.4486 | -151558.0092 | 348999.4486 | 0
154 | WORK ORDER 1D-01-01 (Haymarket) | 510400.4159 | 445068.9078 | -65331.5081 | 445068.9078 | 0
156 | WORK ORDER 5C-01-01 (Gogarburn to Edinburgh park Tram Stop) | 178127.383 | 168385.605 | -9741.7779 | 168385.605 | 0
160 | WORK ORDER 1C-04-01 (Broughton St to McDonald Rd) | 729156.3813 | 587468.7218 | -141687.6596 | 587468.7218 | 0
164 | WORK ORDER 2A-01-01 (Haymarket RaT 2A) | 534042.4365 | 373731.6682 | -160310.7684 | 371229.6682 | -2502
169 | WORK ORDER 7B | 5141.9874 | 5141.9874 | 0 | 5141.9874 | 0
185 | WORK ORDER 1A-02-01 | 4144.4362 | 4144.4362 | 0 | 4144.4362 | 0
190 | WORK ORDER 1C-05-01 (Union St - York place) | 258066.8382 | 258066.8382 | 0 | 258066.8382 | 0
192 | WORK ORDER 1A-04-01 | 4303.6271 | 4303.6271 | 0 | 4303.6271 | 0
198 | NPO | 459453 | 379314.039 | -80138.961 | 379314.039 | 0
228 | WORK ORDER 7B-01-01 Edinburgh Airport | 1567.1508 | 1567.1508 | 0 | 1567.1508 | 0
231 | WORK ORDER 1A-01-02 | 95.64 | 95.64 | 0 | 95.64 | 0
246 | Bypass - All Sites | 672039.0285 | 65840 | -606199.0285 | 65840 | 0
| ENABLING WORKS | 7625105.0585 | 6582675.5197 | -1042429.5389 | 6582675.5197 | 0
| WORK SITE MEASURE | 18259598.7545 | 16690389.016 | -1569209.7385 | 16690389.016 | 0
| PCS | 987610.595 | 987610.595 | 0 | 987610.595 | 0
| PRELIMS | 8936461.6246 | 8936461.6246 | 0 | 8936461.6246 | 0
| GOGAR EARTHWORKS | 5288767.6121 | 5288767.6121 | 0 | 5288767.6121 | 0
| GAIN SHARE | 256000 | 256000 | 0 | 256000 | 0
| INDICES | 1587000 | 1587000 | 0 | 1587000 | 0
| ENTITLEMENT (TO SEP'08) | 1880000 | 1880000 | 0 | 1880000 | 0
| ENTITLEMENT (FROM OCT'08) | 13244871.0446 | 1109426 | -12135445.0446 | 1109426 | 0
| HAND DIGGING | 152000 | 152000 | 0 | 152000 | 0
| tie DEDUCTIONS | -15000 | -794933.16 | -779933.16 | -794933.16 | 0
| TOTAL | 73999578.6037 | 56330481.7407 | -17669096.863 | 56311972.6704 | -18509.0703

## Analysis
Based on Apr'10 AFP 41 & Apr'10 CERT 41
All Variances Between AFP & Certificate
|  |  | 45444227.2746 | 29349175.246 | -16095052.0286
|  |  | Current |  |  |  | Current
Count |  |  | AFP | Cert | Diff | % | % of Difference
1 |  | MOS | 148018.0029 | 13168.49 | -134849.5129 | -91.1% | 8.567%
1 |  | Entitlement | 13244871.0446 | 1109426 | -12135445.0446 | -91.62% | 771%
1 |  | tie Deductions | -15000 | -794933.16 | -779933.16 | 5200% | 49.55%
19 |  | Enabling | 7625105.0585 | 6582675.5197 | -1042429.5389 | -13.67% | 66.23%
13 |  | Measure | 15053500.5385 | 13484290.8 | -1569209.7385 | -10.42% | 99.69%
6 | 0 | Sep'08 Settlement | 34833.2367 | 5970.6502 | -28862.5865 | -82.86% | 1.834%
5 |  | Bypass | 687594.4691 | 69840 | -617754.4691 | -89.84% | 39.25%
1 |  | A8 Sewer | 1859297.75 | 1792924 | -66373.75 | -3.57% | 4.217%
18 |  | NPO | 488456.5676 | 392156.4338 | -96300.1338 | -19.72% | 6.118%
1 |  | Other (Non WS) | 31087.6416 | 21393.5616 | -9694.08 | -31.18% | 0.6159%
11 |  | Other (WS) | 174629.0565 | 71289.7583 | -103339.2982 | -59.18% | 6.565%
1 |  | CCTV | 547070.28 | 495000 | -52070.28 | -9.518% | 3.308%
4 |  | Logistic Support | 837752.848 | 641401.489 | -196351.359 | -23.44% | 12.47%
15 |  | Slew Utilities | 88296.7112 | 27840.5838 | -60456.1274 | -68.47% | 3.841%
1 |  | Mound Gas Main | 572981.872 | 415288 | -157693.872 | -27.52% | 10.02%
7 |  | Disrupted Plant | 181258.7567 | 7269 | -173989.7567 | -95.99% | 11.05%
1 |  | Artificial Obstruction | 10167.8179 | 10167.8179 | 0 | 0% | 0%
11 |  | Supply Connections | 146701.9274 | 0 | -146701.9274 | -100% | 9.32%
1 |  | Demolish Chamber | 40286.7177 | 23423.4876 | -16863.2301 | -41.86% | 1.071%
21 |  | Utility Abandonment | 276692.1191 | 43126.9382 | -233565.181 | -84.41% | 14.84%
3 |  | Exc Abandonment | 57558.4558 | 10344.6387 | -47213.8171 | -82.03% | 3%
800 |  | Agreed(*) | 0 | 0 | 0 | 0% | 0%
1897 |  | Agreed | 31908417.7317 | 31908417.7317 | 0 | 0% | 0%
2839 |  | TOTAL | 28555351.3291 | 26981306.4947 | -1574044.8344 | -5.512% | 100%
2839 |  | Check against actual totals (April AFP/Cert) | 74854162.2125 | 56311973.8531 | -18542188.3594 |  | 1178%
|  | Check | -46298810.88 | -29330667.36 | 16968143.525
2839 |  |  | Current |  |  |  |  | Comments
Change Control | Work Date | Description | AFP | Cert | Diff | % | Category | tie | CUS | Schedules |  |  | Progress |  | tie Mar cert | variance
CR 1-50 | [6 empty] | Agreed(*)
1 |  | Sewer CCTV | 547070.28 | 495000 | -52070.28 | -9.518% | CCTV |  |  | 3rd >£10k | [6 empty] | SW | 100
2 |  | Survey of Sewer Manholes at Gogar Depot | 2961 | 2961 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
3 |  | Survey of Gas Steel Service Pipes up to 15/06/07 | 3185 | 3185 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
4 |  | PC Services; Martin Meehan (Susan Clark). Working days | 9483.29 | 9483.29 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
5 |  | Provide 5 nr vehicles for the exclusive use of tie staff | 28483 | 28483 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email | £5k not certified Mar | 22993.96 | -5489.04 | Gen
6 |  | Provide 4 No. Additional telephone handsets for tie site offices | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
7 |  | Proposed temporary extension to Ingliston Park and Ride | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
7 |  | Trial Investigations at car park. Limit of authority to spend = £6,000 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
8 |  | SDS Trial Holes - Under Review. AMIS rates submitted to SDS, AMIS awaiting CN before estimate can be raised | 0 | 0 | 0 | 0% | Agreed |  |  | AS
9 |  | PC Services - Requirement of Management input to Design Detail and Definition (RATS process). | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
10 |  | tie office requirements - vehicles & IT (Dedicated printer / scanner) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
11 |  | Construction Services Programme Rev.001 imposing Stakeholder requirements | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
12 |  | MUDFA trial holes - proposals | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
13 |  | Electronic copies of Non-PCS Deliverables | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
14 |  | Traffic Management - Specialist Support | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
15 |  | EARL Design and Construct; mobilisation / outline design and planning | 18211 | 18211 | 0 | 0% | Agreed |  |  | AS
16 |  | Increased stock holding to offset preliminary design risk and safeguard production | 0 | 0 | 0 | 0% | Agreed |  |  | AS
17 |  | Emergency Works - IPR; as substantiated in the January 07 Application | 4487.46 | 4487.46 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
18 |  | Replacement of steel gas pipes required following surveys carried out under Change No. 3 above. | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
19 |  | tie additional subsistence and support | 175 | 175 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
20 |  | SDS Design Drawings reproduction | 1581.24 | 1581.24 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
21 |  | Removal of contaminated material - Casino Square (P. Sum 2/5/h) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
22 |  | Team Building Event; assessment. Shared cost (50:50) | 1846.66 | 1846.66 | 0 | 0% | Agreed |  |  | AS
23 |  | Additional Period reports; 13 per annum as opposed to 12 per annum | 0 | 0 | 0 | 0% | Agreed |  |  | AS
24 |  | St. Andrews Square; additional non MUDFA works | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
25 |  | Transfer of responsibility for Scottish Power works to AMIS | 326230.8058 | 326230.8058 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
25.2 |  | Purchase cable for Haymarket | 16777.9066 | 16777.9066 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SP
25.3 |  | Storage costs and balance of power cables | 21250.816 | 21250.816 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SP
25.4 |  | Puchase additional cable for York Pl | 97945.8944 | 97945.8944 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SP
26 |  | Provision of survey resources to support BT Openreach | 9491.984 | 9491.984 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
27 |  | Programme Revision 03 (Stakeholder imposed programme) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
28 |  | GOGAR - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
29 |  | Water services survey for earthing of properties - full length of route for lines 1 and 2. | 14762.2778 | 14762.2778 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
30 |  | Ingliston Depot - AMIS/Purvis design costs | 6000 | 6000 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
31 |  | Archaeological watching brief during excavation works. | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
32 |  | Additional accommodation and facilities required for tie personnel. | 10432.4186 | 10432.4186 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
33 |  | New badger set | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
34 |  | Unknown manhole surveys | 2546 | 2546 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
35 |  | Tram Logo's on pedestrian barriers | 2040 | 2040 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
36 |  | Tram Logo's on protective clothing | 449 | 449 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
37 |  | Reinstatement trial area | 5443 | 5443 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
38 |  | Standing time for site vehicles - no continuity of site works | 2024 | 2024 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
39 |  | Hygiene Training for tie & SDS personnel | 305 | 305 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
40 |  | Wrong fuel in tie vehicle | 255 | 255 | 0 | 0% | Agreed |  |  | AS
41 |  | Comms Room Security & Air-Conditioning | 0 | 0 | 0 | 0% | Agreed |  |  | AS
42 |  | Programme Revision 05 Stakeholder Constrained (formerly Imposed) Programme | 0 | 0 | 0 | 0% | Agreed |  |  | AS
43 |  | Testing for contaminated land at Leith Docks Area | 14497 | 14497 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
44 |  | AMIS MUDFA - Additional support to SDS provider (TUD's & TQ's) | 21687.16 | 21687.16 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
45 |  | Supply dedicated letter drop subcontractor and distribute customer information packs for each Work Order | 23695 | 23695 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
46 |  | Temporary Accomodation Requirements (Alteration to tie office fittings) | 1050 | 1050 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47 |  | WORK ORDER 1A-03-01 (Ocean Drive) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48 |  | WORK ORDER 1B-01-01 (Leith Walk) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
49 |  | Additional support to manage Symology system |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
50 |  | 1% uplift for 5 year defects correction period |  |  | 0 | 0% | Agreed |  |  | AS
CR 51-100 | [6 empty] | Agreed(*)
51 |  | Princes Street Trial Holes (Part 1) | 6939.1575 | 6939.1575 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
52 |  | Leith Walk Trial Holes | 205553.546 | 205553.546 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
53 |  | OCIP Insurance now in place, AMIS insurance cover no longer required (2.8% value up to and including 22/07/2007) | 70882.75 | 70882.75 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | TL/JC agreed 26/05 |  |  |  | Gen
54 |  | Archaeological watching brief during excavation works. | 124562.4 | 124562.4 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
55 |  | Provide Testing Facilities |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
56 |  | Schedule 13 impact on construction activities |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
57 |  | Delay & Disruption | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | D&D
58 |  | Doocey - Additional Costs |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
59 |  | Additional gas service surveys (Whole Route, Line 1 & line 2) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
60 |  | Trial Holes - Gogar (Section 7A) on lay-bye, 2# requested by tie | 3240.517 | 3240.517 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
61 |  | Inspection of Crawley Tunnel | 3767 | 3767 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW & SGN
62 |  | Bill rate adjustments |  |  | 0 | 0% | Agreed |  |  | AS
63 |  | Staff Procurement |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
64 |  | Pre-programme Rev 06 |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
65 |  | Co-ordinates for Street Furniture | 60 | 60 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
66 |  | Scrap materials | -6412 | -6412 | 0 | 0% | Agreed |  |  | AS
67 |  | Additional AMIS insurances required since not included in tie OCIP |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
68 |  | Contaminated soil testing in Leith Walk trial holes | 437 | 437 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69 |  | WORK ORDER 5A-08-02 (Roseburn) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
70 |  | Additional AMIS input into SUC & stakeholder interfaces |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
71 |  | Labour cost uplift not covered in previously allocated late construction start items |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | D&D
72 |  | Scottish Power Tunnel full investigation pending. Outcome will determine impact on MUDFA works |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP | 100
73 |  | Supply on call plumber for dealing with client connections | 3374 | 3374 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
74 |  | Morrison Street trial holes, facilitate with EICC extension (inc 74.2) |  |  | 0 | 0% | Agreed |  |  | AS
74.2 |  | Morrison St. utility diversion for EICC extension. Additional non-MUDFA works | 17055 | 17055 | 0 | 0% | Agreed |  |  | AS | [6 empty] | TBA
75 |  | WORK ORDER 6A-01-01 (Gogar MUDFA) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
76 |  | Princes Street Trial Holes - Part 2 | 5891 | 5891 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
77 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
78 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
79 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
80 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
81 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
82 |  | Accomodation for tie Limited is currently 21#, the AMIS tender included allowance for 10#. Additional is partly addressed under Clause 46. Remainder will be addressed under re-phased prelims | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd >£10k | [6 empty] | Gen
83 |  | DKE, GML & LOD to be marked out by independent contractor (not AMIS responsibility) | 10576.72 | 10576.72 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
84 |  | Risk provisions when Work Order protocol as detailed in the Contract is not followed |  |  | 0 | 0% | Agreed |  |  | AS
85 |  | Trial Holes in Shandwick place (Part 1) | 4913 | 4913 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
86 |  | Trial Holes in Princes Street (Part 3) | 52191.6317 | 52191.6317 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
87 |  | Damaged toby covers / valve covers |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
88 |  | Testing of power cables following installation and before jointing | 1980.16 | 1980.16 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
89 |  | WORK ORDER 1C-01-02 (Princes St) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90 |  | WORK ORDER 1D-05-02 (Princes St) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
91 |  | Confirmation of Road Make-up at St.Andrews Square Start date | 1076.7174 | 1076.7174 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
92 |  | Scottish Water standard details confirmed Scottish Water Std Cover details |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
93 |  | Use of ductile iron tees on PE pipes due to sizing |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
94 |  | Trial Holes in Shandwick Place (PART 2) | 90325.1718 | 90325.1718 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
95 |  | Empty skip at Stead Place | 280.704 | 280.704 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
96 |  | Performance Bond no longer required reduce Contract Value accordingly (-£70k) | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed TL/JC 11/03
97 |  | Delay & Disruption resulting in weekend working | 5921.6358 | 5921.6358 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
98 |  | Scottish Power Map Access & Smartrass; to install on AMIS computers | 190.4 | 190.4 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
99 |  | WORK ORDER 1C-02-01 (St Andrew Square) - SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100 |  | WORK ORDER 1C-02-01; SEPARATE REGISTER |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
CR 101-132 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
102 |  | Vehicle Damages (tie vehicles) | 68.7 | 68.7 | 0 | 0% | Agreed |  |  | AS
103 |  | WORK ORDER RAT 7A/02/01 | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
104 |  | Inspect Arch of Bridge and dig trial holes | 1428.85 | 1428.85 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
105 |  | St Andrew Square Trial Holes (Part 2) | 26981.9934 | 26981.9934 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107 |  | WORK ORDER 1B/02/01 | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
110 |  | Constitution Street Trial Holes | 97813.1669 | 97813.1669 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
111 |  | Stationary for printing drawings for Work Orders | 340.4134 | 340.4134 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
112 |  | Trial hole to confirm depth of 275KV transmission cables @ Edinburgh Park Stn | 1158.3651 | 1158.3651 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
113 |  | Additional Trial Hole @ Request of tie | 541.7247 | 541.7247 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
114 |  | Escalation of labour costs as part of agreed settlement | 144769.52 | 144769.52 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
115 |  | Reliance on stop/start sub-contract labour extra over costs | 130000 | 130000 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
116 |  | Potential indexation related to revised spend profile | 250000 | 250000 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
117 |  | Underecovery of overheads | 198000 | 198000 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
118 |  | Additional recruitment costs | 10880.95 | 10880.95 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
119 |  | Delay & Disruption to Princes Street works (1C/01/02 & 1D/05/02) | 7522.91 | 0 | -7522.91 | -100% | Sep'08 Settlement |  |  | 3rd | Item certified by tie at time of Sep'08 settlement | 7522.91 | JC said S Bell dealing with 11/03 |  |  |  | Gen
120 |  | Provision of an external Planning Manager & Managing QS - Included in CC109 |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
121 |  | De-mobilise city centre works 1 week prior to planned date | 10945.62 | 0 | -10945.62 | -100% | Sep'08 Settlement |  |  | 3rd >£10k | Item certified by tie at time of Sep'08 settlement | 10945.62 | JC said S Bell dealing with 11/03 |  |  |  | Gen
123 |  | Construct stage for tie promotional video | 2166.9913 | 2166.9913 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
124 |  | Additional Traffic Management Signage | 4355.4979 | 4355.4979 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
126 |  | GPS Projection based on Local Grid Co-ordinates to be carried out by L&M Surveys | 2392.24 | 2392.24 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
127 |  | Shandwick Place to Haymarket (Trial Holes) | 49704.3781 | 49704.3781 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
128 |  | Supply & install taxi stance signs | 1366.4736 | 1366.4736 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
130 |  | Repair pot holes to road in front of MUDFA offices | 4963.23 | 4963.23 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
131 |  | Remove Princes St mass barrier on 31/12/07 & replace on 03/01/08 | 4580.9152 | 4580.9152 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
[5 empty] | 0 | 0%
CR 133-164 | [6 empty] | Agreed(*)
133 |  | AMIS to instruct Chubb to continue for 4 weeks from Friday 9th Nov 2007 (MOVED FROM GOGAR 28.4) | 4641.408 | 4641.408 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
134 |  | Wider area signage & auxiliary signage | 23890.066 | 23890.066 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
135 |  | Part of global claim |  |  |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
136 |  | Supervision required for Work Sites on Weekends | 10000 | 10000 |  | 0% | Agreed |  |  | 3rd >£10k |  |  | TL/JC agreed 26/05 |  |  |  | Gen
137 |  | Supervision required for Change Control Items on Weekends & Nightshifts | 1000 | 1000 |  | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | Gen
138 |  | Call out cover for Gogar Depot Site over Xmas and New Year holiday period | 2176 | 2176 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
139 |  | Captured in re-measure |  |  |  | 0% | Agreed |  |  | AS
140 |  | Relalign and strengthen fencing Heras fencing at Gogarburn Depot | 3563.2 | 3563.2 |  | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
142 |  | Vehicle for tram helpers | 5677.6301 | 5677.6301 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
144 |  | ON SEPARATE REGISTER |  |  |  | 0% | Agreed(*) | [9 empty] | Gen
145 |  | Extra over on materials for using tactile slabs where necessary | 3471.9386 | 3471.9386 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
147 |  | Trial Holes (Haymarket - Network Rail) | 2374.3533 | 2374.3533 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
151 |  | Street Furniture (***SEE SEPERATE REGISTER***) |  |  |  | 0% | Agreed(*) | [9 empty] | Gen
152 |  | Hire of MASS Barrier | 1041894.5274 | 1041894.5274 |  | 0% | Agreed |  |  | top 14 |  |  | TL/JC agreed 26/05 |  |  |  | Gen
155 |  | Excavate 3 Trial Holes in Gyle Car Park to route prove for 450mm Water and HV cable. | 894.3582 | 894.3582 |  | 0% | Agreed |  |  | AS | [6 empty] | SW & SP
159 |  | Damage to laminating machine | 126 | 126 |  | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
161 |  | Supply of 12 temporary NAL foundation blocks | 4243.2 | 4243.2 |  | 0% | Agreed |  |  | AS | [6 empty] | Gen
162 |  | Class one call out to re-erect Gogar Depot Herras Fence 23/02/08 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | Part of Agreed Schedule | 0 | Agreed CUS reduce by £359 TL/JC 11/03 |  |  |  | SW | 100
[5 empty] | 0 | 0%
CR 165-196 | [6 empty] | Agreed(*)
165 |  | Installation of bases and sleeves for various sign posts | 14056.8847 | 14056.8847 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
167 |  | Under-recovery on fuel, oil, small tools and mobile phone for Change Control items (i.e. Not recovered when CARP rates used) - withdrawn | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed TL/JC 11/03 |  |  |  | Gen
168 |  | Diversions over Leith Walk Rail Bridge | 13997.1158 | 13997.1158 | 0 | 0% | Agreed |  |  | top 14 |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
169 |  | 7B Design & Build | 183198.4954 | 183198.4954 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
171 |  | A8 Sewer Diversion | 1859297.75 | 1792924 | -66373.75 | -3.57% | A8 Sewer |  |  | top 14 | [6 empty] | SW | 100
172 |  | Continue hire of office complex, generators and toilet unit to | 20406.1332 | 20406.1332 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
173 |  | Litter collection (Leith Walk) | 14492.06 | 14492.06 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
174 |  | Non-domestic rates summary warrant | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
176 |  | Reforcasting of prelims to align Rev 07 programme | 0 | 0 | 0 | 0% | Agreed |  |  | AS
177 |  | 7A Sewer Flow Monitoring | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
178 |  | Additional SUC Administration Requirements | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
179 |  | Assist Siemens with installation of Pedestrian crossings | 1217.5699 | 1217.5699 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
180 |  | Provide road sweeper after accident on guided bus route 30/06/08 | 132.975 | 132.975 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
181 |  | Cable Jointing LV Power | 10800 | 10800 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | TL/JC agreed 26/05 |  |  |  | SP
182 |  | Use of foam concrete due to spacing and congestion of both existing and new utilities making compaction using Type 1 impractical and unlikely to achieve the required compaction. | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed TL/JC 11/03 |  |  |  | Gen
184 |  | Support teams for BT manhole inspections (2 teams) | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed TL/JC 11/03 |  |  |  | BT | 100
186 |  | Purchase of Traffic Management signage | 42236.073 | 42236.073 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
187 |  | Remedial works due to failure of B0 backfill | 0 | 0 | 0 | 0% | Agreed |  |  | top 14 |  |  | Agreed TL/JC 11/03
188 |  | Additional cost of labour standing down during August 08 embargo | 56225.9913 | 56225.9913 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
191 |  | Gogar 1500 sewer; construction of new site entrance/access - not progressed | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
193 |  | Noise monitoring - withdrawn | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed TL/JC 11/03
194 |  | Section 1B - Grouting up of abandoned Sewer | 3463.92 | 3463.92 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
195 |  | Scottish Power Revised Duct Specification | 0 |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP | 100
196 |  | Make good defects in the road- Shandiwck Pl & Lothian Rd. junction. Estimate only - not carried out | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
CR 197-228 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
199 | 39668 | tie Road Traffic Offences (RTO's) | 130.56 | 130.56 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
200 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
201 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
202 |  | Late Payment of AFP No.21 | 0 | 0 | 0 | 0% | Agreed |  |  | AS
203 |  | Works to meet Embargo Restrictions including backfill of trenches / excavations that will require re-opening and demobilisation of affected sites | 119000 | 119000 | 0 | 0% | Agreed |  |  | top 14 |  |  | Change to agreed JC/TL 11/03 |  |  |  | Gen
204 | 39773 | IMP Application 30723 - Undertake CCTV surveys of all drainage systems between plates 22 and 35 (1B-02-01 to 1C-04-01) | 699.04 | 699.04 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
205 | 39753 | Contract Wide Standard Details, Specification and TQ's | 0 | 0 | 0 | 0% | Agreed(*)
206 |  | Prima Testing = Compressive Strength (various locations) | 0 | 0 | 0 | 0% | Agreed(*)
207 |  | Baxters Place Survey | 2943.04 | 2943.04 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
208 |  | Legislative change for excavated contaminated material | 0 | 0 | 0 | 0% | Agreed(*)
209A | 39753 | Additional Traffic Management Works Nov 08 to Aug 09 | 226999.999 | 226999.999 | 0 | 0% | Agreed |  |  | top 14 |  |  | Change to agreed JC/TL 11/03 |  |  |  | Gen
209B |  | Additional Traffic Management Works For Sept '09 charged at 50% | 9668.7078 | 9668.7078 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
209C |  | Additional Traffic Management Works For Oct, Nov, Dec '09 | 35024 | 35024 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
209.35 | 39852 | Install 24 No. RII poles to George Street, | 13798 | 13798 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | TL/JC agreed 26/05 |  |  |  | Gen
210 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
211 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
212 | 39802 | Additional TM costs over Christmas period | 4721.3216 | 4721.3216 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
213-226 |  | Enabling works, see separate register | 0 | 0 | 0 | 0% | Agreed(*) |  |  | top 14
227 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
228 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
229 |  | Supply SP ducts to Infraco | 1218.1683 | 1218.1683 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
230 |  | Hire of Rhino Barrier for the Mound | 31087.6416 | 21393.5616 | -9694.08 | -31.18% | Other (Non WS) |  |  | new | [6 empty] | Gen
231 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
232 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
233 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
234 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | SGN
235 |  | Procure 1x315mm branch saddle from Radius systems. | 882 | 882 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
236 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | MOS
237 |  | Excess MOS tie responsibility | 148018.0029 | 13168.49 | -134849.5129 | -91.1% | MOS |  |  | new
238 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
239 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
240 |  | Refer to CC153.176 | 0 | 0 | 0 | 0% | Agreed(*)
241 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
242 |  | CCTV survey of road gullies in St Andrews Sq and Shandwick Pl. | 937 | 937 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
243 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
244 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
245 |  | Provide 2 men plus vehicle to transfer boxes from leith offices to City Point | 495.04 | 495.04 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
246 |  | Assessed Elsewhere (see Master Change Control Register) | 0 |  |  |  | Agreed(*)
247 |  | CUS instructed by G. Barclay (tie) to pick up & transport a tie printer from the airport to MUDFA offices. | 78.5318 | 78.5318 | 0 |  | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
248 |  | Hire of Propping for Baxters Place underground Structure. Labour aspect claimed under CC189. Reallocated from CC221.10 | 3673 | 3673 | 0 |  | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
249 |  | Additional Temporary Backfill & Reinstatement o/s Tiles Bar as instructed by Frank McFadden (tie Infraco). | 225.0963 | 225.0963 | 0 |  | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 3536806.2174 | 3508643.6074
250 |  | Damage to vehicles supplied for use by tie | 1086 | 1086 | 0 |  | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
251 |  | Extra Over Replacement of Lead Water Supply connections on Leith Walk. | 101837.7096 |  | -101837.7096 |  | Supply Connections |  |  | new | [6 empty] | SW
|  |  | 0 | 0 | 0 | 0%
CR 47 | [6 empty] | Agreed(*)
47.1 |  | Did not materialise | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.2 |  | Work Order 1A-03-01, Unchartered Services | 682.221 | 682.221 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.3 |  | LABOUR UPLIFT (until 12/10/07 @ 100%) | 57823.8925 | 57823.8925 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.4 |  | To be concluded |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.5 |  | Work Order 1A-03-01, Prima 100 LWD testing services | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.6 |  | Work Order 1A-03-01, Delays (CVI) | 8466.7856 | 8466.7856 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.7 |  | Work Order 1A-03-01, Saturday & Sunday Working | 1336.8652 | 1336.8652 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.8 |  | Work Order 1A-03-01, Delays (CVI) | 8605.584 | 8605.584 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.9 |  | Work Order 1A-03-01, Delays | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.10 |  | Work Order 1A-03-01, Delays (CVI) | 22277.5206 | 22277.5206 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
47.11 |  | Work Order 1A-03-01, Delays (CVI) | 4225.6022 | 4225.6022 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.12 |  | Cable pulling, testing, jointing, & terminating cable Purchase power cables | 57167.4586 | 57167.4586 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
47.13 |  | Work Order 1A-03-01, Delays (CVI) | 11604.7603 | 11604.7603 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.14 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.15 |  | Work Order 1A-03-01, Abandonment of Forth Ports cables affecting diversions 1A/FPP/D/06, 07, 08, 09 & 10 | 6939.6542 | 6939.6542 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.16 |  | Work Order 1A-03-01, Delays for Artificial obstructions & Unchartered utilities | 5575.8458 | 5575.8458 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.17 |  | Work Order 1A-03-01, Delays for Artificial obstructions | 5222.1421 | 5222.1421 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.18 |  | Work Order 1A-03-01, Delays for Artificial obstructions, demolishing chambers, & trial holes | 9456.6243 | 9456.6243 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.19 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.20 |  | At Casino Trial Site to insert Protectaline through sleeves | 3880.5696 | 3880.5696 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.21 |  | Work Order 1A-03-01, Delays for Artificial obstructions, demolishing chambers, & trial holes | 6395.8926 | 6395.8926 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.22 |  | Work Order 1A-03-01, Supply & Install Scottish Water frame & covers | 825.6387 | 825.6387 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.23 |  | Reinstate granite setts and boundary wall at casino | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
47.24 |  | Work Order 1A-03-01, Artificial obstructions | 1300.0745 | 1300.0745 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.25 |  | Work Order 1A-03-01, Abandoned Work & Power Supply Connections | 22107.715 | 22107.715 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
47.26 |  | Work Order 1A-03-01, Remove and replace kerbs & Unchartered services | 1633.875 | 1633.875 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.27 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS
47.28 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS
47.29 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.30 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.31 |  | Work Order 1A-03-01, Artificial obstructions & Unchartered utilities | 3215.6454 | 3215.6454 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.32 |  | Temporary connection to Forth Ports water supply | 674.2989 | 674.2989 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.33 |  | Protectaline pipe required for dealing with Contaminated land (Also see CR 47.20) | 4691.3363 | 4691.3363 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.34 |  | To be concluded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
47.35 |  | Various CVI's | 1560.4295 | 1560.4295 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.36 |  | Additional valves etc | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.37 |  | Supply generator for Casino during FPP diversions and installations | 1640.16 | 1640.16 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.38 |  | Concrete slab over diversion (C/way rate claimed in lui) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.39 |  | Remove & replace kerbs | 4326.3084 | 4326.3084 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.40 |  | Remove artificial obstructions | 289.5473 | 289.5473 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.41 |  | New Thus diversion | 0 | 0 | 0 | 0% | Agreed |  |  | AS
47.42 |  | Proceed FPP water meter and connections | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
47.43 |  | Various re-measure items | 0 | 0 | 0 | 0% | Agreed |  |  | AS
47.44 |  | DISRUPTED PLANT ITEMS | 6214.5723 | 6214.5723 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 139361.1876 | 139361.1876
Gen
CR 48 | [6 empty] | Agreed(*) | [9 empty] | Gen
48.1 |  | Additional Signage Request | 3678.7623 | 3678.7623 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.1 p2 | Estimate | Additional Signage Request | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.1 p2 b |  | Supply 10 no. signs 'All Shops Open For Business As Usual'. Price amended to exclude erection and maintenance. | 272 | 272 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.1 p3 |  | Supply 4 no. signs for the wider area signage covering Piccardy Place and Great Junction Street | 1025.2006 | 1025.2006 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.3 | Estimate | Supply Operatives to Facilitate Working with Network Rail (Estimate, claimed in 48.3a) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW
48.3a |  | Supply Operatives to Facilitate Working with Network Rail | 4189.2807 | 4189.2807 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
48.6 | Estimate | Abandonment of 8" CI Scottish Water Estimate, claime din 48.6a) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW
48.6a |  | Removal of Cast iron Water pipe | 344.5969 | 344.5969 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.6b | 39377 | Remove further 44m of 6" CI water pipe (total removed to date 91m) | 399.3722 | 399.3722 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.6c |  | Remove 11.4m of 8" CI water pipeand 5.8m of 12" CI water pipe. (total removed to date 91m 6", 11m 8", 6m 12") | 368.6513 | 368.6513 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.7 | Estimate | Loss in productivity (15%) (estimate) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT
48.8 |  | Works to allow Water Main Abandonment | 6465.0645 | 6465.0645 | 0 | 0% | Utility Abandonment |  |  | 3rd | [6 empty] | Gen
48.9 |  | Re-dig of Trial Hole due to Apparatus in Planned BT Chamber Position | 245 | 245 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
48.11 |  | Concrete in Trench | 539 | 539 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.12 |  | Delays for Uncharted Utilities - 3 11KV Cables found in intended trench | 4696.9349 | 0 | -4696.9349 | -100% | Sep'08 Settlement |  |  | 3rd | Item certified by tie at time of Sep'08 settlement | 4696.9349 | JC said S Bell dealing with 11/03 |  |  |  | Gen
48.13 |  | Trial holes | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW | 100
48.14 | Estimate | Uplift on Labour Rates (delay in original procurement) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.15 |  | Upfront Valve Survey | 238 | 238 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW | 100
48.16 |  | Removal of Central Reserve | 4766.9975 | 4766.9975 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.16a | Estimate | Removal of Leith Walk Central Reserve | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.16b | 39365 | Remove Central Reserve and Kerb Outcrops on Leith Walk to facilitate Traffic Management | 161500 | 161500 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | JC/JC agreed email 18/05 |  |  |  | Gen
48.17 |  | Artificial Obstruction & Unknown Services | 1791.9115 | 1791.9115 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
48.18 |  | Soft Spot causing Collapse in Carriageway | 850 | 850 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.19 |  | Concrete in Trench | 943 | 943 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.20 |  | Trial holes | 724 | 724 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.21 |  | Unknown Services | 140 | 140 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.25 |  | Foam Concrete | 2504.032 | 2504.032 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | £2.5k not certified | 0 | -2504.032 | SW | 100
48.26 | 39361 | Due to Quantity of track excavated within a small worksite combined with poor existing road quality, the area of existing tar (by request from Highways Officer Williw Barker) has increased from originally anticipated nominal track widths | 10000 | 10000 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
48.27 | 0 | Due to high flow levels a specialist subcontractor is required a floating camera for the Sewer CCTV Surveys on Sections 1A, 1B, 2, 5A and 5C. | 5083.4901 | 5083.4901 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW | 100
48.30 | 39365 | Concrete in trench | 283 | 283 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | VM
48.31 | 39359 | Whilst excavating after heavy rain, depressions / voids appeared requiring digging out and backfiling | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.32 | 39371 | Demolish Virgin Media Box / Chambers | 1549 | 1549 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.33 | 39372 | Trial holes above original scope | 1519 | 1519 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.34 |  | Provision of Mass Barrier (NOT ESTIMATED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.35 | 39370 | Labour, Plant and Materials used to tie in pipes over and above that in tendered rates build-up (NOT ESTIMATED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.36 | 39385 | Demolish BT chambers and slew cables | 4285.7601 | 4285.7601 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
48.37 | 39386 | Excavate subsided area and backfill to 100mm below surface. Reinstatement under CVI 17857 | 1238 | 1238 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.38 | 39388 | Connection to 9" water main at McDonald Road required to be 15m long as opposed to the planned 5m length due to existing services. (VALUE CLAIMED AS REMEASURE OF ORIGINAL ITEM) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
48.39 | 39388 | Isolate water main to cease flow of water to allow diversion to continue | 295 | 295 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.40 | 39380 | Drill service to determine if live & lay extra duct | 2201 | 2201 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.41 | 39399 | Demolish existing chamber to build JF6 outside Leith Cycle Shop | 547 | 547 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.42 | 39398 | Removal and replacement of kerbs | 1314 | 1314 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.43 | 39398 | Concrete found in various excavations | 1183 | 1183 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | TW
48.44 |  | Backfill spec - no cost implications | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.45 |  | Build Telewest Cabinets (NOT PRICED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.46 | 39405 | Break out and rebuild old tunnel in road crossing including riveted steel plates to allow installation of BT ducts | 1377 | 1377 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.47 |  | All disrupted plant relating to 1B | 33994.6847 | 0 | -33994.6847 | -100% | Disrupted Plant |  |  | 3rd | [6 empty] | Gen
48.48 |  | Concrete around shallow water main (NO COST IMPACT) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
48.49 | 39412 | Remove kerb outcrops at demolition yard | 568 | 568 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.50 | 39412 | 4 no extra 300mm DI bends to alter diversion as per Scottish Water | 1176 | 1176 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.51 | 39412 | Hand digging due to nature of existing utilities | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT
48.52 | 39406 | Following prolonged heavy rain track had to be re-excavated to formation level | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.53 |  | Unable to build chambers (NOT PRICED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.54 | 39415 | Lift and relay blocks in collapsed area as per Ronnie Black | 151 | 151 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.55 | 39415 | Demolish chamber and slew cables | 1510 | 1510 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.56 | 39385 | Trial holes over and above original scope | 2722.3331 | 2722.3331 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | cert add £0.3k | 2454 | -268.3331 | Gen
48.57 | 39398 | To increase pressure in 4" CI water main at point of 1B/SW/D/390 hydrant | 2049.75 | 2049.75 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | SW | 100
48.58 | 39399 | Due to poor existing road surfacing AMIS had to reinstate additional carriageway over and above the original 1.0m wide track. | 1666 | 1666 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.59 | 39402 | Gas diversion at Shrubhill | 3170.9869 | 3170.9869 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.60 | 39413 | Extra reinstatetement of carriageway due to poor existing road condition. | 3804.6364 | 3804.6364 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.61 | 39405 | Removal of tunnel | 477 | 477 | 0 | 0% | Agreed |  |  | 3rd <£2k
48.62 | 39400 | Concrete and artificial obstructions | 10137.0995 | 10137.0995 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
48.63 |  | TQs & CVIs with no cost impact | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.64 | 39417 | Weekend works due to traffic management restrictions | 505 | 505 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.65 | 39416 | Concrete & Trial holes | 3140.1579 | 3140.1579 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | Gen
48.66 | 39421 | Investigative work due to services not appearing as per drawing. | 341 | 341 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.67 |  | Trial Holes (Included in Leith Walk trial holes) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.68 |  | Raising of BT ducts and lowering of SGN main (Included in 48.70) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
48.69 | 39419 | Additional works due to TQ-298. | 6524.55 | 6524.55 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
48.70 | 39426 | Lower 90mm gas main | 2653.065 | 2653.065 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
48.71 | 39422 | Gas connections | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | SP
48.72 | 39433 | Breaking out concrete. | 410 | 410 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.73 | 39433 | Widending Track to lay Scottish Power Insurance ducts. Ducts abandoned due to unchartered utulities. | 892 | 892 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.74 | 39433 | Removal of redundant wastewater chamber. | 1210 | 1210 | 0 | 0% | Agreed |  |  | 3rd <£2k
48.75 | 39433 | Artificial obstructions | 2003.5277 | 2003.5277 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | SW | 100
48.76 |  | Confirmation of bedding (NO COST IMPACT) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.77 | 39456 | Use of foam concrete to make safe shallow water pipes | 235 | 235 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.78 | 39454 | Downtime due to incorrect traffic management - Leith Walk / McDonald Road | 2684.9936 | 0 | -2684.9936 | -100% | Sep'08 Settlement |  |  | 3rd | Item certified by tie at time of Sep'08 settlement | 2684.9936 | JC said S Bell dealing with 11/03 |  |  |  | Gen
48.79 | 39457 | Downtime due to inclemant weather | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.80 | 39465 | Hand digging around existing services due to density of services in the area | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN | 100
48.81 | 39463 | Trial Hole | 245 | 245 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
48.82 | 39456 | Incorrect SGN maps and SDS IFC drawings resulted in excessive excavations to determine connection points | 1535 | 1535 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.83 |  | Removal of 6m of cast pipe and artificial obstruction | 255 | 255 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW | 100
48.84 | 39470 | Remove concrete BT duct & Remove redundant 4" cast pipe | 234 | 234 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.85 |  | Use of ductile tees as opposed to PE (NOT PRICED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.86 |  | Demolish CCTV box to allow 20 way duct to be layed (NOT PRICED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
48.87 | 39468 | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN | 100
48.88 | 39476 | Job abandoned due to SW failure to attend | 512 | 512 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW | 100
48.89 | 39469 | Delay caused by SGN gas leak | 420 | 420 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.90 | 39469 | Removal of Kerbs, Railing and Slabbing | 913 | 913 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.91 |  | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.92 | 39469 | Pilrig Street Traffic signals (LUX INCLUDED UNDER CC109.4) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.93 | 39112 | Artificial obstructions | 396 | 396 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.94 |  | Bus shelter moved by tie | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.95 | 39482 | Abortive works due to change in diversion | 900 | 900 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.96 | 39484 | Repair surface at Leith Walk (NOT CARRIED OUT YET 30/05/2008) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
48.97 | 39486 | Drill & remove 4" and 9" main | 80 | 80 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.98 | 39486 | Cleaning off encrustations on 12" gas main to install clip & valve x 2 | 691 | 691 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
48.99 | 39486 | Exposing of unchartered main and thrust blocks. Additional diversion around existing 9" main and thrust blocks. | 523 | 523 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.100 | 39503 | Removal of Artificial Obstruction | 2157.1202 | 2157.1202 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | SW
48.101 | 39485 | Delay waiting on answer to TQ. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW
48.102 | 39475 | Hand digging due to congested services | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
48.103 | 39489 | Removal of Artificial Obstructions and removal of redundant main. | 3881 | 3881 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP and cert changed | 3838 | -43 | Gen
48.104 | 39498 | Second excavation for Clip & Valve to be placed on 12" Gas Main due to main being damged in original location. | 2071.4672 | 2071.4672 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP -£1k | 2071 | -0.4672 | SGN
48.105 | 39493 | Relaying Kerbstones | 700 | 700 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP & cert change | 162 | -538 | Gen
48.106 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.107 | 39510 | Standing down time. | 158 | 158 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.108 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.109 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.11 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | SGN
48.111 |  | Trial holes at Network Rail Overbridge | 1977 | 1977 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.112 | 39512 | Remove cast redundant cast pipe | 1305 | 1305 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | TW
48.113 | 39512 | Cleaning gas main. | 1700 | 1700 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
48.114 | 39521 | Erecting Telewest cabinets on Balfour St. | 1992 | 1992 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP & cert changed | 1731 | -261 | TW
48.115 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.116 | 39524 | Artificial Obstructions | 2372.1495 | 2372.1495 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | Gen
48.117 | 39524 | Kerb Removal | 877 | 877 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.118 | 39535 | Supporting collapsed trench & xtra foam concrete required | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.119 |  | Non-MUDFA relateted mason work | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SW
48.12 | 39541 | Removal of artificial obstruction | 1937.2516 | 1937.2516 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
48.121 | 39535 | Sinking of existing manhole | 221 | 221 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
48.122 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.123 |  | Artificial obstruction | 614 | 614 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.124 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.125 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | BT
48.126 | 39569 | Removal of lamp posts | 3145.5821 | 3145.5821 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP changed | 3146 | 0.41792 | BT
48.127 |  | Demolish Chamber & Artificial Obstruction | 1014.0712 | 1014.0712 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 27/04 meeting | cert changed | 950 | -64.0712 | BT
48.127 | 39570 | Demolish Chamber & Artificial Obstruction | 1014 | 1014 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.128 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.129 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.13 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.131 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.132 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | SGN
48.133 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.135 | 39735 | Extra over items for supply connections coming of 180mm - now in measure | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k
48.136 | 39771 | Remove concrete | 0 | 0 | 0 | 0% | Agreed(*) |  |  | top 68 | [6 empty] | SGN
48.137 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | BT
48.138 | 39800 | Backfill SGN Holes | 312 | 312 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
48.139 | 39792 | Extra concrete on BT ducts. | 118 | 118 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.14 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.141 | 39864 | Additional reinstatement | 359 | 359 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.142 | 39840 | hand digging and removal of artificial obstruction | 207 | 207 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.143 | 39876 | Standing down time | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.144 | 39835 | Artificial obstruction | 2196.4389 | 2196.4389 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting |  |  |  | Gen
48.145 | 39847 | Excessive hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.146 |  | Standing down costs | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.147 | 39841 | Remove concrete | 909 | 909 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
48.148 | 39841 | Remove concrete | 3112 | 3112 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | AFP & cert change | 2597 | -515 | SP
48.149 | 39854 | Remove concrete. | 3814.9658 | 3814.9658 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/04 meeting | cert changed | 3222 | -592.9658 | Gen
48.150 |  | Delay encountered during re-design and acceptance of re-design of 275kV Scottish Power diversion. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new |  |  | CUS agree reduce by £12k since in D&D TL/JC 16/03
48.151 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | BT
48.152 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
48.153 | 39874 | Slew 4w BT duct | 1091 | 1091 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.154 | 39874 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
48.155 | 39882 | Remove BT Ducts | 2082.885 | 2082.885 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.156 | 39882 | Remove concrete | 1791.91 | 1791.91 | 0 | 0% | Agreed |  |  | AS |  |  | CUS agree reduce by £194 TL/JC 11/03 |  |  |  | SW
48.157 | 39882 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
48.158 | 39889 | Divert 4" Pipe | 5412 | 5412 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
48.159 | 39889 | Repair BT Ducts | 1200 | 1200 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
48.16 | 39882 | Re-divert 180mm Pipe | 13211.8653 | 13211.8653 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
48.161 | 39889 | Locating services to transfer | 7893.527 | 0 | -7893.527 | -100% | Supply Connections |  |  | new
48.162 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.163 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | SW
48.164 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | SW
48.165 |  | Excavating and fitting washout | 5415 | 5415 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
48.166 |  | Excavating to locate serivices opposite pilrig | 4352 | 4352 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | SW
48.167 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.168 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.169 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.170a |  | Excavating to install washouts WE 10/04/09 as allocation sheet 0579 | 3916.8 | 3916.8 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
48.170b |  | Excavating to install washouts WE 17/04/09 as allocation sheet 0587 | 2176 | 2176 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
48.171 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.172 |  | Fitting mechnical joints | 1765.0538 | 1765.0538 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
48.173 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.174 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.175 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.176 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.177 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
48.178 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
48.179 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SW
48.18 |  | Delay and disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
48.181 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.182 |  | Remove concrete | 588.6324 | 588.6324 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 27/04 meeting |  |  |  | SW
48.183 |  | Remove concrete | 450.6717 | 450.6717 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 27/04 meeting |  |  |  | SW
48.184 |  | Removal of temp reinstatement | 1167.4933 | 1167.4933 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 27/04 meeting |  |  |  | Gen
48.185 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.186 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.187 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.188 |  | Hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
48.189 |  | Gas Abandonment on Pilrig street (9'') | 27570.3543 | 0 | -27570.3543 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
48.19 |  | Hand digging due to unchartered utilities | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
48.191 |  | Supply connections over leith walk rail bridge | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | Agreed that now in measure email TL/JC 22/03 |  |  |  | SW
48.192 |  | Failed decay test (cut & cap) at Brunswick Place. Further trial hole investigations to prove network found water in the main, which required siphoned. Second decay test subsequently passed so cut & cap of 12" carried out. | 25302.5228 | 0 | -25302.5228 | -100% | Other (WS) |  |  | new | [6 empty] | SGN | 100
48.193 |  | Additional Trial Holes required to prove existing SGN Network at Balfour Street. (As per CUS letter 2829 & Technical Query 1593) | 3911.7637 | 3911.7637 | 0 | 0% | Agreed |  |  | new |  |  | Agreed at £3.9k TL/JC 16/03 |  |  |  | SGN
48.194 |  | Failed decay test due to dirt in the existing 12" C/I main (conflict 1B/LP/09) at Albert Place. CUS to employ specialist subcontractor to carry out foam bagging as per TQ 1567. | 3432 | 3432 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN | 100
48.195 |  | Measure of additional works requested under item 7 of Change Order 5316. | 4349 | 4349 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW | 100
48.196 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.197 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.198 |  | CUS required to investigate flood at basement of leith walk laundry, repair existing 4" main. | 920 | 920 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 27/04 meeting | Afp & cert changed | 0 | -920 | SW
48.199 |  | As per Item 8 of tie Change Order 5316: Additional 30 no. service connections due to pressure probems and condition of existing main. | 2178 | 2178 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SW
48.2 |  | Additional works for SW Water as per TQ: SW4 - Additional Fire Hydrant & 100mm SV. | 1922 | 1922 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
48.201 |  | Additional 2 no supply connections to No. 25 Crighton Place & one failed connection to existing lead supply entering building, resulting in flooding. | 1471.23 | 0 | -1471.23 | -100% | Supply Connections |  | CUS adjusted recently only failed supply connection over here | new | [6 empty] | SW | 100
48.202 |  | Albert Place - Cut and Cap of exisitng 12" C/I (conflict 1B/LP/09). | 11722.0806 | 0 | -11722.0806 | -100% | Utility Abandonment |  |  | new | [6 empty] | SW
48.203 |  | Bypass and decommissioning of conflict 1B/LP/32 at Balfour Street. | 8678.3223 | 0 | -8678.3223 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
48.204 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
48.205 |  | Service transfer (360 leith walk) | 2353.2282 | 0 | -2353.2282 | -100% | Supply Connections |  |  | new | [6 empty] | SGN
48.206 |  | Hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
48.207 |  | Additional 2 no. supply connections to 4 Crighton Place. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 20/05 |  |  |  | SW | 100
48.208 |  | Decay test to acertain pressure levels in main (CO 5320) | 672 | 672 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN | 100
48.209 |  | Demolish JRCX12 and rebuild JRF110 (CO 5463) | 3409 | 3409 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
48.21 |  | Blank plated abandoned clip and valve | 3304 | 3304 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
48.211 |  | Backfill joint bays due to incorrect IFC design | 5959.52 | 5959.52 | 0 | 0% | Agreed |  |  | new |  |  | CUS agree to exclude hand dig JC/TL 16/03 |  |  |  | SP
48.212 |  | Further to resolution of TQ 1568, CUS placed a 63mm Bypass to carry out the Cut & Cap of 12" cast iron (conflict 1B/LP/09) at Brunswick Place. | 8546.8155 | 0 | -8546.8155 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
48.213 |  | Abandon gas main at Shrub Hill (opposite Albert St) (claimed in 48.192) | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | CUS agree to recover in 48.192 TL/JC 18/05 |  |  |  | SGN
48.214 |  | Under pressure supply connections at Dalmany Street in order to facilitate additional BT works. | 4222.3757 | 0 | -4222.3757 | -100% | Supply Connections |  |  | new | [6 empty] | SW
|  |  | 0 |  | 0
CR 48.24 | [6 empty] | Agreed(*)
48.24.1 | 39377 | Uplift existing skip (left by others) and provide new skip for waste removal and tidy-up. | 280.704 | 280.704 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.24.2 | 39384 | Cut out 4 no power cables after scottish power confirmed dead. Break out old ducts. | 411.4688 | 411.4688 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
48.24.3 | 39385 | Break away cast duct from gas pipe to allow dropping of BT ducts. | 471.69 | 471.69 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.4 | 39391 | Shoring of excavation to ensure safety of operatives | 496.71 | 496.71 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
48.24.5 | 39391 | Locate joints along cable section and demolish old link box | 1464.1651 | 1464.1651 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
48.24.6 | 39392 | Divert Gas Main in order to allow building of manhole | 1980.889 | 1980.889 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.7 | 39407 | Purchase and Installation of H-beam frame to support existing apparatus and enable shuttering of excavation | 3957.1606 | 3957.1606 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.8 | 39393 | Concrete found in trial hole 39 trial hole for BT Manhole 404 | 79.0591 | 79.0591 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.9 | 39396 | Carry out additional SPEN cable diversions | 8284.6467 | 8284.6467 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
48.24.10 |  | Street Lighting & Traffic Contol Works (NOT PRICED YET) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 293782.4265 | 252405.8133
48.24.11 | 39370 | Demolish existing manholes for new 1B/BT/511 and new 1B/BT/512 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.12 | 39370 | Disrupted plant for all CCs relating to RAT 1B/01 | 2484.4699 | 2484.4699 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.13 |  | Delay & Disruption to BT Chamber Works | 15000 | 15000 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.14 | 39414 | Failed 7" water main next to excavation for BT manhole |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
48.24.15 | 39427 | Move shuttering of manhole by 100mm to avoid existing sewer. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
48.24.16 | 39434 | Slewing of BT ducts. | 11389.2058 | 11389.2058 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.17 | 39434 | Demolish BT manhole. | 30170.5088 | 30170.5088 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.18 | 39436 | Use of platiciser. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
48.24.19 | 39436 | Additional Hours in order to meet imposed deadline. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
CR 69 | [6 empty] | Agreed(*)
69.1 |  | Work Order 5A-08-02 - Aborted Trial Hole | 245.3658 | 245.3658 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.2 |  | Work Order 5A-08-02 - Demobilise Traffic Management over weekend of Rugby International | 1215.8427 | 1215.8427 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.3 |  | to be confirmed if required |  |  | 0 | 0% | Agreed |  |  | AS
69.4 |  | to be confirmed in CVI |  |  | 0 | 0% | Agreed |  |  | AS
69.5 |  | Work Order 5A-08-02, Demobilise Traffic Management over weekend of Rugby International | 11001.2907 | 11001.2907 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.6 |  | Work Order 5A-08-02 - Artificial obstructions | 11604.7603 | 11604.7603 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.7 |  | Work Order 5A-08-02, Demobilise Traffic Management over weekend of Rugby International | 3000 | 3000 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  | 2923 | -77 | Gen
69.8 |  | will be captured in re-measurement |  |  | 0 | 0% | Agreed |  |  | AS
69.9 |  | GS |  |  | 0 | 0% | Agreed |  |  | AS
69.10 |  | LABOUR UPLIFT (until 12/10/07 @ 50%) | 7375.8349 | 7375.8349 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.11 |  | Work Order 5A-08-02, Demobilise & Remobilise Work Site | 8932.7003 | 8932.7003 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
69.12 |  | Work Order 5A-08-02, Artificial obstructions | 273.0532 | 273.0532 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 43648.8479 | 43648.8479
69.13 |  | Work Order 5A-08-02, Supply Cable to Scottish Power Spec. | 4201.6384 | 4201.6384 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
69.14 |  | Slewing cable | 446.2309 | 446.2309 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
[5 empty] | 0 | 0%
CR 75 | [6 empty] | Agreed(*)
75.1 | 39331 | Break out concrete for C&W diversion including concrete under Motorway signs and concrete at 3 road crossings. | 3879.4472 | 3879.4472 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.7 | 39337 | Remove concrete from Police Layby section of roundabout for C&W diversion | 597.3038 | 597.3038 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.8 | 39337 | Ductwork found on C&W cable not to C&W spec therefore required replacing | 298.3725 | 298.3725 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.9 | 39330 | Dismantle and re-erect signs to allow C&W slewing exercise | 1962 | 1962 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.11 | 39337 | Trial holes on twin 600mm diameter water main | 312.7347 | 312.7347 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
75.12 | 39365 | Remove block pavers 17.5m x 1m at police layby and transport and store at concrete slab area for later use. | 282.24 | 282.24 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
79.13 | 39338 | Remove and breakout overspill of concrete from manhole to expose existing ducts | 95.5686 | 95.5686 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
75.14 | 39338 | C&W duct to be uncovered over 1m deep for 230m. Average extra depth at 0.5m | 1858.032 | 1858.032 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.16 | 39352 | Purchase of cable for SP diversion | 10755.3152 | 10755.3152 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
75.20 | 39336 | Two trial holes either side of SGN Gas Main to confirm C&W depth | 304.1212 | 304.1212 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.22 | 39337 | Erect Herras Fence c/w debris netting at police ramp | 952.74 | 952.74 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
75.24 | 39351 | 100mm steel duct found along BAA acccess road (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
75.25 | 39366 | Break out reinforced concrete and old foundationd of ex Inkworks | 1839.4762 | 1839.4762 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
75.26 |  | Uplift on Labour rates for delay in original procuement and procuement strategy (NO COST) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
75.27 |  | 250mm DI crossing HP gas main (methodology only) (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
75.28 |  | 250mm DI crossing twin 600mm water main (Methodology only) (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
75.29 |  | Cable testing (Orion) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
75.30 |  | All disrupted plant relating to CC 75 | 382.4538 | 382.4538 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
75.31 |  | Moved to 28.4.55 (NO COST ON THIS CC) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
75.32 |  | 250mm Water main installation obstructed by C&W and Streetlighting cables (Methodology only) (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
75.33 | 39429 | Repair fallen Heras fencing | 196.065 | 196.065 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 3370.7349 | 3370.7349
75.34 |  | Trial holes moved to 28.4.53 (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
75.35 |  | A1 Jointing Invoice for 33kVA | 4705.11 | 4705.11 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
75.36 |  | Issue C&W coordinates to tie (NO COST INCURRED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | CW
75.37 |  | Proceed to buy 250mm ductile pipe & fittings | 0 | 0 | 0 | 0% | Agreed |  |  | AS
75.38 |  | Relocate site fence due to 250mm excavation(NO COST CLAIMED) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
75.39 | 39490 | Pump out 800mm twin water valve chambers | 615.69 | 615.69 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
|  |  | 0 | 0 | 0 | 0%
75.41 |  | Excavate 6 no. trial holes | 1136.25 | 1136.25 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
CR 89 | [6 empty] | Agreed(*)
89.1 | 39401 | Artificial Obstructions | 2590.5921 | 2590.5921 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
89.2 | 39402 | Demolish Telecom chambers | 921.3108 | 921.3108 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
|  |  | 0 | 0 | 0 | 0%
89.4 | 39496 | Trial Hole (power) & Artificial Obstruction. | 1266.2476 | 1266.2476 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
89.05 |  | All disrupted plant relating to 1C-01-02 | 35 | 35 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 3891.8397 | 3891.8397
CR 90 | [6 empty] | Agreed(*)
90.1 | tbc | Marking out of DKE | 1550.4 | 1550.4 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.3 |  | Demolish existing Virgin media JF6 chamber | 942.2325 | 942.2325 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
90.4 | 39401 | Artificial obstructions | 5673.762 | 5673.762 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.6 | 39477 | Artificial obstructions in diversions | 2155.4062 | 2155.4062 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.7 | 39470 | Artificial Obstructions | 1532.8968 | 1532.8968 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.8 | 39426 | Remove existing utility, abandon diversion works, additional reinstatement | 2200 | 2200 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  | 1866.35 | -333.65 | Gen
90.1 | 39503 | Artificial Obstruction. | 1915.9857 | 1915.9857 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.11 | 39483 | Late change of works. | 926.145 | 926.145 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
90.12 | 39402 | Removal and Replacement of Kerbstones within diversionary routes. | 825 | 825 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen |  | 16779.5957 | 16779.5957
90.13 | 39562 | Re-excavation on south side connection due to initial instruction that existing 3" main did not require connection. | 4497.3887 | 4497.3887 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
90.14 | 39578 | Re-excavation to carry out connections on 1D/SW/D/01. | 3066.74 | 3066.74 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW | 100
90.15 |  | All disrupted plant relating to 1D-05-02 | 611.339 | 611.339 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
90.16 |  | Change Order 1399- Hire a sond and locate 1D/VM/D/701a & 708a and mark duct line in relation to kerbline. | 1342.3925 | 1342.3925 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | VM
0
CR 99 | [6 empty] | Agreed(*)
99.1 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
99.2 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.3 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.4 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.5 |  | Trial holes at Hanover St & the Mound ***(COMBINED) | 27000.0005 | 27000.0005 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
99.6 | TBA | Costs Associated with Diversion 1C/MP/D/101 | 572981.872 | 415288 | -157693.872 | -27.52% | Mound Gas Main |  |  | 3rd >£10k | [6 empty] | SGN
99.7 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.8 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.9 | 39722 | Downtime due to required alterations to traffic management as instructed by tie. | 1164 | 1164 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.1 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.11 | 39725 | Completed Route proving trial holes. | 47566.6062 | 47566.6062 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
99.12 | 39742 | Drill & tap existing 6" cast iron main as suspected it could be live Gas | 173 | 173 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
99.13 | 39749 | Removal & Replacement of street furniture. | 703 | 703 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.14 |  | All Disrupted Plant Relating to 1C-01-01 | 5973 | 5973 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.15 | 39763 | Slewing of existing Cable & Wireless conflict 1C/CW/850 to allow construction of JRCX12 as per CVI 00752. | 7173.4832 | 7173.4832 | 0 | 0% | Slew Utilities |  |  | 3rd | 50.2 | [5 empty] | CW
99.16 | 39790 | Drilling & Tapping of suspected gas mains as per CVI 00754. | 119 | 119 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
99.17 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.18 | 39752 | Artificial Obstructions | 1282 | 1282 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.19 | 39752 | Artificial Obstructions | 6154.0968 | 6154.0968 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.2 |  | Artificial Obstructions | 1861 | 1861 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.21 |  | Artificial Obstructions | 4508.7907 | 4508.7907 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.22 | 39755 | Artificial Obstructions | 658 | 658 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.23 |  | Artificial Obstructions | 897 | 897 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.24 | 39758 | Final Trial Hole Ref 1449 completed to determine position of 30" gas main to chamber wall and culvert. | 3313.0468 | 3313.0468 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SGN
99.25 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.26 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.27 |  | N.P.O. Associated with weekend working on 4th & 5th Oct 2008 and 18th & 19th Oct 2008. | 3294.55 | 3294.55 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
99.28 |  | N.P.O. Associated with weekend working on 25th & 26th Oct 2008 and 1st & 2nd Oct 2008 | 2878.41 | 2878.41 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
99.29 |  | N.P.O. Associated with weekend working on 8th & 9th Nov 2008. | 1144.4 | 1144.4 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
99.3 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.31 | 39841 | Delay and Disruption | 216 | 216 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.32 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.33 |  | Excavation of Trial Holes ( Superseded by CC 99.6) | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.34 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.35 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.36 | 39842 | Delay and Disruption | 141 | 141 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.38 | 39842 | Additional works | 98 | 98 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.39 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.4 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.41 | 39839 | Artificial Obstructions (Concrete) | 3105.98 | 3105.98 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.42 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.43 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.44 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.45 | 39845 | Additional works | 205 | 205 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.46 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.47 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.48 | 39845 | Atificial Obstructions | 303 | 303 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.49 | 39836 | Embargo Works | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
99.5 | 39854 | Delay and Disruption | 796 | 796 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.51 | 39853 | Artificial Obstructions | 454 | 454 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.52 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.53 | 39855 | Artificial Obstruction | 632 | 632 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.54 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.55 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.56 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.57 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.58 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.59 | 39857 | Artificial Obstruction | 617 | 617 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.6 | 39855 | Artificial obstruction | 1482 | 1482 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.61 | 39843 | Delay and Disruption | 65 | 65 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.62 | 39857 | Artificial Obstruction | 1467 | 1467 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.63 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.64 | 39853 | Trial Holes | 404 | 404 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.65 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.66 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.67 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.68 | 39859 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.69 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.7 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.71 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.72 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.73 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.74 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.75 | 39860 | Additional works | 542 | 542 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.76 | 39856 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
99.77 | 39862 | Additional Works | 1051 | 1051 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.78 | 39864 | Artificial Obstruction | 1025 | 1025 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.79 | 39848 | Abandoned Trial Hole | 1275.902 | 1275.902 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
99.8 | 39863 | Demolish of BT Box | 681 | 681 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
99.81 | 39864 | Artificial Obstructions | 2611.0711 | 2611.0711 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | BT
99.82 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.83 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.84 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.85 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.86 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.87 | 39864 | Additional works | 115 | 115 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.88 | 39862 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.89 | 39865 | Delay and disruption | 208 | 208 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.9 | 39869 | Delay and Disruption | 597 | 597 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.91 | 39867 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
99.92 | 39867 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
99.93 | 39874 | Additional works | 380 | 380 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.94 | 39869 | Hand Digging / Additional works | 1930 | 1930 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.95 | 39874 | Additional works | 1083 | 1083 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.96 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.97 | 39875 | Additional works | 420 | 420 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.98 | 39869 | Not claimable - Included in rates | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
99.99 | 39863 | Delay and Disruption | 519 | 519 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.1 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.101 | 39863 | Delay and Disruption | 259 | 259 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.102 | 39867 | Artificial Obstruction | 1369 | 1369 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.103 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.104 | 39870 | Artificial Obstructions | 1830 | 1830 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  | 1989.8751 | 159.8751 | Gen
99.105 |  | Additional Works | 607.1739 | 607.1739 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.106 | 39869 | Abandoned BT Manhole | 3550 | 3550 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  | 3377 | -173 | BT
99.107 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.108 | 39876 | Delay and Disruption | 295 | 295 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.109 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.11 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.111 | 39870 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.112 | 39868 | Artificial Obstructions | 3310.7699 | 3310.7699 | 0 | 0% | Agreed |  |  | 3rd |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.113 |  | 0 | 0 | 0 | 0 | 0% | Agreed(*)
99.114 | 39884 | Additional Works | 1066.54 | 1066.54 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
99.115 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.116 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.117 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.118 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.119 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.12 |  | Trial Hole | 881 | 881 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.121 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
99.122 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.123 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 478.72 | 478.72
99.124 |  | Survey of Crawley Tunnel | 478.72 | 478.72 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -478.72 | SW
99.125 |  | CUS excavated for new Verizon Chamber | 633 | 633 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Ver
99.126 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.127 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.128 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.129 |  | Artificial Obstructions | 1573.2232 | 1573.2232 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.13 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.131 |  | Exposed water main | 1126.5402 | 1126.5402 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SW
99.132 | 39885 | CUS assisting archaelogist excavation | 1332 | 1332 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.133 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.134 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.135 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.136 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.137 |  | CUS hire of Mabey plates for emergency lane | 3535 | 3535 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
99.138 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.139 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.14 |  | Artificial Obstructions | 1323.6253 | 1323.6253 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.141 | 39875 | CUS excavating to expose underground structure | 1056 | 1056 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.142 | 39892 | Delay and Disruption | 214 | 214 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.143 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.144 |  | Delay and Disruption | 970 | 970 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.145 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.146 |  | CUS installed concrete protection to shallow BT Ducts | 261 | 261 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
99.147 |  | Artificial Obstruction | 3880.113 | 3880.113 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.148 |  | CUS installed road plates to maintain emergency lane | 423.5699 | 423.5699 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.149 |  | CUS installed concrete protection to existing shallow services | 218.5683 | 218.5683 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
99.15 |  | Use of foam concrete | 1001.6128 | 1001.6128 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | BT
99.151 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.152 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.153 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.154 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.155 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
99.156 |  | Removal of silt from unchartered tunnels | 8000 | 8000 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 6566 | -1434 | SW | 100
99.157 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.158 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.159 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.16 |  | Delay and Disruption | 206 | 206 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.161 |  | CUS removed existing water mains to accommodate 24" gas main | 9694.4489 | 9694.4489 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
99.162 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.163 |  | Works recorded in CC99.171 | 0 | 0 | 0 | 0% | Agreed(*)
99.164 |  | Artificial Obstructions | 938.45 | 938.45 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.165 |  | Additional Works | 1861.53 | 1861.53 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.166 |  | Additional Works | 328.1605 | 328.1605 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.167 |  | CUS removed spoil from unchartered tunnels | 2950.1989 | 2950.1989 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
99.168 |  | Bypass for diversion 1C2/LP/D/124 | 1004.9856 | 0 | -1004.9856 | -100% | Bypass |  |  | new | not incl in CC246 | [5 empty] | SGN
99.169 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.17 |  | Data Logger Chamber | 942 | 942 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1122.6873 | 180.6873 | SW
99.171 |  | Contingency plan arrangements (Excavation labour not included) |  | 0 | 0 | 0% | Agreed(*) | [5 empty] | CUS added 12/03 |  |  |  | SGN
99.172 |  | Protecting excavation | 418 | 418 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
99.173 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SGN
99.174 |  | Additional works to Craley tunnel Annex | 4163 | 4163 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 4814.7881 | 651.7881 | SGN
99.175 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.176 |  | CCTV Survey of Sewer | 345.44 | 345.44 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SW | 100
99.177 |  | Demolish Existing Chamber | 1194 | 1194 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
99.178 |  | Exposing traction cables | 1768 | 1768 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 2264.0066 | 496.0066 | SGN
99.179 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.18 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.181 |  | Delay and Disruption | 232 | 232 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
99.182 |  | Delay and Disruption | 804 | 804 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
99.183 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.184 |  | Artificial Obstruction | 380 | 380 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 419.8193 | 39.8193 | SGN
99.185 |  | Works in Unchartered Tunnels - Princes St | 9000 | 9000 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -9000 | SW
99.186 |  | Artificial Obstructions | 1700 | 1700 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1958.97 | 258.97 | SGN
99.187 |  | Abandoned MRX510B | 2523 | 2523 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -2523 | BT
99.188 |  | Emergency Incident | 691.9 | 691.9 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 959 | 267.1 | Gen
99.189 |  | Installation & Hire of Mabey Plates | 1443 | 1443 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
99.19 |  | CCTV Survey 30" gas main | 3686 | 3686 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN | 100
99.191 |  | Artificial Obstructions | 1996.7 | 1996.7 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 2212.35 | 215.65 | SGN
99.192 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
99.193 |  | Artificial obstructions (Included in CC99.6) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
99.194 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
99.195 |  | Abandoned MRX510 | 2523 | 2523 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -2523 | BT
99.196 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | BT
99.197 |  | CCTV Survey of Gas main | 900 | 900 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -900 | SGN | 100
99.198 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.199 |  | Artificial Obstructions | 1535.92 | 1535.92 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1701.8 | 165.88 | Gen
99.2 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.201 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
99.202 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.203 |  | Backfill around existing pipes | 179.9189 | 179.9189 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SGN
99.204 |  | Pedestrian Walkway | 2599.73 | 2599.73 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 3210.5284 | 610.7984 | SGN
99.205 |  | Repair of burst Water main | 900 | 900 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1161.3339 | 261.3339 | SW
99.206 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.207 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
99.208 |  | Additional Scottish Water Works | 636.3561 | 636.3561 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SW
99.209 |  | Survey of BT Manholes | 850 | 850 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1020.0725 | 170.0725 | BT
99.21 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.211 |  | Confined space team assist SW | 1346.91 | 1346.91 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 1827.2017 | 480.2917 | SW | 100
99.212 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.213 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.214 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.215 |  | Excavation for Cut and Capped Main tie in | 400 | 400 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -400 | SGN
99.216 |  | Artificial Obstruction | 1500 | 1500 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 2526.49 | 1026.49 | SGN
99.217 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.218 |  | Foam concrete backfill | 100.1588 | 100.1588 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SGN
99.219 |  | Delay and disruption - caught in CC99.6 | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
99.22 |  | Site welfare - removing litter outwith site boundary | 100 | 100 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 123.4989 | 23.4989 | Gen
99.221 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.222 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
99.223 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
99.224 |  | Removal of Traffic Island | 513 | 513 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 651.1583 | 138.1583 | Gen
99.225 |  | Concrete protection to shallow Virgin Media diversion | 196.1737 | 196.1737 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | VM
99.226 |  | Core Drilling Manhole | 500 | 500 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -500 | BT
99.227 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.228 |  | Installation of road plates over flooded walkway | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
99.229 |  | Shoring under gas main to allow foam concrete backfill | 400 | 400 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 507.2401 | 107.2401 | SGN
99.23 |  | Removal of Traffic Island | 212.0691 | 212.0691 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.231 |  | Installation of communication ducts previously removed to allow gas bypass | 2600 | 2600 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -2600 | SGN
99.232 |  | Water main repair | 138.2663 | 138.2663 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | SW | 100
99.233 |  | Removal of pedestrian guard rail | 117.5312 | 117.5312 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  |  |  | Gen
99.234 |  | Additional reinstatement | 2000 | 2000 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -2000 | Gen
99.235 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
99.236 |  | Procurement of fabricated material for water tie in | 1098 | 1098 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -1098 | SW
99.237 |  | Additional Works | 160 | 160 | 0 | 0% | Agreed |  |  | new |  |  | Meeting 03/05 TL/JC Agreed |  | 0 | -160
99.238 |  | CUS excavated at Brandon tce and Holyrood Rd in accordance with Change Order 4101 | 0 | 0 | 0 | 0% | Agreed(*) | [8 empty] | 0 | Gen |  | 157850.4103 | 157850.4103
[5 empty] | 0 | 0%
CR 100 | [6 empty] | Agreed(*)
100.1 |  |  |  |  | 0 | 0% | Agreed |  |  | AS
100.3 | 39456 | Hand excavation around existing utilities |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.4 | 39457 | Trial hole trenches | 1204.2081 | 1204.2081 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.5 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
100.6 | 39463 | Hand dig around utility to install 1C/BT/D/108 |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
100.7 | 39470 | Supply & Install concrete in carriageway to support existing water utility | 647.5736 | 647.5736 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
100.8 | 39465 | Artificial obstructions & abandoned excavations | 10099.3974 | 10099.3974 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
100.9 | 39471 | Stand down due to faulty existing utility | 950.0579 | 950.0579 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
100.10 | 39774 | Artificial obstructions, reinstatement & unchartered utilities | 2433.9553 | 2433.9553 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.11 | 39458 | Delay & disrupted diversions |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.12 | 39489 | Additional Works (Artificial Obstruction & Signs) | 1322.1456 | 1322.1456 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.13 | 39503 | Artificial Obstruction. | 3200.6885 | 3200.6885 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.14 | 39517 | Additional woks to gas main | 1285.2518 | 1285.2518 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
100.15 |  | #REF! |  |  | 0 | 0% | Agreed |  |  | AS
100.16 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS
100.17 | 39658 | Night shift work to complete tie in with existing 16" water main | 2147.712 | 2147.712 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
100.18 | 39661 | Removal of Concrete from said diversion | 2389.2154 | 2389.2154 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
100.19 | 39708 | Investigation and removal of unchartered structure | 2021.8696 | 2021.8696 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
100.2 | 39723 | Additional Reinstatement due to close proximity of diversionary works prior to MUDFA. | 253.84 | 253.84 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
100.21 | 39723 | Decommisioning of existing Y-branch. | 819.0118 | 819.0118 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
100.22 | 39723 | Trial Hole on conflict 1C2/LP/127 | 829.5238 | 829.5238 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
100.23 | 39710 | Structural Survey on unidentified structure at junction of Princes St. & South St Andrews St. | 755.529 | 755.529 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.24 | 39714 | Artificial Obstruction | 578.6133 | 578.6133 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
100.25 | 39714 | Artificial Obstruction | 1431.208 | 1431.208 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 10926.3478 | 10926.3478
100.26 | 39714 | Repair damage to unchartered structure & Abandoned track for 180mm Gas Main. | 1491.6046 | 1491.6046 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN | 100
100.27 |  | Abandoned track due to CUS realisation that new prposed location of 1C2/LP/D/122 would result in Valves located within the DKE. | 1159.5767 | 1159.5767 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
100.28 | 39718 | Installation of impromptu 250mm DI main to make water live. | 3028.7509 | 3028.7509 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
100.29 | 39717 | Nightworks required for SW connections. | 4995.1151 | 4995.1151 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
CR 103 | [6 empty] | Agreed(*)
103.1 | 39412 | Archaeological Watching Brief (15 days) | 1864.3466 | 1864.3466 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
103.2 | tbc | Marking out of DKE | 2584 | 2584 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
103.3 |  | Additional Virgin Media works required | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
103.4 |  | Supply additional BT duct alongside diversion 7A/SW/D/03 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
103.5 |  | Remeasurable Items | 0 | 0 | 0 | 0% | Agreed |  |  | AS
103.6 | 39414 | Reinstate pot holes & repair steps at Cabinet Works (ALL OTHER ITEMS RELATING TO THESE CVIs ARE CLAIMED WITHIN REMEASURE) | 1128.264 | 1128.264 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
103.7 | 39419 | Standing time due to constraints of electronic gate at the Gogar Farm Road | 447.516 | 447.516 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
103.8 | 39423 | Set water pipe in concrete at road entrance to Gogar Cabinet Works | 612.7397 | 612.7397 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
103.9 | 39435 | Trial Holes | 1539.6701 | 1539.6701 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
103.10 |  | Disrupted Plant | 807.5446 | 807.5446 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
103.11 | 39435 | Hand dig around existing uncharted services | 1291.6525 | 1291.6525 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
103.12 | 39426 | Stand-down time due to sections being deleted | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
103.13 |  | TQs / CVIs with no cost impact, to be captured in remeasure | 0 | 0 | 0 | 0% | Agreed |  |  | AS
103.14 | 39421 | Protection of unidentified pipe with concrete | 315.9 | 315.9 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 5211.7626 | 5211.7626
CR 107 | [6 empty] | Agreed(*)
107.1 | 39412 | Additional THUS diversion (issued after IFC drawings (CAPTURED IN REMEASURE)) | 0 | 0 | 0 | 0% | Agreed | 0 |  | AS | [6 empty] | THUS
107.2 | 39483 | Removal of pedestrian crossing at Jane Street (LUX AGAINST CC109.4) | 0 | 0 | 0 | 0% | Agreed | 0 |  | AS | [6 empty] | BT
107.3 | 39483 | Tril hole & artificial obstruction Artificial obstruction | 6217.658 | 6217.658 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.4 | 39486 | Removal of redundant sewer pipe | 146.1712 | 146.1712 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.5 | 39486 | Trench collapse whilst awaiting resolutin of TQ | 311 | 311 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.6 |  | TQs / CVIs with no cost impact / Re-measure Items | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.7 | 39482 | Hand digging |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.8 | 39482 | Remove and dispose of trees and bases | 1184 | 1184 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.9 | 39493 | Relay 50 linear metres of kerbs from no. 264 Leith Walk to no. 242 Leith Walk | 4475.5312 | 4475.5312 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.10 |  | Disrupted Plant | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.11 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.12 | 39491 | Trial hole for to locate route of diversion that required backfilling | 345.9657 | 345.9657 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.13 | 39504 | Concrete | 617.7828 | 617.7828 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.14 | 39464 | Artificial Obstructions & Kerb Removal | 16932.2035 | 16932.2035 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.15 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.16 | 39496 | Demolish Virgin Media Junction Box No. 26 | 85 | 85 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | VM
107.17 | 39507 | Hand Digging |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.18 | 39510 | Removal of Trees | 1372 | 1372 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.19 | 39481 | Remove old culvert from 400mm / 180mm water trench | 5007 | 5007 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
107.20 | 39512 | Change M/H covers from footpath to roadway covers, remove brickwork and fit new CI roadway covers | 736 | 736 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
107.21 | 39512 | Delay awaiting instruction from SW on culvert removal | 2317 | 2317 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
107.22 | 39518 | Purchase of NAL retention socket | 2562 | 2562 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.23 | 39521 | Trial Holes | 954 | 954 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.24 | 39521 | Artificial obstruction - Extra tar & concrete | 410.5598 | 410.5598 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.25 | 39521 | Extra reinstatement | 2676.3168 | 2676.3168 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.26 | 39524 | Remove concrete from trench | 2457.4787 | 2457.4787 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.27 | 39541 | Additional foam concrete | 1082.2118 | 1082.2118 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.28 | 39547 | Trial hole | 245.3658 | 245.3658 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.29 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.3 | 39552 | Artificial obstruction | 3385.8595 | 3385.8595 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.31 | 39507 | Running sand | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.32 | 39555 | Artificial obstruction | 6676.1503 | 6676.1503 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.33 | 39539 | Artificial Obstruction | 3505.3202 | 3505.3202 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.34 | 39563 | Remove redundant cast main | 281 | 281 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
107.35 | 39563 | Artificial Obstruction | 228.682 | 228.682 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.36 | 39588 | Gas service alterations | 673 | 673 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
107.37 | 39570 | Artificial Obstruction | 1092.2127 | 1092.2127 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.38 | 39570 | Demolish Chamber | 2849 | 2849 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
107.39 | 39565 | Artificial Obstruction | 2109.3358 | 2109.3358 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.40 | 39566 | Removal of trees | 809 | 809 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.41 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.42 | 39582 | Remove Concrete | 409.5798 | 409.5798 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.43 | 39582 | Demolish VM chamber | 524 | 524 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | VM
107.44 | 39587 | Artificial Obstruction | 4321.0666 | 4321.0666 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.45 | 39582 | Trial Hole | 530 | 530 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
107.46 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.47 | 39575 | Delays due to TQs and IFC;s |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.48 | 39575 | Trail hole | 2016 | 2016 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.49 | 39575 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
170.5 | 39587 | Delays to due archeologists | 9335.584 | 9335.584 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
170.51 | 39588 | Gas service alterations | 1715.9936 | 1715.9936 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
170.52 | 39578 | Exploratory excavation | 2957.7715 | 2957.7715 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
170.53 | 39578 | Drill mians | 763.8461 | 763.8461 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
170.54 | 39596 | Remedial works | 380.299 | 380.299 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
170.55 | 39603 | Remove concrete | 4096 | 4096 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.56 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.57 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.58 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.59 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.6 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.61 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
170.62 | 39613 | Weekend Working | 3840.842 | 3840.842 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
170.63 | 39632 | Artificial obstruction | 7696.6866 | 7696.6866 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
170.64 | 39637 | Demolish Chamber | 5777.1797 | 5777.1797 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
107.65 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.66 |  | Remove SPEN Ducts | 9791.1296 | 6695.7696 | -3095.36 | -31.61% | Utility Abandonment |  |  | new | [6 empty] | SP
107.67 | 39647 | Remove concrete | 4552.9422 | 4552.9422 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.68 | 39647 | Re-build sewer | 2226.584 | 2226.584 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.69 | 39647 | Concrete | 735.7905 | 735.7905 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.7 | 39650 | Removal of redundant pipe | 961.6288 | 961.6288 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.71 | 39647 | Build sewer access chamber | 6372.7987 | 6372.7987 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.72 | 39665 | By-Pass for Gas diversion | 2808.585 | 0 | -2808.585 | -100% | Bypass |  |  | 3rd | not incl in CC246 | [5 empty] | SGN
107.73 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.74 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.75 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.76 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.77 | 39699 | Trial Hole | 6134.144 | 6134.144 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.78 | 39672 | Extra over foam concrete | 2596 | 2596 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.79 | 39672 | Additonal works- Seimans power cable | 3239 | 3239 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.8 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.81 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.82 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.83 | 39672 | Remove Protecta line pipe and replace with 180mm PE | 28000 | 28000 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | SW
107.84 | 39688 | Gass bypass, Trace water main | 770 | 770 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
107.85 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.86 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.87 | 39688 | Remove and replace gulleys. | 2878 | 2878 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
107.88 | 39709 | Remove concrete, hand digging | 4463.689 | 4463.689 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.89 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.9 | 39716 | Remove concrete, slewing & design change | 12257.0762 | 12257.0762 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
107.91 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.92 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.93 | 39734 | Doubling handling of goods |  |  | 0 | 0% | Agreed |  |  | AS
107.94 | 39737 | Use of extra over foam concrete (30w BT) | 1403 | 1403 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
107.95 |  | Delay, disruption and dislocation. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | D&D
107.96 | 39735 | Excavate & backfill connection for SGN | 1500 | 1500 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | SGN
107.97 | 39735 | Pedestrian Crossing (maderston) | 1800 | 1800 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | BT
107.98 | 39737 | Extra tar due to underminging and replace gulley pot. | 536 | 536 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
107.99 |  | Gas service connections for future use. | 2945.4336 | 0 | -2945.4336 | -100% | Supply Connections |  |  | new | [6 empty] | SGN
107.1 | 39737 | Overtime due to traffice management restrictions |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
107.101 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.102 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.103 | 39833 | Extra cores for coms box | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
107.104 | 39792 | Build Temp. box | 1478 | 1478 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
107.105 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.106 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.107 | 39805 | Weekend working overtime | 2091.321 | 0 | -2091.321 | -100% | NPO |  |  | 3rd | [6 empty] | Gen
107.108 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.109 | 39832 | Re-erect lamp post | 12571.4451 | 7635.63 | -4935.8151 | -39.26% | Other (WS) |  |  | 3rd >£10k | [6 empty] | Gen
107.11 | 39826 | Re-erect RTI poles | 1722 | 1722 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.111 | 39835 | Removal of concrete | 1979.6356 | 1979.6356 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.112 |  | Extra coring for coms box. | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
107.113 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.114 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.115 | 39884 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
107.116 | 39890 | Remove lamp posts | 1598 | 1598 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.117 |  | Reinstate track as per tie instruction 3669 & 3670 | 5012 | 5012 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
107.118 |  | Remvoing ductile main from 400mm gas main for Manderston St connection. | 8764.928 | 8764.928 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
107.119 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.12 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
107.121 |  | Contingency plan - excavate valves. | 2521.7331 | 2521.7331 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
107.122 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
107.123 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
107.124 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
107.125 |  | Proprietary works on basses and large diameter flow stopping | 3089 | 3089 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
107.126 |  | Extra Track | 2957.7715 | 2957.7715 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
107.127 |  | Assissting Steve Vick remove cast pipe from parent main, | 3630.3018 | 3630.3018 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
107.128 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.129 |  | Constructing 315mm bypass and connecting bypass to 400mm parent main. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | top 68 | [6 empty] | SGN
107.13 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.131 |  | Additional track for shoring | 12994.8 | 9606.6 | -3388.2 | -26.07% | Other (WS) |  |  | top 68 | [6 empty] | Gen
107.132 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.133 |  | Bypasses for 180mm connection and 63mm transfer | 13781 | 13781 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
107.134 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.135 |  | Temp. reistatement @ Manderston Street | 11337.1504 | 0 | -11337.1504 | -100% | Other (WS) |  |  | new | [6 empty] | BT
107.136 |  | Additional works as per CVI 01351 | 1154 | 1154 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.137 |  | Additional works as per CVI 01357 | 4261 | 4261 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
107.138 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.139 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.14 |  | Remove cast main (existing) | 302 | 302 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
107.141 |  | Remove buried sewer | 354 | 354 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
107.142 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.143 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.144 |  | Hire of Marley Bridge | 1435 | 1435 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.145 |  | Service connection o/s No 73 | 190 | 190 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
107.146 |  | Excavate and re-route Diversion 1B/BT/D/517 elsewhere with slow bends. | 3039 | 3039 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
107.146a |  | Relay 4way due to Infraco damage | 12951.552 | 0 | -12951.552 | -100% | Other (WS) |  |  | new
107.146b |  | Rope Fujitsu laid ducts | 172 | 172 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
107.146c |  | Repair SW damaged ducts | 3630 | 3630 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW | 100
107.147 |  | 0 | 0 | 0 | 0 | 0% | Agreed(*)
107.148 |  | Could not fit CCTV pole base in proposed location. | 627.8176 | 627.8176 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
107.149 |  | Gas abandonment on Crown street (6'') | 11354.796 | 0 | -11354.796 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
107.15 |  | Delay in testing 30 way BT due to water ingress. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | BT
107.151 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.152 |  | Nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
107.153 |  | Resources required to install cabinet, carry out unsuccessful trial holes & delay awaiting clarification from BT & tie. | 3126 | 3126 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
107.154 |  | Furher to CC107.150, CUS have incurred further delay in testing the 30way BT diversion 1B/BT/D/523 due to water ingress in the ducts. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | BT
107.155 |  | Additional BT Works (not claimed in measure) | 11740.1975 | 1686.9204 | -10053.2771 | -85.63% | Other (WS) |  |  | new | [6 empty] | BT
107.156 |  | Decommissioning of 12" C/I gas from smiths place to maderson street. Including failed attempt due to all services not transferred from existing main (CUS letter 2656). | 10829.2347 | 0 | -10829.2347 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
107.157 |  | hand digging | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
107.158 |  | Service connection (outsite 193 leith walk) | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agree 20/05 |  |  |  | SW
107.159 |  | Remove artificial obstruction from gas abandonemtn hole opposite the foot of the walk | 1279.9368 | 1279.9368 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
107.16 |  | Trial hole | 278.0676 | 278.0676 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 158217.4278 | 147802.0917
107.161 |  | Provide gas detector to florists (did not happen) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | SGN
107.162 |  | Repair to gully previously damaged by SGN, as requested by tie Change Order 3893. | 2593 | 2593 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN 100
107.163 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.164 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
107.165 |  | Remove 300mm Gas valve (previously claime din measure to be claimed in CC as per Fiona Dunn) | 5148.2912 | 0 | -5148.2912 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
107.166 |  | Abandon esicting valve set up on a live main. This includes inserting a tee and a fire hydrant on to a live 180mm water main. | 9779.5887 | 0 | -9779.5887 | -100% | Utility Abandonment |  |  | new | [6 empty] | SW | 100
0
CR 122 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
122.5 |  | Additional fittings & weekend working to divert uplanned existing water main | 2000 | 2000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SW
122.6 |  | Slewing of ducts and hand dig around services | 6043 | 6043 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | BT
122.7 |  | Demolish chambers & artificial obstructions | 3131 | 3131 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
122.1 |  | Drill 4" Main, Weekend Work, Slewing Ducts, Demolish M/H, Demolish M/H. | 40286.7177 | 23423.4876 | -16863.2301 | -41.86% | Demolish Chamber |  |  | 3rd | [6 empty] | BT
122.11 |  | Hand Digging,Water Main Fracture, Weekend Working,Trials Holes | 7649.7162 | 7649.7162 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW | 100
122.12 |  | Additional Works (Various) | 4056.72 | 4056.72 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | Gen
122.13 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.14 |  | Water diversion & Trial hole. | 2644 | 2644 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
122.15 |  | Build JRC112 THUS Box | 1547.5472 | 1547.5472 | 0 | 0% | Agreed |  |  | AS | [6 empty] | THUS
122.16 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.17 |  | Slew of ducts, slew & lower, removal of concrete & brick up tunnels. | 6453.5 | 6453.5 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | BT
122.18 |  | Trial Hole, weekend working, & hand digging. | 3445.0315 | 3445.0315 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 27/05 |  |  |  | Gen
122.19 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.2 |  | Weekend Work | 2626.458 | 2626.458 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.21 |  | Trial Holes | 2852.8633 | 2852.8633 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.22 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.23 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.24 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.25 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.26 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.27 |  | Additional Works | 1312 | 1312 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
122.28 |  | Assessed Elsewhere (see Master Change Control register) |  |  | 0 | 0% | Agreed(*)
122.29 |  | Removal of Artificial Obstruction Removal of Sign Post | 3439.3483 | 3439.3483 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
122.3 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.31 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.32 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.33 |  | Demolish Chamber for rebuild | 1057.995 | 1057.995 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
122.34 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.35 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.36 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.37 |  | Demolish of JRF106 for new JRF112 | 1289.0011 | 1289.0011 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
122.38 |  | Trial Hole abandoned for diversion 1C/BT/D/99B Outwith boundary of worksite | 245.3651 | 245.3651 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
122.39 |  | Abandoned excavation due to existing 180mm Gas Main on Diversion 1C/BT/D/115 (Moved) | 3342.7821 | 3342.7821 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
122.4 |  | Demolish chamber JF10 in order to rebuild New JF110 chamber | 1080 | 1080 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
122.41 |  | Extensive existing charted/uncharted services having to be excavated around to accommodate new 12 way | 2899 | 2899 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
122.42 |  | Excavate around existing charted/uncharted utilities to accommodate diversion | 713 | 713 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
122.43 |  | Emergency Repair on scottish water burst- unrelated to MUDFA works | 1582.605 | 1582.605 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
122.45 |  | Replace additional tar due to the close proximity of 2 areas of previous track by non-MUDFA works | 549.7868 | 549.7868 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
122.46 |  | Removal of 3m of sewer roof as stated in CVI 3157 & 3064 | 3092.6025 | 3092.6025 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
122.47 |  | Removal Of Artificial obstruction | 306.5794 | 306.5794 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.48 |  | All disrupted plant relating to RaT 1C/03/01 | 1152.3869 | 1152.3869 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.49 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.5 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.51 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.52 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.53 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.54 |  | Rod, Rope test and Backfill track done at weekend due to Traffic Management restrictions | 1530 | 1530 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
122.55 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.56 |  | Delay to diversion due to awaiting investigation | 97.92 | 97.92 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.57 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.58 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.59 |  | Additional Reinstatement due to undermining. | 420.7317 | 420.7317 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
122.6 |  | Hand-Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
122.60B |  | Hand-Digging | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
122.61 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.62 |  | Assessed Elsewhere (see Master Change Control register) | 0 | 0 | 0 | 0% | Agreed(*)
122.65 |  | Trial hole to determin if concrete was present | 1737.3449 | 1737.3449 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 21447.3839 | 21447.3839
[5 empty] | 0 | 0%
CR 125 | [6 empty] | Agreed(*)
125.1 | 39496 | Logistics support team | 215083 | 215083 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.2 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.3 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.4 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.5 | 39483 | Artificial obstruction | 416.4061 | 416.4061 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.6 | tba | Provision of additional site security | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.7 | tba | Temporarily remove and later reinstate road crossings | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.8 | tba | Removal of CAT posts @ Lothian Rd | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.9 | tba | Additional signage @ Western approach Additional signage @ Lothian road | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.10 | tba | Provision of call out service to cover rugby 12pm to 12am Sat 08/03/2008 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.11 | 39521 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
125.12 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.13 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.14 | 39512 | Remove Scrap | 1122.4005 | 1122.4005 | 0 | 0% | Agreed |  |  | AS
125.15 | 39518 | Unchartered Utilities, trail holes & drilling. | 1606.4944 | 1606.4944 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.15.1 | 39547 | Remove diused pipes | 1094.535 | 1094.535 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.16 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.17 |  | Scaffolding outside 22 to 30 & temp works | 451.52 | 451.52 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.18 |  | 0 | 358 | 358 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05
125.19 | 39510 | Removal of Artificial Obstructions. | 4873.9993 | 4873.9993 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.20 | 39524 | Abandoned track due to unchartered stone culvert. | 2136.5523 | 2136.5523 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.21 | 39519 | Removal of Artificial Obstructions | 1907.9591 | 1907.9591 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.22 |  | Removal of Artificial Obstructions | 119.4608 | 119.4608 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.23 | 39519 | Removal of Artificial Obstructions | 529.0405 | 529.0405 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.24 | 39517 | Removal of Artificial Obstructions | 5054.8971 | 5054.8971 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.25 | 39508 | Removal of Artificial Obstructions. | 910 | 910 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.26 | 39525 | Removal of Artificial Obstructions | 651.9145 | 651.9145 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.27 | 39513 | Abandoned Trial Holes | 965.5143 | 965.5143 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.28 | 39525 | Removal of Artificial Obstruction | 3744.2418 | 3744.2418 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.29 | 39521 | Repair Damage to Unchartered Manhole Shaft. | 394.4077 | 394.4077 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.30 | 39518 | Inspection & Removal of Unchartered Utility. | 416.3103 | 416.3103 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.31 | 39521 | Removal of Unchartered Steel Obstruction from Diversion Path. | 103.9038 | 103.9038 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.32 | 39512 | Removal of Artificial Obstructions. | 358.3823 | 358.3823 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.33 | 39512 | Abandoned Trial Hole due to Inaccurate Issued for Construction Drawings. | 1401.7692 | 1401.7692 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.34 | 39519 | Removal of existing 4" cast iron from route of diversion. | 558.675 | 558.675 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.35 | 39532 | Requested to Abandon new JUF106 excavation until next stage of Traffic Management. | 2171.97 | 2171.97 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.36 | 39532 | Abandoned Trial Hole for new JUF106 | 245.3658 | 245.3658 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.37 | 39538 | Remove Concrete from existing 12way BT and dig back on existing 4way Cable & Wireless to create slack to manouvre new manhole. | 4484.6946 | 4484.6946 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.38 | 39539 | Demolish Existing Joint box in diversion path | 179.3963 | 179.3963 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.39 | 39541 | Drill & Tap Existing 4" Water Main. | 57.1838 | 57.1838 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.40 | 39539 | Removal of Unchartered Power Culvert & Unchartered Fire Clay. | 1232.775 | 1232.775 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
125.41 |  | Supply 20 No. 22mm Spanners for Emergency Services to use at Shandwick Place. | 71.325 | 71.325 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.42 | 39544 | Weekend working | 1058.6872 | 1058.6872 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.43 | 39545 | Aritificial obstruction | 420.5019 | 420.5019 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.44 | 39546 | Remove rock | 1911.3723 | 1911.3723 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.45 | 39547 | Install water meter | 2349.1525 | 2349.1525 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.46 | 39548 | Trial Holes | 490.7315 | 490.7315 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.47 | 39548 | Additional reinstatement | 369.8996 | 369.8996 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.48 | 39548 | Artificial obstructions | 634.8487 | 634.8487 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.49 | 39547 | Remove old cast main | 176.6956 | 176.6956 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.5 | 08/04/2008/ | Make safe existing BT cables | 852.584 | 852.584 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.51 | 39548 | Artificial Obstructions. | 1317.4816 | 1317.4816 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.52 | 39548 | Artificial Obstructions. | 2443.826 | 2443.826 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.53 | 39548 | Artificial Obstruction. | 1580.2953 | 1580.2953 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.54 | 39531 | Remove Artificial Obstructions. | 1344.7869 | 1344.7869 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.55 | 39561 | Remove Artificial Obstructions. | 300.3585 | 300.3585 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.56 | 39561 | Remove Artificial Obstructions. | 238.9215 | 238.9215 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.57 | 39548 | Remove Artificial Obstructions. | 593.8907 | 593.8907 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.58 |  | Remove Artificial Obstructions. | 7276.8674 | 7276.8674 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.59 | 39561 | Remove Artificial Obstructions. | 11058.654 | 11058.654 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.60 | 39511 | Remove Artificial Obstructions. | 14741.4588 | 14741.4588 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.61 | 39518 | Remove Artificial Obstructions. | 945.4466 | 945.4466 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.62 | 39546 | Trial Hole & Drilling on Existing 10" Gas conflict - 1D/LP/D/104, to ascertain the location of the inserted 180mm PE in relation to the DKE. | 303.5659 | 303.5659 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.63 | 39554 | Slew & lower conflict 1D/SP/20 to adequate cover by; Shutting of live 4" water main, cutting section of main, lower said conflict, then replacing section of water main. | 355.2638 | 355.2638 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
125.64 | 39566 | Drill & tap existing 15" cast iron main. | 96.4 | 96.4 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.65 | 39545 | Remove 12 x spiked Scottish Power cables, cut to length and place in specified skip for collection by Scottish Power every night. (Jackie Paton tie has verified duration as per RS 02318) | 6398.4024 | 5670.6408 | -727.7616 | -11.37% | Utility Abandonment |  |  | 3rd | [6 empty] | SP
125.66 | 39563 | Remove existing (dead) valve & fire hydrant covers, then reinstate trench. | 1105.1438 | 1105.1438 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.67 | 39573 | Extra excavation required in order to manouvre; a buried unchartered sewer shaft and 2 x unchartered Scottish Power ducts. | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
125.68 | 39563 | Demolish JRF14. | 2071.44 | 2071.44 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.69 | 39556 | Abandoned track due to close proximity of lead joint and bend. | 1954.8749 | 1954.8749 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.70 | 39556 | Removal & Reinstatement of Cathness Slabs. | 1825 | 1825 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | Gen
125.71 | 39573 | Delay, Disrupted and Dislocated Works; Shandwick Place (Canning Street). | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.72 | 39575 | Drill and tap then remove existing cast mains from route of diversion. | 422 | 422 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
125.73 | 39573 | Hand Digging. |  |  | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.75 | 39580 | removal of existing cast iron mains. | 354.0713 | 354.0713 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.74 | 39575 | Additional fittings for supply connections. | 331 | 331 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
125.76 | 39580 | Additional materials to make safe around existing scaffolding. | 2512 | 2512 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
125.77 | 39576 | Abandoned track due to two unchartered shafts. | 4152.75 | 4152.75 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.78 | 39562 | Bricking up unchartered sewer shaft. | 778.725 | 778.725 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.79 | 39583 | Artificial Obstruction. | 846.4649 | 846.4649 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.80 | 39583 | Artificial Obstruction. | 1099.0391 | 1099.0391 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.81 | 39583 | Artificial Obstruction. | 457.3641 | 457.3641 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.82 | 39583 | Artificial Obstruction. | 276.4663 | 276.4663 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.83 | 39583 | Artificial Obstruction. | 4894.4783 | 4894.4783 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.84 | 39583 | Artificial Obstruction. | 399.3403 | 399.3403 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.85 | 39583 | Remove Artificial Obstruction. | 7789.4049 | 7789.4049 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.86 | 39587 | Assisting sewer survey | 945 | 945 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.87 | 39589 | Slewing existing ducts into new MRX404. | 2146.537 | 2146.537 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.88 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.89 | 39575 | Hand digging around unchartered 180mm Gas connections at Stafford Street. | 958 | 958 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
125.90 | 39588 | 2 No. Trial Holes on two unchartered 4" C/I mains to verify whether they were supply connections. | 490.7315 | 490.7315 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.91 | 39589 | Trial Hole on unchartered 6" cast iron to verify whether the service had to be transferred. | 391 | 391 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.92 | 39554 | Nightworks N.P.O. | 6017.9712 | 5195.8528 | -822.1184 | -13.66% | NPO |  |  | 3rd | [6 empty] | SW
125.93 | 39597 | Nightworks to transfer 3" & 4" supply connections onto new 125mm main. | 819 | 819 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.94 | 39568 | Additional fittings for supply connections. | 2677.8182 | 0 | -2677.8182 | -100% | Supply Connections |  |  | 3rd | [6 empty] | SW
125.95 | 39570 | Downtime incurred during changing formation of additional 4 x 150mm Rigiducts. | 477.3504 | 477.3504 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.96 | 39615 | Removal of Reinforced Concrete. | 7999.6774 | 7999.6774 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.97 | 39612 | Remove Artificial Obstructions. | 375.4481 | 375.4481 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.98 | 39616 | Remove Artificial Obstructions. | 1057.5043 | 1057.5043 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.99 | 39615 | Remove Artificial Obstructions. | 1290.1763 | 1290.1763 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.100 | 39611 | Remove Artificial Obstructions. | 1438.8791 | 1438.8791 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.101 | 39615 | Remove Artificial Obstructions. | 658.7408 | 658.7408 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.102 | 39611 | Remove Artificial Obstructions. | 1614.427 | 1614.427 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.103 | 39616 | Additional foam concrete & reinstatement due to overbreak of existing cobbles. | 5892.8535 | 5892.8535 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.104 | 39616 | Additional foam concrete & reinstatement due to overbreak of existing cobbles. | 747.0581 | 747.0581 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.105 | 39618 | N.P.O and sleep time for carrying out water connections at night. | 3109.68 | 3109.68 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.106 |  | All disrupted plant relating to 1D/04/01 | 41075.259 | 0 | -41075.259 | -100% | Disrupted Plant |  |  | new | [6 empty] | Gen
125.107 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.108 | 39616 | Remove Artificial Obstructions. | 1365 | 1365 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.109 |  | City Sweep requested by tie due to Stafford street market on Saturday 7th June. | 57 | 57 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.110 | 39611 | Trial Hole requested to speed up the planning process for Scottish Water Diversions between Lothian Road and South Charlotte Street. | 993.7313 | 993.7313 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.111 | 39631 | Removing temporary tar outside scaffolding to prepare for permanent reinstatement. | 760.1304 | 760.1304 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.112 | 39630 | Remove concrete from around gully to allow a route for diversions - 1D/CW/D/05 & 1D/BT/D/34. | 284 | 284 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | CW & BT
125.113 | 39630 | Additional Reinstatement due to two unchartered concrete shafts. | 2613.2883 | 2613.2883 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.114 | 39630 | Additional Blank Plate requested by TQ/UTL/577. | 145.3725 | 145.3725 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.115 | 39630 | Hand digging around existing unchartered gas supply connections and hand digging around existing chartered/ unchartered water supply connections. | 1011.84 | 1011.84 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.116 |  | Raising of existing buried sewer shaft to ground level. | 1389.3319 | 1389.3319 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.117 | 39634 | Essential weekend working & hire of specialist shoring. | 2735 | 2735 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | SW
125.118 | 39638 | Drill and tap existing 3" C/I main then subsequently remove. | 325.8313 | 325.8313 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.119 | 39637 | Removal of footway blister to progress works. | 2944.2837 | 2944.2837 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.12 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.121 | 39589 | Repair existing 4" cast iron water main - conflict 1D/SW/D/18. | 291.2119 | 291.2119 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.122 | 39639 | Artificial Obstruction. | 1843.1066 | 1843.1066 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.123 | 39639 | Remove Artificial Obstructions. | 6222.1994 | 6222.1994 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.124 | 39639 | Remove Artificial Obstructions. | 2863.6453 | 2863.6453 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.125 | 39639 | Remove Artificial Obstructions. | 976.1651 | 976.1651 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.126 | 39639 | Remove Artificial Obstructions. | 1808.9773 | 1808.9773 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.127 | 39639 | Remove Artificial Obstructions. | 2128.5519 | 2128.5519 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.128 | 39639 | Remove Artificial Obstructions. | 791.8542 | 791.8542 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.129 | 39639 | Remove Artificial Obstructions. | 846.4649 | 846.4649 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.130 | 39639 | Remove Artificial Obstructions. | 1208.2603 | 1208.2603 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.131 | 39639 | Remove Artificial Obstructions. | 320.8375 | 320.8375 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.132 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.133 | 39626 | Delay, Disruption and Dislocation | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.134 | 39630 | Demolish JUF6 to construct JBF10 (south side). Demolish FW 3 to construct JBF6 (north side). | 2178.675 | 2178.675 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
125.135 |  | CUS where instructed to move the 500mm Gas diversion a minimum of 750mm from cellars (tie 0302). This has resulted in the main being within the DKE at certain points. Prior to this CUS had already backfilled 105 metres of both 500mm gas & 180mm water. It is noted in TQ's 571 & TQ 580 that this issue arose due to failure in IFC design. | 34918.4385 | 0 | -34918.4385 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
125.136 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.137 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.138 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.139 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.140 |  | Delay, disruption & dislocation | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | D&D
125.141 |  | Screed 95 Shandwick Pl doorway to make good puddle. | 195.3 | 195.3 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.142 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.143 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.144 | 39660 | Decommission of approx 15m of 315mm Gas pipe | 277.644 | 277.644 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.145 | 39637 | Artificial Obstruction within excavation for 180mm Gas bypass | 736.561 | 736.561 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
125.146 | 39637 | 0 | 1123 | 1123 | 0 | 0% | Agreed |  |  | 3rd <£2k
125.147 | 39660 | 0 | 369 | 369 | 0 | 0% | Agreed |  |  | 3rd <£2k
125.148 | 39660 | 0 | 317 | 317 | 0 | 0% | Agreed |  |  | 3rd <£2k
125.149 | 39638 | Artificial Obstruction within Gas Bypass excavation (bypass claimed in measure) | 1175 | 1175 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
125.15 | 39660 | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) |  |  | 3rd
125.151 | 39660 | Down Time due to Artificial Obstructions | 1406.1774 | 1406.1774 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.152 | 39639 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.153 | 39660 | Construction of temporary Virgin Media chamber related to TQ 703. | 2761.7487 | 2761.7487 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
125.154 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.155 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.156 | 39668 | Stand down of gulley pot renewal due to meeting with Tie & C.E.C. | 371.25 | 371.25 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.157 | 39671 | Construction of 1No Reinforced slab | 1416 | 1416 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.158 | 39680 | Additional fittings for supply connections. | 206 | 206 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.159 | 39699 | Construct 4 x base and erect 4 x 'B' type cabinets for virgin media | 6448 | 6448 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | VM
125.16 | 39699 | Artificial Obstructions (Concrete) | 396.9872 | 396.9872 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.161 | 39664 | Double handling of spoil due to restricted work space | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
125.162 | 39657 | Double handling of spoil due to restricted work space |  |  | 0 | 0% | Agreed |  |  | AS
125.163 | 39685 | Excavating Joint Bays for Scottish Water | 439 | 439 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.164 | 39699 | Abandoned Trial Hole | 70 | 70 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.165 | 39699 | Additional Reinstatement due to poor existing road surface. | 6162.8982 | 6162.8982 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.166 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.167 | 39707 | Artificial Obstruction | 741.3394 | 741.3394 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.168 | 39661 | Abandoned Excavations due to late alterations to SW diversions prior to embargo. | 15000 | 15000 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | SW
125.169 | 39763 | Artificial Obstructions | 85.0902 | 85.0902 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.170 | 39763 | Artificial Obstructions | 2684.7038 | 2684.7038 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.171 | 39827 | Construct 1nr Reinforced concrete slab to protect unchartered sewer shaft. | 2402.965 | 2402.965 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
125.172 | 39823 | Provisions to made to allow for protest march on 10/01/2009 at Lothian Road Junction. | 240.1792 | 240.1792 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.173 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.174.1 | 39826 | Completion of trial hole - 13/01/2009 and Artificial Obstructions within. | 1054 | 1054 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.174.2 | 09/01/2009 & 12/01/2009 | Completion of 2 nr trial holes - 09/01/2009 & 12/01/2009, plus Artificial Obstructions. | 1684 | 1684 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.174.3 |  | Completion of 4nr Trial Holes & Artificial Obstructions removed. | 7731 | 7731 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
125.174.4 |  | Completion of final trial hole. | 310 | 310 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.175 | 39822 | Additional Hours to enable completion of trial hole at Lothian Road Junction on 09/01/2009. | 293 | 293 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.176 | 39826 | Drilling of Unidentified mains | 271 | 271 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
125.177 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.178 |  | Instruction for a team to remain unproductively at Lothian Road / Princes St Junction due to camera crew attending site. | 507.0449 | 507.0449 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
125.179 | 39829 | Unproductive resources due to unchartered structure in trial hole. | 240 | 240 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.180 | 39836 | Delay for 3 man team due to early completion of trial hole program. | 347 | 347 | 0 | 0% | Agreed |  |  | 3rd <£2k |  |  | Agreed tie add £347 TL/JC 11/03 |  |  |  | Gen
125.181 | 39847 | Additional 2way traffic light ducts laid at Lothian Road to assist Infraco at later date. | 6887.5024 | 6887.5024 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.182 |  | Additional labourer instructed to manage traffic. | 344.7002 | 344.7002 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
125.183 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.184 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.185 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.186 |  | Failure of tie to issue pedestrian crossing instruction & Phase 3 TM | 5730.27 | 5730.27 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | Gen
125.187 |  | Removal of Redundant Cast Main to facilitate diversion | 235.6222 | 235.6222 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
125.188 |  | Altering Pedestrian Crossing at South Charlotte St. | 374 | 374 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
125.189 |  | Operatives aiding Traffic Management Switchover to enable excavation to commence. | 1860 | 1860 | 0 | 0% | Agreed |  |  | AS |  |  | CUS reduce by £535 TL/JC 11/03 |  |  |  | Gen
125.19 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.191 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.192 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.193 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.194 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.195 |  | Artificial Obstruction | 8760.1634 | 8760.1634 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03 |  |  |  | Gen
125.196 |  | Emergency repair to fragile SW 4 inch main to mitigate further delay. | 1450.94 | 1450.94 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
125.197 |  | Temporary Reinstatement | 5689.6143 | 5689.6143 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
125.198 |  | Abandoned Trial Holes as TQ No. 1396 | 396 | 396 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.199 |  | Artificial Obstruction | 8881.8228 | 8881.8228 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03 |  |  |  | Gen
125.200 |  | Artificial Obstruction | 12423.9199 | 12423.9199 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03
125.201 |  | Crown Engineering removal of structural steel from 3 no. 450mm Road Crossings. | 3012.4979 | 3012.4979 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.202 |  | Sacrificed shoring to maintain public safety. | 926.976 | 926.976 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.203 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.204 |  | Drilling of Unidentified mains | 328 | 328 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.205 |  | Re-excavation of Valves o/s "House of Frasers to enable Swabbing. | 13784.6484 | 13784.6484 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03 |  |  |  | SW
125.206 |  | Re-excavation o/s "Boots" to enable transfer of cross connection from existing 12" to new 355 PE. | 981.463 | 981.463 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.207 |  | Re-excavation for 15" connection at South Charlotte St. | 2551.8039 | 2551.8039 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.208 |  | 1D/SW/D/01 Re-excavtion of Valve 19 to enable Swabbing. | 1727.375 | 1727.375 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.209 |  | Re-excavation to enable 10" connection to conflict 1D/SW/02 & removal of cast. | 3209.6269 | 3209.6269 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.210 |  | Concrete in Connection to 15" South Charlotte. | 132 | 132 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.211 |  | Concrete in cross Connection o/s "Boots". | 329 | 329 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.212 |  | Concrete in excavation o/s "The House of Frasers". | 8628.8219 | 8628.8219 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03 | £8k not certified? | 0 | -8628.8219 | SW
125.213 |  | Concrete in excavation for Valve 19 as per 4th Revision Schematic. | 579 | 579 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.214 |  | Concrete in excavation for tie-in point to existing 10" at South Charlotte. | 1207 | 1207 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.215 |  | Additional reinstatement. | 123 | 123 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.216 |  | TM switch delayed due to Infraco. | 343.2019 | 343.2019 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.217 |  | Artificial Obstruction | 696.2856 | 696.2856 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.218 |  | CUS Aiding Crown Engineerings Burning / Removal of unchartered steel structure from route of 3 no. 450mm SW crossings. | 5704 | 5704 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
125.219 |  | Reinforced Concrete & Extra Over Tar in route of 9" & 3" connections at South Charlotte St. | 3010.948 | 3010.948 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.22 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.221 |  | Resources required to connect to existing 15"; cut & cap exisitng 4" main ; install 80mm SV & Washout then install thrust block as requested. | 2008 | 2008 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | SW
125.222 |  | Concrete within excavtion for 15" & 5" connections at Lothian Road. | 7324.3786 | 7324.3786 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 16/03 |  |  |  | SW
125.223 |  | Drilling of Unidentified mains | 892.1295 | 892.1295 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.224 |  | The street outside the MUDFA Yard was closed by the police on Sat 20th Aug, as a result the Grab Wagon was not capable to leaev the Yard. As the operatives where there to backfill work was on hold until 10:30 am. | 519.384 | 519.384 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.225 |  | Concrete within excavation for additional works. | 4450.7669 | 4450.7669 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.226 |  | Hand Digging for 8" fire connection. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SW
125.227 |  | Temporary Backfill due to Health & Safety. | 169.208 | 169.208 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.228 |  | Re-excavation of Sluice Valves & removal of 45 deg bends to enable swabbing of 3 no. 450mm PE Road crossings. | 7030.1263 | 7030.1263 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
125.229 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.23 |  | Removal of Cast & 10 no. SP cables to enable 1D/SW/D/01, SW/D/04 & 1D/SW/D/05 | 253 | 253 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.231 |  | Exttra Over width within 1D/SW/D/02 & 04 required to enable support to uncharted structure. Adjusted based on discussions | 426.8268 | 426.8268 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.232 |  | Reducing & Rebuilding SV chambers to enable chlorination & swabbing. | 729.9544 | 729.9544 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.233 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.234 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.235 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.236 |  | Additional Inline flow meter requested by tie to be installed on the new 355mm PE water at Princes St. | 3368 | 3368 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
125.237 |  | Reinstated Trial Holes awaiting approval of adequate TM for additional work. | 2382 | 2382 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
125.238 |  | Completion of abandonment of 15" cast gas at Shandwick Place as requested by tie Change Order 5303. | 10659.0533 | 0 | -10659.0533 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
125.239 |  | installalation of additional pedestrian walkway on Princes St. | 395.8107 | 395.8107 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.24 |  | Delay awaiting tie/Infraco TM switch as agreed. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | D&D
125.241 |  | Initial Trial Hole investigation around Gas abandonments as per tie Change Order 5303 and artificial obstruction within excavations. | 3718.1738 | 3718.1738 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
125.242 |  | Additional Reinstatement non MUDFA related. | 1780.9356 | 1780.9356 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.243 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
125.244 |  | Cancellation of 3 no. radius system teams planned for 01st & 02nd October 2009. (continuation of SGN/tie indemnity issue) | 3133.44 | 3133.44 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
125.245 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.246 |  | Removal of Concrete | 624 | 624 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.247 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.248 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
125.249 |  | Hand Digging around existing SP traction cables. | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | SP
125.25 |  | Double Handling Spoil & Backfill from Lothian Road / Princes St to Haymarket required until CUS gained possession of the main site compound on the North Bound carriageway of Princes St from Infraco. | 3586.1437 | 3586.1437 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
125.251 |  | Requirement for use of 6m3 + EO foam concrete for o/s no 1-3 Shandwick Place and Canning St. | 129 | 129 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 471995.2797 | 430920.0208
CR 129 |  |  |  | 0 | 0 | 0 | Agreed(*)
|  | 0 | 0 |  | 0 | 0%
129.7 |  | Logistic support | 63693.7723 | 63693.7723 | 0 | 0% | Logistic Support |  |  | 3rd >£10k | [6 empty] | Gen
129.8 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.9 | 39707 | Abandoned track including hand digging | 1651 | 1651 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.1 | 39698 | Abandoned trial holes | 1480 | 1480 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.11 | 39698 | Abandoned Trial Holes | 3206.1358 | 3206.1358 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.12 | 39716 | Removal of road signage | 82 | 82 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.13 | 39716 | Removal of Artificial Obstructions (concrete) | 1307 | 1307 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.14 | 39735 | Artificial Obstructions (concrete) | 2580.8527 | 2580.8527 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.15 | 39735 | Removal of artificial obstructions (cast iron) | 235 | 235 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.16 | 39701 | Removal of artificial obstructions (cast iron) | 271 | 271 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.17 | 39732 | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.18 | 39732 | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.19 | 39732 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.2 | 39732 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.21 | 39727 | Artificial Obstructions (concrete and excess carraige way) | 4181.1269 | 4181.1269 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.22 | 39735 | Artificial Obstruction (Concrete) | 2581 | 2581 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.23 | 39705 | Removal of artificial obstructions (cast iron) | 263 | 263 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.24 | 39731 | Abandoned Track | 1147 | 1147 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.25 | 39737 | Artificial obstructions (abandoned underground structure) | 1007 | 1007 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.26 | 39734 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.27 | 39734 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.28 | 39734 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.29 | 39734 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.3 | 39734 | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.31 | 39749 | Demolishing Virgin Media Box | 386 | 386 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | VM
129.32 | 39725 | Hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.33 | 39739 | Hand Digging (Multi diversional works) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.34 | 39755 | Gas connection abandoned due to condition of existing main | 790 | 790 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
129.35 | 39738 | Delay, disruption and dislocation due to TM | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | D&D
129.36 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.37 | 39765 | Reinstating information poles | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.38 | 39757 | Duct protection replacement | 855 | 855 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
129.39 | 39757 | Removal and replacement of slabs to enable required compaction of diversions | 1698 | 1698 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.14 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) |  |  | 3rd
129.41 | 39772 | Artificial obstructions | 2329.485 | 2329.485 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.42 | 39772 | Trial hole and artificial obstructions | 1760 | 1760 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.43 | 39730 | Removal of sign posts | 238 | 238 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.44 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.45 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.46 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.47 | 39819 | Use of Gully Sucker |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
129.48 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.49 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.5 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.51 | 39757 | Abandoned Trial Hole | 572 | 572 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.52 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.53 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.54 | 39826 | Abandoned Trial holes | 2461.0186 | 2461.0186 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.55 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.56 | 39833 | Abandoned Track | 1017 | 1017 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.57 | 39835 | Trial Holes | 387.408 | 387.408 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.58 | 39836 | Removal of road signage | 268 | 268 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.59 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.6 | 39839 | Removal of road signage | 135 | 135 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.61 | 39829 | Ababdoned Track | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.62 | 39818 | Hand digging due over congested tracks | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.63 | 39832 | Hand digging due over congested tracks | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.64 | 39841 | Emergency repair to Scottish Water fire hydrant - damaged by no direct fault of CUS | 218 | 218 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW | 100
129.65 | 39847 | Abandoned track due to over congestion | 2775.94 | 2775.94 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.66 | 39847 | Gas connection - Down Time | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SGN
129.67 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.68 | 39849 | Use of foam concrete | 1001.6128 | 1001.6128 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.69 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.7 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.71 | 39849 | Trial holes | 196 | 196 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.72 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.73 | 39849 | Removal of lamp standards | 537 | 537 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.74 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.75 |  | Nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.76 | 39818 | Hand digging due to excessive congestion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.77 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.78 | 39829 | Trial Holes | 1765 | 1765 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.79 | 39818 | Double Handling of Materials | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
129.8 | 39857 | Use of concrete due to shallow depth | 1283 | 1283 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.81 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.82 | 39857 | Downtime due to a telecoms duct obstructing SP diversion | 245 | 245 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
129.83 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.84 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.85 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.86 | 39844 | Excessive hand digging |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.87 | 39863 | Artificial Obstructions - Part of embargo works. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | top 68 | [6 empty] | Gen
129.88 | 39863 | Uncover gas connection area | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SGN
129.89 | 39863 | Removal of lamp posts | 492 | 492 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.9 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.91 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.92 |  | Trial Holes | 1154 | 1154 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.93 | 39844 | Excessive hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.94 | 39851 | Excessive hand digging week ending 13/02/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.95 |  | Slew 4 way cable and wireless | 5853.56 | 5853.56 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | CW
129.96 | 39867 | Artificial Obstructions on structure | 4597.53 | 4597.53 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.97 | 39880 | Removal of brick and steel structure | 5811.73 | 5811.73 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | Gen
129.98 | 39857 | Disrupted Plant | 11055.2742 | 0 | -11055.2742 | -100% | Disrupted Plant |  |  | 3rd | [6 empty] | Gen
129.99 | 39874 | Shoring [not incl shoring hire cost (separate cost build up] | 3677.774 | 3677.774 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.1 | 39874 | Removal of Cast Iron Pipes | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
129.101 |  | Gas Bypass on York Place | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.102 |  | Demolish box | 193 | 193 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
129.103 |  | Demolish box | 457.191 | 457.191 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
129.104 | 39858 | Hand digging for weekending 20/02/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.105 | 39865 | Hand digging week ending 27/02/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.106 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.107 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.108 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.109 |  | Exposing power cables | 214 | 214 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
129.11 | 39881 | Breaking away concrete | 393 | 393 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.111 | 39881 | Removal and replacement of steel plates | 1339 | 1339 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.112 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.113 |  | Gas bypass o/s Harvey Nichols |  |  | 0 | 0% | Agreed(*) | [9 empty] | SGN
129.114 |  | Removal of traffic signal | 93 | 93 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.115 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.116 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.117 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.118 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.119 |  | Artificial Obstructions | 234.4708 | 234.4708 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.12 |  | Artificial obstructions | 771.4845 | 771.4845 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.121 |  | Artificial Obstructions | 2325.7988 | 2325.7988 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.122 |  | Extra removal of sub structure | 357 | 357 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
129.123 |  | Hand digging W/E 06/03/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.124 |  | Hand digging for week ending 13/03/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
129.125 |  | Steel cutting on under ground structure | 1584.47 | 1584.47 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.126 |  | Trial Holes | 852.2976 | 852.2976 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.127 |  | Abandoned track and artificial obstructions | 3140.0314 | 3140.0314 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.128 |  | Artificial Obstructions | 1875.7662 | 1875.7662 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.129 |  | Artificial Obstructions | 2243 | 2243 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.13 |  | Slew and lower 4 way verizion ducts. Item was slewed in order to build a coms box- track from which ducts were slewed was not recovered anywhere. Withdrawn | 0 | 0 | 0 | 0% | Agreed(*) |  |  | top 68 | [6 empty] | Ver
129.131 |  | Artificial obstructions | 1350.0978 | 1350.0978 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.132 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.133 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
129.134 |  | Hand digging w/e 20/03/2009 |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
129.135 |  | Hand digging w/e 27/03/2009 |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
129.136 |  | Abandoned Tracks | 4405.67 | 4405.67 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
129.137 |  | Slew 1 way verision and 1 way cable and wireless REVISED RATE TO WITH 25% UPLIFT FOR SLEW. | 4031.38 | 4031.38 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | BT
129.138 |  | Split ducting | 183 | 183 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | BT
129.139 |  | Foam Concrete | 3191 | 3191 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
129.14 |  | Demolish vergin media boxes | 1430.1472 | 1430.1472 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
129.141 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.142 |  | Artificial Obstruction within 1C2/SP/JB/10, Scottish Power Joint Bay at Dublin St. | 1802 | 1802 | 0 | 0% | Agreed | [5 empty] | TL/JC agreed 26/05 |  |  |  | SP
129.143 |  | Artificial Obstructions | 3551.0976 | 3551.0976 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.144 |  | Demolish Virgin Media box o/s Harvey Nichols | 382.4581 | 382.4581 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
129.145 |  | Removal of Traffic Signal | 339.4387 | 339.4387 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
129.146 |  | Gas Bypass on Princes Street | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.147 |  | Repair to cellar | 1313.2922 | 1313.2922 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.148 |  | Water bypass to allow continuation of new diversions | 5034.1542 | 2000 | -3034.1542 | -60.27% | Bypass |  |  | new | not incl in CC246 this is water | [5 empty] | SW
129.149 |  | Water bypass to allow gas connection | 6707.7158 | 2000 | -4707.7158 | -70.18% | Bypass |  |  | new | not incl in CC246 this is water | [5 empty] | SGN
129.15 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.151 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.152 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.153 |  | Repair water main | 182 | 182 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
129.154 |  | Gas bypass at North St Andrews Lane | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.155 |  | Gas Bypass o/s Zest | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.156 |  | Gas bypass at North St Andrews square | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.157 |  | Gas bypass South St Andrews Square | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.158 |  | Gas bypass O/S Tiles Bar | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.159 |  | Gas bypass at West Register Street | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.16 |  | Foam concrete o/s tiles bar | 150.2419 | 150.2419 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
129.161 |  | Gas bypass o/s Barcley's Bank | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
129.162 |  | Povision of walkways | 2500 | 2500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
129.163 |  | Cut and Cap Water Mains | 780 | 780 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
129.164 |  | Steel plates over power | 365.8775 | 365.8775 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
129.165 |  | Removal of uncharted ducts | 149.3655 | 149.3655 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
129.166 |  | Demolish and remove link box | 142.6153 | 142.6153 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
129.167 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.168 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.169 |  | Trial holes on York Place | 2753.6031 | 2753.6031 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.17 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.171 |  | Foam Concrete | 129 | 129 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.172 |  | Hand digging due to existing services | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
129.173 |  | Demolish boxes | 906.0469 | 906.0469 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
129.174 |  | Erecting rino fencing for advertisment space for stakeholder during festival | 238.3204 | 238.3204 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.175 |  | Standdown resoures due to noise levels | 559 | 559 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.176 |  | Abandoned 6 way virgin media | 671 | 671 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
129.177 |  | Assessed Elsewhere (see Master Change Control Register) | 9854.9517 | 0 | -9854.9517 | -100% | Exc Abandonment |  | review separately |  |  |  |  | Was in measure but now CC as per Mar AFP (removed Agreed* status). JC discussed with JC |  | 0 | SW
129.178 |  | Service connections | 6129.4779 | 0 | -6129.4779 | -100% | Supply Connections |  |  | new | [6 empty] | SW
129.179 |  | A1 Jointing Ltd for jointing works | 4243.2 | 4243.2 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
129.18 |  | Slew 3 way thus ducts for 1c2/sp/d/02 | 12738.0211 | 0 | -12738.0211 | -100% | Slew Utilities |  |  | new | [6 empty] | THUS
129.181 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
129.182 |  | Obsticals obstructing 1C2/SP/D/02 | 583.2018 | 583.2018 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
129.183 |  | Proof of diversion | 144 | 144 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
129.184 |  | Provission of walkway | 400 | 400 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
129.185 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
129.186 |  | Artficial Obstructions | 624.6092 | 624.6092 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
129.187 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
129.188 |  | Artificial obstruction - Excess carraigeway | 1351.6133 | 1351.6133 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 166814.7216 | 155759.4474
129.189 |  | Requirement to demolish and rebuild a Thus CW2 chamber to facilitate diversion 1C/SP/D/02. | 1480 | 1480 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | THUS
129.19 |  | Carry out additional duct testing on South St Andrews / Princes St at night. | 437 | 437 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
129.191 |  | CUS were required to remove silt from duct route originally laid in 2007. | 739 | 739 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
CR 144 | [6 empty] | Agreed(*)
144.1 |  | Purchase materials In the event of Scottish Water Outage | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.2 | 39496 | 800mm Water Main trial holes | 4276.5798 | 4276.5798 | 0 | 0% | Agreed |  |  | new |  |  | Agreed JC/TL 20/05 |  |  |  | SW
144.3 |  | Purchase 800mm Water Main materials | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.4 |  | Purchase 800mm Water Main materials | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.5 |  | Purchase 800mm Water Main materials | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.6 |  | Supply Call-off materials as required | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.7 |  | Installation of 800mm water main at Gogar Depot Site. | 1838000 | 1838000 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.7B |  | Revised CCE allocation of costs for CC144 as Mar 10 AFP submission | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | Agreed TL/JC 20/05 |  |  |  | SW
144.9 | 39587 | Bactec Survey | 7643.2 | 7643.2 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
144.23 |  | 800mm diameter water main backfill at Gogar Depot | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
144.34 |  | 100 ton of Crusher Run for Gogar haul rd. | 3114.944 | 3114.944 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
144.35 | 39805 | Supply vacum/jetter machine | 2112.6784 | 2112.6784 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
144.36 | 39792 | Excavate drainage channel | 1261.0516 | 1261.0516 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
144.37 | 39799 | Disconnect and reconnect 600mm main | 1109.2607 | 1109.2607 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
144.38 | 39829 | Slew 3w CW and remove 250DI water main (70) | 3481 | 3481 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed TL/JC 20/05 |  |  |  | CW
144.63 |  | Provision of Red Line Drawings | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | Agreed JC/TL 20/05 |  |  |  | Gen
0
CR 149 | [6 empty] | Agreed(*)
[5 empty] | 0 | 0%
149.4 | 39507 | Trial Holes, Artificial Obstructions | 3594.0087 | 3594.0087 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.06 | 39512 | Remove Reinforced Concrete from existing 12way BT duct line. | 360.405 | 360.405 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
149.07 | 39520 | Remove 450mm D/I to validate bedding. | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | SW
149.08 | 39526 | Trial Holes Requested by Scottish Power | 529.99 | 529.99 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
149.14 | 39511 | Additional Excavations & Traffic Management due to the existing 450mm Water Main bursting because of absence of Thrust Block. | 3726.9246 | 3726.9246 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
149.15 | 39512 | Abandoned Trial Hole for Transmission Cables & Pilots. | 388.9047 | 388.9047 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
149.16 | 39517 | Abandoned trial hole due to not locating existing pilots. | 765.5412 | 765.5412 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
149.17 | 39513 | Abandoned Trial Holes to Ascertain Depths of Existing Power. | 3441.2548 | 3441.2548 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
149.18 | 39510 | Removal of Concrete. | 290.119 | 290.119 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
149.22 |  | Removal of centrel reserve at junction of South Gyle Access and Bankhead Drive - Now CC166 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.23 | 39542 | Abandoned trial hole and extra carriageway excavation as per original 450mm water tie-in point that is now abandoned. | 1074.702 | 1074.702 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.24 | 39539 | Downtime associated with hand digging around existing gas mains & related downtime waiting on SGN supervision. | 1602.2812 | 1602.2812 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
149.25 | 39547 | Demolish JRF6 to build JUF110 in location. | 1097.0719 | 1097.0719 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
149.26 | 39559 | Slewing existing ducts from route of diversion. | 591.8176 | 591.8176 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
149.27 | 39553 | Checking route of conflict 5B/TE/01 with drain rods & sonde. (cost to be mitigated against gain share reference 29) | 131.3184 | 131.3184 | 0 | 0% | Agreed |  |  | AS
149.28 | 39573 | Trial Hole requested by tie to check whether it would be possible for the 450mm water main to tie-in to existing before the guided busway. This proved unsuccessful. | 245.3658 | 245.3658 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.29 | 39559 | Artificial Obstructions. | 133.1134 | 133.1134 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.30 | 39547 | Necessary overtime working to lay 450mm water main & 1 way BT across guided busway. 20 hours N.P.O. & 20 hours sleep time for changing shift patterns. | 2604.4744 | 2604.4744 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW & BT
149.31 | 39566 | Excavation to expose thrust blocks on 450mm water main & reinstate. | 1224.9956 | 1224.9956 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.32 |  | All Disrupted Plant Relating to 5B-01-01 | 0 | 0 | 0 | 0% | Disrupted Plant |  |  | new | [6 empty] | Gen
149.34 |  |  | 0 | 0 | 0 | 0% | Agreed |  |  | AS
149.35 | 39617 | Hand digging. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.36 | 39631 | Hand digging aroung existing utilities. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.39 | 39658 | The use of 7.5m3 of Foam Concrete in diversion | 375.6048 | 375.6048 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.4 | 39695 | Supply & Install 675 x 675 Manhole Cover to existing Frame | 132 | 132 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
149.41 | 39694 | Down time due to failure of altering existing traffic signals | 1490.3572 | 1490.3572 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.44 | 39741 | CUS have carried out the necessary repair to the 225mm sewer pipe as per tie CVI 1553 | 3223.7078 | 3223.7078 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
149.45 | 39710 | Traffic management resulting in down time | 2990.3476 | 2990.3476 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
149.46 | 39779 | Installation of 2 No. CCTV Cabinets. | 1468.0122 | 1468.0122 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 9542.7257 | 9542.7257
CR 153 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
153.4 | tbc | Logistics Support Team | 227360.7167 | 227360.7167 | 0 | 0% | Logistic Support |  |  | 3rd >£10k | [6 empty] | Gen
153.6 | 39538 | Supply of Heras Fencing |  | 0 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email
153.07 | 39547 | Support foundations of existing sandstone wall. | 170 | 170 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.08 | 39547 | Supply of extra Footboards & Road Plates | 2417.7536 | 2417.7536 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.09 | 39547 | Assisting Archaeologist. | 274 | 274 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.10 | 39547 | Pump water from road crossing due to existing leaning Scottish Water valve. | 416 | 416 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.11 | 39547 | Assisting the Archaeologist. | 910 | 910 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.12 | 39538 | Re-positioning of existing heras fencing on tie request. | 333 | 333 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.13 | 39539 | Remove existing traffic signal columns & replace with new column. | 651 | 651 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.14 | 39539 | Remove existing "No Waiting" column to enable logistics team access for deliverables. | 248 | 248 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.15 | 39547 | Uncovering & removing historic tram rails from diversion path. | 243 | 243 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.16 | 39539 | Remove Traffic Island. | 668 | 668 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.17 | 39546 | Artificial Obstructions. | 2054.7252 | 2054.7252 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.18 | 39541 | Removal of Artificial Obstructions. | 3696.4575 | 3696.4575 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.19 |  | Removal of Artificial Obstruction. | 454 | 454 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.20 | 39550 | Completion of Road & Pedestrian crossing on Saturday 12th April 2008, to accommodate business & residential requirements. | 870 | 870 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.21 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.22 | 39546 | Removal of Artificial Obstructions. | 6532.7974 | 6532.7974 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
153.23 | 39548 | Hand digging around existing utilities. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
153.24 | 39545 | Hand digging around existing utilities. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
153.25 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.26 | 39552 | De-mobilise & Re-mobolise labour, plant & equipment due to City of Edinburgh Councils non-attendance on site to remove street furniture. | 203 | 203 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.27 | 39554 | Inspection & removal of unchartered sandstone culvert. | 237 | 237 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.28 | 39554 | Assisting archaeologist investigate, measure & then remove unchartered sandstone culvert. | 496 | 496 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.29 | 39554 | Abandoned Trial Hole for BT Manhole. | 709 | 709 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
153.30 | 39555 | Removal of historic tram sleeper from route of diversion. | 173 | 173 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.31 | 39560 | Artificial Obstruction | 9102.9105 | 9102.9105 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
153.32 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.33 | 39566 | Downtime due to water leak | 832 | 832 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.34 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.35 | 39563 | Extra Ducts layed on Scottish Power crossing | 1258 | 1258 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
153.36 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.37 | 39562 | Divert around unchartered utility | 352 | 352 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.38 | 39549 | Assisting Archaeologists | 1568 | 1568 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.39 | 39552 | Artificial Obstruction | 2751.0108 | 2751.0108 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.4 | 39554 | Removal of 16 way BT Concrete duct, slewing & lowering of existing BT 2 way duct | 6949.1648 | 6949.1648 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
153.41 | 39557 | Extra digging around unchartered utilty 600mm deeper than spec | 411 | 411 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
153.42 | 39552 | Awaiting removal of solar powered ticket machine to continue diversions | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
153.43 | 39555 | Extra digging around existing M/H & old gas lamp standard | 1228 | 1228 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.44 | 39567 | Delays to diversion assisting Archaeologists | 411 | 411 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.45 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.46 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.47 | 39580 | Delay & Disruption to Zone diversions | 246.3438 | 246.3438 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.48 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.49 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.5 | 39540 | Extend width of Road Crossing to 1m to assist Archaeologists | 666.0765 | 666.0765 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.51 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.52 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.53 | 39584 | Additional cut back on Reinstatement due to existing cracks | 482.2549 | 482.2549 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.54 | 13/05/08,14/05/08, | Artificial Obstruction | 1884 | 1884 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.55 | 39580 | Repairs to sewage manhole | 357 | 357 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.56 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.57 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.58 | 39589 | Removal of Artificial Obstruction | 1070.765 | 1070.765 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.59 | 39587 | Rebuildiing of existing Traffic Control Chamber | 282.87 | 282.87 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.6 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.61 | 39604 | Removal of Artificial Obstruction | 835.4181 | 835.4181 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.62 | 39605 | Divert around existing Road gulleys | 1119 | 1119 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.63 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.64 | 39616 | Removal of Buried Brick wall | 315.5625 | 315.5625 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.65 | 39618 | Demolishing of Existing Chambers | 3167.168 | 3167.168 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
153.66 | 39618 | Demolish Existing JRC1 Box | 1354 | 1354 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
153.67 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.68 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.69 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.7 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.71 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.72 | 39630 | Abandoned Trial Holes on diversion | 491 | 491 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.73 | 39636 | Removal of Concrete from diversions 95 x 0.9 x 0.25 | 7304.1727 | 7304.1727 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
153.74 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.75 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.76 | 39636 | Delay, Disruption & Dislocation | 3012.128 | 0 | -3012.128 | -100% | Sep'08 Settlement |  |  | 3rd | Item certified by tie at time of Sep'08 settlement | 3012.128 | JC said S Bell dealing with 11/03 |  |  |  | Gen
153.77 | 39650 | Removal of Concrete from various road crossings on Constitution St | 2145.1741 | 2145.1741 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.78 |  | Disrupted Plant (exludes post Sep 08 Disrupted Plant) | 21729.0308 | 0 | -21729.0308 | -100% | Disrupted Plant |  |  | 3rd | [6 empty] | Gen
153.79 | 39630 | Use of Foam Concrete on Junction of Coatfield lane 10m3 | 501 | 501 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.8 | 39637 | Removal of Old lamp standard from o/s of Be Seated | 444 | 444 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.81 | 39631 | Delays to the programme caused by funerals and morning service at ST Marys RC Church | 1238 | 1238 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.82 | 39653 | Removal of Concrete from diversion | 230 | 230 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.83 | 39671 | Removal & replacing of Road Gulley | 657 | 657 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.84 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.85 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.86 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.87 | 39514 | Delay, disruption and dislocation due to TM | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.88 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.89 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.9 | 39686 | Removal of Concrete from diversions | 556.0045 | 556.0045 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.91 | 39682 | Demolishing of existing Thus Box | 847.6093 | 847.6093 | 0 | 0% | Agreed |  |  | AS | [6 empty] | THUS
153.92 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.93 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.94 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.95 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.96 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.97 | 39638 | Delay to the program, awaiting Tie Ltd TQ Response | 71 | 71 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.98 | 39717 | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.99 | 39717 | Abandoned Trial Hole | 761.6576 | 761.6576 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.1 | 39717 | Hand digging around existing utilities | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.101 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.111 |  | Assessed Elsewhere (see Master Change Control Register) | 0 |  | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
153.121 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.131 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.141 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.106 | 39724 | Additional reinstatement due to unstable ground | 387.6 | 387.6 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.107 | 39724 | Artificial Obstruction (concrete) | 334.7147 | 334.7147 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.108 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.109 | 39723 | Hand digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.11 | 39722 | Artificial Obstructions (concrete) | 1245.0991 | 1245.0991 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.111 | 39722 | Removal of excess carraigeway | 556.0045 | 556.0045 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.112 | 39722 | Abandoned Trial Hole | 362.6941 | 362.6941 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.113 | 39724 | Demolishing BT Boxes | 640.5548 | 640.5548 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
153.114 | 39730 | Abandoned Track | 956.2194 | 956.2194 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.115 | 39729 | Access to post office by requirement of the police | 120 | 120 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.116 | 39745 | Abandoned Trial Holes | 1216 | 1216 | 0 | 0% | Agreed |  |  | 3rd <£2k |  |  | Agreed tie add £235 TL/JC 11/03 | £0.2k tie not certified? | 981 | -235 | Gen
153.117 | 39758 | Abandoned Trial Holes | 981 | 981 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.118 | 39745 | Abandoned Trial Holes | 642 | 642 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.119 | 39780 | Abandoned Trial Hole to determin extent of sewer | 684 | 684 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
153.12 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.121 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.122 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.123 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.124 | 39850 | Trial Holes | 2573.8868 | 2573.8868 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.125 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.126 | 39856 | Delay due to Archiologist | 2712.5899 | 2712.5899 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.127 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
153.128 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.129 | 39839 | Abandoned Tracks | 21200.1696 | 21200.1696 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
153.13 | 39839 | Delay and Disruption due to un-answered TQ's and closere or work area | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
153.131 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.132 |  | Stand down due to funeral | 179 | 179 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
153.133 |  | Cut out window of BT M/H | 1121 | 1121 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
153.134 |  | Stand down due to Mass | 26038.3856 | 0 | -26038.3856 | -100% | Other (WS) |  |  | new | [6 empty] | Gen
153.135 |  | Down time due to Archiologist | 3826 | 3826 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
153.136 |  | Artificial obstructions | 670.3215 | 670.3215 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.137 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.138 |  | Transport geonet ducts | 131 | 131 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
153.139 |  | Removal of cast iron | 562.4449 | 562.4449 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
153.14 |  | Hand digging w/e 15/05/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.141 |  | Hand digging w/e 08/05/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.142 |  | Hand digging w/e 01/05/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.143 |  | hand digging w/e 24/04/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.144 |  | Hand digging w/e 17/04/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.145 |  | Hand digging w/e 03/04/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.146 |  | Hand digging w/e 27/03/2009 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
153.147 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.148 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.149 |  | Gas Bypass - Now claimed in CC 246 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
153.15 |  | Gas Bypass - Now claimed in CC 246 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
153.151 |  | Gas Bypass - Now claimed in CC 246 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
153.152 |  | Gas Bypass - Now claimed in CC 246 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
153.153 |  | Removal of cast iron | 297 | 297 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
153.154 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.155 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.156 |  | Trial hole o/s 37 constitution street | 624.5285 | 624.5285 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.157 |  | Services conections exceeding 1m in length | 7217.3305 | 0 | -7217.3305 | -100% | Supply Connections |  |  | new | [6 empty] | SW
153.158 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.159 |  | Re-test water main after loss of samples by Scottish Water | 612.0642 | 612.0642 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
153.16 |  | Gas Bypass - Now claimed in CC 246 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SGN
153.161 |  | Gas Abandonment of the 14'' main on Duke Street | 25505.0595 | 0 | -25505.0595 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
153.162 |  | Services conections exceeding 1m in length | 4071.674 | 0 | -4071.674 | -100% | Supply Connections |  |  | new | [6 empty] | SW
153.163 |  | Foam concrete at Queen Charlotte Junction | 951.5322 | 951.5322 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.164 |  | Removal of BT cabinet | 662.9399 | 662.9399 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
153.165 |  | Removal of traffic light | 472.7659 | 472.7659 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.166 |  | Install BT cabinet | 541.2592 | 541.2592 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
153.167 |  | Artificial obstructions | 273.0532 | 273.0532 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.168 |  | Gas Abandonment of the 6'' main on Duke Street | 10934.1271 | 0 | -10934.1271 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
153.169 |  | Supply Connections | 5882.1226 | 0 | -5882.1226 | -100% | Supply Connections |  |  | new | [6 empty] | SW
153.17 |  | Store cobble setts and secure | 80.3419 | 80.3419 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.171 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.172 |  | Nill (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
153.173 |  | Foam concrete backfill | 600.9677 | 600.9677 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
153.1754 |  | Remove conrete and trial holes | 1444.083 | 1444.083 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 376683.2328 | 325903.6884
153.176 |  | Additional Works - Slew 16w BT ducts round a thrust block. The works were required by Scottish Water Solutions. Reinstatement was in a cobbled road. | 19638.7917 | 0 | -19638.7917 | -100% | Slew Utilities |  |  | new | [6 empty] | BT
153.177 |  | Nill (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
153.178 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
153.179 |  | Nill (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
153.18 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
153.181 |  | Abandonment of the 12" main on Constitution Street. | 27529.3594 | 0 | -27529.3594 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
153.182 |  | Abandonment of the 9" main on Constitution Street. | 329 | 329 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
CR 154 | [6 empty] | Agreed(*)
154.1 |  | Archaeological recordings of undergreound chamber | 5204.9376 | 5204.9376 | 0 | 0% | Agreed |  |  | AS |  |  | agreed tie add £5205 TL/JC 11/03 |  |  |  | Gen
154.2 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.3 |  | All Disrupted Plant | 39824.2681 |  | -39824.2681 | -100% | Disrupted Plant |  |  | 3rd >£10k | [6 empty] | Gen
154.4 |  | Logistic support for Elm Row | 34147.4312 | 34147.4312 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.5 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.6 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.7 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.08 | 39666 | Abandoned Trial Holes | 490.7315 | 490.7315 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.09 | 39681 | Artificial Obstructions | 626 | 626 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.10 | 39681 | Artificial Obstructions | 1424 | 1424 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.11 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.12 | 39681 | Resources used to transfer spoil to an area where the HIAB can lift it due to alterations in Traffic Management. |  |  | 0 | 0% | Agreed |  |  | AS
154.13 | 39682 | Use of spill kit to absorb oil leak from bus. | 20.6176 | 20.6176 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.14 |  | Unproductive time spent locating BT conflicts. | 778.3734 | 778.3734 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
154.15 | 39689 | Repair of Unchartered, Shallow ducting | 213.9008 | 213.9008 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.16 |  | Unproductive resources due to unresolved TQ 860, coupled with inability to locate BT conflicts and inability to contact Davie Finnie of BT. Inabilty to carry out productive works noted on tie CVI 1633 | 0 |  | 0 | 0% | Agreed |  |  | new |  |  | D&D Elsewhere |  |  |  | BT
154.17 | 39685 | Unproductive Resources due to unresolved TQ's and conflicts not as per IFC's. |  |  | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.18 | 39687 | Unproductive manhole team. |  |  | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT
154.19 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.2 | 39702 | Artificial Obstruction | 695 | 695 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.21 | 39702 | Artificial Obstruction | 911 | 911 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.22 | 39702 | Re-excavating 1D/SP/D/23 to accept 12 No. Insurance ducts as opposed to scheduled 8 No. ducts. | 763 | 763 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
154.23 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.24 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.25 | 39699 | Abandoned Trial Holes | 964.1201 | 964.1201 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.26 |  | Excavate 400mm Water crossing at weekend of 13th & 14th Sept 2008 | 522.24 | 522.24 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.27 | 39702 | Artificial Obstructions | 4637.0779 | 4637.0779 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.28 | 39702 | Artificial Obstructions | 1225 | 1225 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.29 | 39707 | Employment of Crown Engineering to burn steel beams safely from BT manhole | 661.2864 | 661.2864 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
154.3 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.31 | 39709 | Demolition of existing manhole in order to construct new MRX10A. | 6547.3969 | 6547.3969 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
154.32 | 39709 | Removal of Street Furniture. | 263.6369 | 263.6369 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.33 | 39702 | Removal of capped 15" Gas main. | 179 | 179 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
154.34 | 39699 | Hand-digging around 6way verison and unidentified cable and removal of steel beam. |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
154.35 | 39701 | Hand-digging. | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.36 | 39693 | Unproductive resources due to TM alterations and various unanswered TQ's. | 5970.6502 | 5970.6502 | 0 | 0% | Sep'08 Settlement |  |  | 3rd | [6 empty] | Gen
154.37.1a | 39678 | Inefficient Resources due to Traffic Management Design Issues. (excluding manhole team claimed in 154.37.3) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.37.1b | 39678 | Double Handling materials due to Traffic Management Design Issues. (excluding manhole team claimed in 154.37.3) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.37.2 | 39682 | Remobilised Resources due to seven diversions scheduled for original Haymarket Traffic Management falling out with de-scoped Traffic Management. (i.e. demobilise/re-mobilise resources sent off site and some utilised unproductively elsewhere; evaluated @ 50% efficient) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
154.37.3 | 39678 | Double Handling materials to BT manhole – 1D/BT/D/54 due to minimum load bearing capacity of adjacent retaining wall and reduced 'Worksite 3'. Minus 42 team hours spent demolishing existing manhole - CVI 00459 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT
154.38 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.39 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.4 | 39723 | Additional Slewing & Lowering of 3 No. existing power cables to provide route for 1D/SW/D/25. | 1411.2883 | 1411.2883 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.41 | 39723 | Drill & Tap 4 inch cast main, then subsequently remove from route of diversion. | 168.382 | 168.382 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.42 | 39711 | Weekend working required to recoup time lost to the program awaiting TQ responses. | 740 | 740 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.43 | 39721 | Artificial Obstruction | 2766.0522 | 2766.0522 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.44 | 39721 | Artificial Obstruction | 5836.643 | 5836.643 | 0 | 0% | Agreed |  |  | 3rd | [6 empty] | Gen
154.45 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.46 | 39736 | Manual excavation in 1D/SP/D/24 | 339 | 339 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
154.47 | 39736 | Removing 3"CI main on diversion 1D/SW/D/43 | 562.8033 | 562.8033 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.48 | 39736 | Removal of unchartered structure from route of 1D/SP/D/23. | 398.2596 | 398.2596 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
154.49 | 39692 | Unproductive resources whilst awaiting clarification on duct formation at 1D/SP/D/23 | 522 | 522 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
154.5 | 39711 | Reclaim of resources costs due to late call off of works around Haymarket Retaining Wall. | 1349.12 | 1349.12 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.51 | 39742 | Purchase and compaction of additional stone to enable excavation of altered SW diversions. (TQ 964) | 743.8323 | 743.8323 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.52 | 39742 | Hand digging around existing utilities at above diversion | 224.7731 | 224.7731 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.53 | 39741 | Artificial Obstruction | 1467 | 1467 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.54 | 39736 | Additional Backfill/ Reinstatement | 408.6285 | 408.6285 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.55 | 39736 | Artificial Obstructions | 3072.8518 | 3072.8518 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.56 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.57 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.58 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.59 | 39749 | Artifical Obstruction | 978.307 | 978.307 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.6 | 39750 | Whilst excavation for a connection point CUS undercovered what looks like the start of a tunnel structure. This area had to be hand dug. | 620 | 620 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.61 | 39750 | CUS were required to transport excavated material from the mentioned diversion to the main site compound due to access problems | 130.5431 | 130.5431 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.62 | 39718 | Diversion required essential weekend working | 1649.408 | 1649.408 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.63 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.64 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.65 |  | tie accepted the use of foam concrete on the following water diversions at Haymarket:- 1D/SW/D/25, 1D/SW/D/23 & 1D/SW/D/23a. In pratice only 1D/SW/D/25 (2 no road crossings aspect where foamed due to alterations). | 2889 | 2889 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.66 | 39741 | Artificial Obstructions | 4945.6758 | 4945.6758 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.67 | 39762 | Removal of steel tram structure | 33.6291 | 33.6291 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.68 | 39762 | Hand-Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.69 | 39762 | Artifical Obstruction | 4716.9938 | 4716.9938 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
154.7 | 39762 | Artifical obstruction | 443 | 443 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.71 | 39769 | Remove concrete from the above diversion | 5914.1375 | 5914.1375 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.72 | 39771 | Transporting excavated material from diversion to main site due to access. | 6420.5543 | 6420.5543 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.73 | 39727 | Downtime due to Archaeologist. | 166.8258 | 166.8258 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.74 | 39778 | Due to uncharted 6" water bypass pipe work could not proceed the the two mentioned diversions | 800.7636 | 800.7636 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
154.75 | 39773 | Hand-digging around existing utilites | 890 | 890 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.76 | 39778 | Whilst excavating the mentioned diversion Cus were required to remove the following amount of concrete. | 1588.3504 | 1588.3504 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.77 | 39781 | Abandoned trial hole | 426.8292 | 426.8292 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.78 | 39773 | Artifical Obstruction | 4235.601 | 4235.601 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.79 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.8 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.81 | 39780 | Late verbal instruction to cancel the next phase of traffic management. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
154.82 |  | nil (see Master Change Register) |  |  | 0 | 0% | Agreed(*)
154.83 | 39791 | Reinstatement of 15th Century Well. | 782.8298 | 782.8298 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.84 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.85 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.86 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.87 | 39837 | Cus were required to arrange to have the power disconnected at the bus stop at Haymarket Place to allow the bus stop to be removed | 498 | 498 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.88 |  | Additional thrust block to protect existing main as instructed by tie 3506 | 439.2474 | 439.2474 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.89 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.9 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.91 | 39799 | Cus were required to remove 10m x 6" CI water main from the above diversion | 135.8118 | 135.8118 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.92 | 39756 | Due to work site layout Cus were required to transport excavated material round the oneway contraflow in place. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
154.93 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.94 | 39801 | Due to Christmas embargo Cus were required to temporary backfill the above diversion. | 884.4512 | 884.4512 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.95 | 39798 | Cus were required to carry out the tie in connection on the above mentioned diversion, This was carried out through the night of the 16/12/08. | 1419 | 1419 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.96 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.97 | 39819 | Wasted 1 way due to requirement to re-excavate for 4 way following ammendments on-site (as per tie 1634). | 555 | 555 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
154.98 | 39821 | Cus were required to repair a section of carriageway on Grosvenor St | 7677.277 | 7677.277 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
154.99 | 39800 | Follow up from CVI 154.94, Cus were required to temporary backfill the above diversions | 2484 | 2484 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.1 | 39829 | Cus were required to remove the following dimensions of concrete | 367 | 367 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.101 | 39827 | Due to an old Scottish Water hydrent being damaged when breaking out the tarr cus had to wait on S/W coming out to repair the damage. | 579 | 579 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW | 100
154.102 | 39829 | Hand digging around existing utilities | 54 | 54 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.103 | 39825 | due to working space Cus had to transport materials from the diversion to the main site to be up-lifted | 452 | 452 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.104 | 39827 | Cus were required to excavate to allow Verizon to build | 1671 | 1671 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Ver
154.105 | 39836 | Cus were required to hand dig around existing services | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.106 | 39832 | Due to the site location Cus were required to double handle materials | 321 | 321 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.107 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.108 | 39836 | Cus were required to remove the following dimentions of extra over Tarr | 81 | 81 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.109 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.11 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.111 | 39825 | Tie instructed Cus to have a general tidy of the site, however the mess was created by Verizon and SGN operatives | 66.999 | 66.999 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Ver & SGN
154.112 | 39838 | Cus were required to hand dig arround exsicting services | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.113 | 39832 | Cus were required to carry out works for Verizon on the instruction of tie | 2380 | 2380 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Ver
154.114 | 39793 | Cus were required to carry out temporary road repairs on Roseberry Crescent | 1857 | 1857 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.115 | 39834 | Cus were delayed due to uncovering an old sewer and were waiting an instruction from tie. | 383 | 383 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.116 | 39839 | Cus were required to remove the following dimentions of concrete | 4061.6661 | 4061.6661 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.117 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.118 | 39842 | Cus were requiresd to hand dig aroung existing services to allow the above diversions | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.119 | 39836 | Double handling materials | 428 | 428 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.12 | 39848 | Cus were required to double handle materials at the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
154.121 | 39847 | Whilst excavating for the above diversion Cus uncovered a large abount of concrete around SGN Gas service, Cus were required to call SGN out to inspect this. | 331 | 331 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN | 100
154.122 | 39848 | Cus were required to remove the following dimentions of concrete | 3512.1466 | 3512.1466 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN | 100
154.123 | 39850 | Cus were required to remove the following dimentions of concrete | 1588 | 1588 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN | 100
154.124 | 39850 | Cus were required to remove the following dimentions of concrete | 2177.5991 | 2177.5991 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN | 100
154.125 | 39790 | Cus were required to dismantle and rebuild the above Scottish water meters as per Tie change order | 2110 | 2110 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.126 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.127 | 39840 | Due to the delay from Tie in answering TQ1169 Cus were delayed and unproductive during this period | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
154.128 | 39854 | Cus were required to remove the following dimentions of Concrete | 787 | 787 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.129 |  | Requirement to cut, drain and remove section of 355mm PE water main. | 8559.177 | 4492 | -4067.177 | -47.52% | Utility Abandonment |  |  | 3rd | [6 empty] | SW
154.13 | 39857 | Cus were required to remove and replace couplers with Flex lock couplers on the above SW meter | 1470 | 1470 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.131 | 39850 | Cus were required to transport excavated material from the above diversion to the main site to be up-lifted | 204 | 204 | 0 | 0% | Agreed |  |  | 3rd <£2k
154.132 | 39847 | Cus were required to hand dig around existing services | 0 |  | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | Gen
154.133 | 39847 | Cus are required to transport backfill material from the main site | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.134 | 39804 | Cus were required to construct a new 300mm DI water Meter | 9400 | 9400 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
154.135 | 39856 | Cus were required to construct a new 200mm Water Meter | 4721 | 4721 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.136 | 39868 | Cus were required to excavate 4nr trial holes in order to find a route for the diversion along Manor Place | 1511 | 1511 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.137 | 39860 | Hand digging around existing services | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | SW
154.138 | 39858 | Weekend working | 4427.9555 | 922 | -3505.9555 | -79.18% | NPO |  |  | 3rd | [6 empty] | SW
154.139 | 39868 | Cus were required to remove the following dimentions of Concrete | 163 | 163 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.14 | 39785 | Cus were required to demolish an existing BT box as per Tie instruction 3497 | 1877 | 1877 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.141 | 39863 | Cus were required to remove the following dimentions of Concrete | 6655.6714 | 6655.6714 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | BT
154.142 | 39867 | Cus were required to construct a concrete support for an old tram structure | 1861 | 1861 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.143 | 39863 | Cus were required to demolish an existing verizon chamber | 406 | 406 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Ver
154.144 | 39868 | Due to existing services Cus were required to hand dig to allow the above diversions can take place | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT
154.145 | 39871 | Cus ere required to install a footway signal chamber as per Tie instruction | 893 | 893 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
154.146 | 39876 | Cus were required to remove a large amount of old Cast Iron water main to allow to tie in on the above diversions | 162 | 162 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.147 | 39876 | Hand digging under existing services | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.148 | 39864 | Cus were required to excavate down onto the SW main to prove that it had not "mounted" after reinstating | 377 | 377 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.149 | 39869 | Cus were required to remove the following dimentions of concrete | 1815 | 1815 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.15 | 39871 | Cus were required to move the following dimention of concrete | 815 | 815 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.151 | 39874 | Cus were requested to reinstate 2nr Trial holes for SGN | 2650.2265 | 2650.2265 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN | 100
154.152 | 39871 | Cus were required to remove the following dimentions on Artificial obstruction | 1770 | 1770 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.153 | 39860 | Cus are required to double handle all backfill material at the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
154.154 | 39875 | Cus were required to hand dig around existing services to allow the above diversion | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k
154.155 | 39875 | Cus were required to remove the following dimentions of concrete | 832 | 832 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.156 | 39877 | Hand digging around existing services | -260.0196 | -260.0196 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.157 | 39878 | Cus were required to remove concrete to allow for the above diversion | 3481.4281 | 3481.4281 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.158 | 39878 | Extra aver Tarr | 331 | 331 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.159 | 39877 | Cus were unable to get the required depth for the above diversion due to an existion BT duct. Cus were requested to protect the PE water main with DI ducts | 1388 | 1388 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.16 | 39878 | Cus were required to have the power to the bus stop on Clifton Terrace disconected. | 995 | 995 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.161 | 39874 | Double handling materials | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.162 | 39867 | Double handling materials | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.163 | 39882 | cus were required to backfill the tie-in points with concrete due to the lack of depth. | 1511 | 1511 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.164 | 39867 | Cus were required to hand dig around existing services to allow for the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW
154.165 | 39895 | Cus were required to remove the following dimentions of reinforced concrete to allow the mentioned diversions | 3924.2158 | 3924.2158 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.166 | 39895 | Removel of artificial obstruction to allow for the mentioned diversion | 815 | 815 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.167 | 39888 | Cus were required to hand dig along West Maitland St to clear a route for the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | SW
154.168 | 39888 | To allow for the above diversions cus were required to break out the existing CI Gas main | 1365 | 1365 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.169 | 39853 | Cus were required to remove and reinstate 2nr Traffic islands on Dalry Rd | 8192.6966 | 8192.6966 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | Gen
154.17 | 39897 | Due to Cus being unable to get the required depth for the mentioned diversion on Manor pl cus were required to backfill with Concrete | 413 | 413 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.171 | 39897 | To allow for the pedestrian access to me moved cus were required temp backfill part of the excavation under the road plates | 539 | 539 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.172 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.173 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.174 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.175 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.176 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.177 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.178 |  | Cus were requested by Tie to reconnect a 225mm Gully tail, Whilst excavating it was brought to the attention that the gully tail was redundant. | 2554.3035 | 2554.3035 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.179 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.18 |  | Due to SGN drilling and breaking newly laid Verizon ducts, Cus were required to excavate and re-lay 15m of duct | 1091.4816 | 1091.4816 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN 100
154.181 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.182 |  | Hand digging along West Maitland Street | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
154.183 |  | Cus were required to hire a grab wagon to up-lift a large amount of old CI Gas main | 163.4663 | 163.4663 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
154.184 |  | Cus were required to safely support an existing fire hydrent in order to hand excavating around to allow for the above diversion | 105 | 105 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
154.185 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.186 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.187 |  | Cus were required to use C20 concrete as appose to Type 1 along Clifton Terrace to get the required compaction | 297.8482 | 297.8482 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
154.188 |  | Due to the re-alignment of the DKE this caused a delay in ordering materials of the SP diversion 22 as this was changed to the south side of clifton terrace | 517.2212 | 517.2212 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
154.189 |  |  | 0 | 0 | 0 | 0% | Agreed |  |  | AS |  |  | CUS reduce by £3584 JC/TL 11/03
154.19 |  | Cus were required to remove the following dimentions of concrete to allow for the above diversion | 3583.823 | 3583.823 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.191 |  | to allow for the above diversion cus were required to lay 100mm of c20 concrete over an existing BT to allow the water main to be laid ubove the BT duct. | 3675.3402 | 3675.3402 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.192 |  | Cus were required to expose a leak on an existing S/W main | 5388.4556 | 5388.4556 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
154.193 |  | Cus were required to remove spoil from SGN excavations. | 450.3345 | 450.3345 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
154.194 |  | Cus were required to re-sand a section of the 180mm Gas main due the Scottish water service leak. | 1496.8436 | 1496.8436 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
154.195 |  | Carillion were required to backfill with C20 concrete in order to get the required compaction. | 345.3965 | 345.3965 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
154.196 |  | As a result of traffic management restrictions Carillion were required to double handle materials due to space constraints | 533 | 533 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
154.197 |  | Carillion were required to remove old cast mains to allow for the above diversion | 116.5811 | 116.5811 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
154.198 |  | Additional Reinstatement | 220.0785 | 220.0785 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
154.199 |  | Additional chamber to house water meter & additional 6m duct route to carry water telemetry cable to o/s Ryres Bar | 220.0785 | 220.0785 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.2 |  | Removel of artificial obstruction | 2082.0305 | 2082.0305 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
154.201 |  | Build a bend configuration on Coats Place to allow SP to inspect | 144.247 | 144.247 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.202 |  | Carillion were required to hand dig under existing utilities in order to take Gas services across West Maitland Street | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | SGN
154.203 |  | Carillion were required ti install a signal chamber | 1140 | 1140 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
154.204 |  | In order to lay the above diversions Cus were required to hand excavate under existing utilites | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SP
154.205 |  | to allow cus to lay above diversion under existing utilites Cus were required to hand dig | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SP
154.206 |  | Carillion were required to hand excavate along West Maitland Street. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
154.207 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.208 |  | Due to space constraints along Coats Place Carilion were require to remove duct which were laid under instruction form Tie. | 7969 | 7969 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
154.209 |  | Carillion were required to remove concrete from the above diversion | 2832.9268 | 2832.9268 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.21 |  | Hand digging | 0 |  | 0 | 0% | Agreed(*) |  |  | new |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | Gen
154.211 |  | Carillion were required to remove the following dimentions of concrete to allow the above diversion | 1279.9368 | 1279.9368 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.212 |  | Removel of concrete | 1418.17 | 1418.17 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.213 |  | Abandond Trial Holes | 815.6 | 815.6 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.214 |  | Hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | Gen
154.215 |  | Making safe underground tunnel at Grosvenor Street | 2535.36 | 2535.36 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.216 |  | Carillion were required to hire Crown Engineering to remove old steel beams. | 1280.576 | 1280.576 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.217 |  | Removel of Concrete | 2685.07 | 2685.07 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.218 |  | Removel of Concrete | 945.45 | 945.45 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.219 |  | Due to Tie change order 3635 cus were delayed due to the time taken to order the new fittings | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
154.22 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.221 |  | Use of CUS to close of temporary access to Network Rail | 142.4262 | 142.4262 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.222 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.223 |  | Repairs to existing VM chamber on FW at West Maitland. | 342.4763 | 342.4763 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.224 |  | Carillion were required to use 2 x labouers to tidy site from public litter, as requested by Tie | 193 | 193 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.225 |  | hand digging under existing utilites to allow the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | VM
154.226 |  | As requested by Tie and SW carillion were instructed to excavate and expose a SW diversion for inspection and backfill | 1082.065 | 1082.065 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.227 |  | Carillion were required to remove the following dimensions of artificial obstruction | 931.794 | 931.794 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.228 |  | Due to the shallow existion 1D/VM/D/18 Cus were required to use concrete | 304.8129 | 304.8129 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.229 |  | Due to existing utilites at Palmerston Pl Cus have have to use 1m3 to get the required compaction | 100.8455 | 100.8455 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.23 |  | Fujitsu have requested Cus to use 11.25 deg bends ioin the 10 way BT/D/37. | 199.3651 | 199.3651 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.231 |  | Cus were required to install a 150mm SV as Scottish Water could not get a shut off on the existing 6"main | 464.304 | 464.304 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.232 |  | Cus were required to lay 4m3 of C20 concrete to gain the required compaction along west maitland street. | 172.0642 | 172.0642 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.233 |  | Carillion were required to remove a section on 500mm LP Gas main as requested by Tie | 1273 | 1273 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.234 |  | Cus were required to remove the following dimentions of concrete | 3379.0332 | 3379.0332 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.235 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.236 |  | Carillion were required to use 4m3 of C20 concrete to backfill newly laid surface water drainage pipe | 307.1206 | 307.1206 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.237 |  | Carillion were instructed by Tie to carry out a survey of the undergroung tunnel at Grosvenor Street. | 3502 | 3502 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.238 |  | Carillion were instructed to move the position to the above diversion tie in point, as a result CUS were required to backfill the excavation which was previously excavated | 844 | 844 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.239 |  | Carillion were required to remove the following dimentions of artificial obstruction to allow the above diversion | 174.0714 | 174.0714 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.24 |  | Carillion were required to remove the following dimention of artificial obstruction to allow the above diversion | 136.5266 | 136.5266 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.241 |  | Whilst excavating for the above diversion carillion were required to hand excavate through solid rock as it was not possible to possision an excavator at the excavation | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | BT
154.242 |  | Abandon new mains due to underground structure - 100% complete | 10344.6387 | 10344.6387 | 0 | 0% | Exc Abandonment |  |  | new | [6 empty] | SW
154.243 |  | Abandoned trial holes | 1690.7357 | 1690.7357 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.244 |  | Carillion were required to provide 1nr labourer to carry oyt site tidy duities as a result of the council | 135.1296 | 135.1296 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.245 |  | Artificial obstructions | 1788.4984 | 1788.4984 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.246 |  | Carillion were required to use 0.5m³ of concrete to gain the required compaction | 68.4594 | 68.4594 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.247 |  | Carillion were required to hand excavate to allow the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
154.248 |  | Breaking away concrete from existing services | 753.6547 | 753.6547 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.249 |  | Carillion were required to use c20 concrete to allow the following diversions | 721.0546 | 721.0546 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.25 |  | To allow for SW and SP diversions CUS have been required to slew existing ducts along West Maitland Street and Haymarket Terrace | 3067.6622 |  | -3067.6622 | -100% | Slew Utilities |  |  | new | [6 empty] | SW & SP
154.251 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.252 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.253 |  | CUS have been required to backfill 2nr tracks to enable the delivery of a large industrial fridge. The excavations were required to be re-excavated | 1430 | 1430 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.254 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.255 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.256 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.257 |  | Slew 2 way Virgin media | 2009.3674 |  | -2009.3674 | -100% | Slew Utilities |  |  | new | [6 empty] | VM
154.258 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.259 |  | Carillion were instricted to carry out the tie in connection on the above diversion on the 27/07/09, but were advised on the date the we were unable to get the required water shut down for long enough to carry out the connection. | 273 | 273 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.26 |  | As instructed by tie, Carillion were instructed to provide a working platform for BT to carry out the construction of the manhole at Palmerston Pl | 2357 | 2357 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.261 |  | To locate the above diversion carillion were required to remove the following dimentions of artificial obstruction | 3631.6073 | 3631.6073 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.262 |  | Due to TM restrictions Carillion were instructed to stop work for 1hrs during 12.30 and 14.00 to ease traffic flow. | 44.7603 | 44.7603 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.263 |  | Carillion were required to remove the following dimentions of atrificial obstruction | 1006.8836 | 1006.8836 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.264 |  | Carillion were required to remove the following dimentions of atrificial obstruction | 4778.4307 | 4778.4307 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.265 |  | Due to design change carillion were required to abandon part of the excavation for BT diversion | 1959.6327 | 1959.6327 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.266 |  | Carillion were instructed bt tie to make safe an area left un-safe bt Contractor | 248 | 248 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.267 |  | Carrilion were required to divers weter around an excavation to stop further flooding due to heavy rain as requested by tie | 5476.5638 | 5476.5638 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.268 |  | Carillion were required to remove the following dimentions of artificial obstruction | 6901.4192 | 6901.4192 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.269 |  | As instracted by Tie carillion were required to remove the War memorial island at haymarket | 4827 | 4827 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
154.27 |  | Assessed Elsewhere (see Master Change Register) | 0 |  | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05
154.271 |  | Whilst excavating for the joint bays at the above diversion carillion were required to remove the followig dimentions of extra over Tarr | 58.0238 | 58.0238 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.272 |  | Carillion were required to excavate around a scottish water leak to carry out a repair | 288 | 288 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.273 |  | Carillion were required to hand excavate to allow the above diversion | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.274 |  | As per instruction 5268 Carillion were instructed to carry out a trial hole to locate the cellars along West Maitland Street | 5476.5638 | 5476.5638 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
154.275 |  | As per Tie instruction 3764 Carillion were required to demolish an existing Cable and Wireless chamber | 828 | 828 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | CW
154.276 |  | As requested by Tie (Russell Maxwell) Carillion have been required to provide 1nr labourer to carry out litter picking duties | 157.6512 | 157.6512 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.277 |  | Carillion were required to re-locate the site (Cabins, materials, Pipe and fittings ect) to allow SGN access to Clifton Terrace to carry out there Gas works. | 5058 | 5058 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
154.278 |  | Tie had requested Carillion to provide labour to assist SGn with a Gas leak at Haymarket Bar area. | 532 | 532 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN 100
154.279 |  | CUS have been required to excavate and reinstate area at Palmerston Place due to BT failure to reinstate to Spec | 2085 | 2085 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT 100
154.28 |  | Additional Excavation to enable 'others' to install Verizon Box. Additional Slewing existing 4way BT | 4505.6827 | 981 | -3524.6827 | -78.23% | Slew Utilities |  |  | new | [6 empty] | VM
154.281 |  | Resources required to assist SGN to excavate and repair existing main | 877 | 877 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN 100
154.282 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.283 |  | CUS have been required to reduce a buried sewer shaft to enable route for 1D/LP/D/101C | 350 | 350 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.284 |  | Remove and Replace Gully Pots | 171 | 171 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.285 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.286 |  | CUS required to use a 3m 450mm Double Flanged Spool Piece | 836 | 836 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.287 |  | Structure encountered requiring investigation and breakout of structure at Torphichen Street. | 3060 | 3060 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.288 |  | Abandoned service crossings at West Maitland Street due to uncharted cellars. In addition concerete obstructions where located in each service crossing. Only 12 nr crossings paid in 1D-01-01 measure | 15761.3952 | 6429 | -9332.3952 | -59.21% | Other (WS) |  |  | new | [6 empty] | SW
154.289 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.29 |  | CUS were required to drill and tap 4 no. existing 15" cast mains outside the Haymarket Bar in order to establish a route for the 500mm gas. | 203 | 203 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.291 |  | Excessive Hand digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | SGN
154.292 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.293 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.294 |  | Temporary backfill to allow for Fujitzu access on Palmerston Place | 429 | 429 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.295 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.296 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.297 |  | Excavate and replace existing coroded water main at Palmerston Place | 454.1832 | 454.1832 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
154.298 |  | Litter picking week commencing 24/08/09 | 57 | 57 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.299 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
154.3 |  | existing energist box required to be cleaned by means of gully sucker. | 121.0866 | 121.0866 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Energ | 100
154.301 |  | Demolish existing CW chamber at Haymarket Bar | 1007 | 1007 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | CW
154.302 |  | Removal of artificial obstruction at Athol Place | 1601.4569 | 1601.4569 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.303 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.304 |  | Trial Hole outside Haymarket Bar next to structure to locate possible route for HV cables. | 2159.2187 | 2159.2187 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.305 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.306 |  | Supply and maintain site at Clifton Terrace on behalf od SGN for 6 weeks and 4 days. | 4558 | 4558 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN 100
154.307 |  | Additional reinstatement works on behalf of SGN outside Haymarket Bar. | 997.1691 | 997.1691 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.308 |  | CUS have been required to rebuild drainage chamber outside Haymarket Bar, As per Change Order 5421 and 5420. | 1492 | 1492 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.309 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.31 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.311 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.312 |  | Excavate Back On Virgin Media | 362 | 362 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.313 |  | Labourer to assist traffic around flatbed | 5 | 5 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.134 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.315 |  | CUS are required to demoish existing JRC2 Cable and Wireless Box at Torphichen Street | 1753 | 1753 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.316 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.317 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.318 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.319 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.32 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.321 |  | Removal of Artificial Obstruction | 4792.0834 | 4792.0834 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.322 |  | Hand digging and tunneling at Torphichen Street for Multi Utility Track | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
154.323 |  | Removal of Concrete | 1426.7029 | 1426.7029 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.324 |  | Litter Picking Monday 14th - Sunday 20th September 2009 | 77 | 77 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.325 |  | Breaking Out Concrete for 4-way Verizon and 2-way Energis (Opposite Haymarket Bar next to Underground Structure). Additional Reinforeced Concrete Protection Required. | 1087 | 1087 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Ver
154.326 |  | Length of 560mm EF water required to be cut in half due to congestion of exisiting services. Additional coupler required. | 863.8221 | 863.8221 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.327 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.328 |  | Additional trial holes required to determine service connections at West Maitland Street | 1313.9336 | 1313.9336 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.329 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.33 |  | Structure encountered requiring breakout and remedial works to brick up and backfill structure with Concrete. At West Maitland Street / Grosvenor Street Junction | 8239 | 8239 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
154.331 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.332 |  | Additional works to 4-way VM and rebuild exisiting MH | 1909.9107 | 1909.9107 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.333 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.334 |  | Removal of Artificial Obstructions when excavating for 1D/LP/D/112 opposite Haymarket Bar | 10167.8179 | 10167.8179 | 0 | 0% | Artificial Obstruction |  |  | new | [6 empty] | SGN
154.335 |  | Removal of Artificial Obstructions when excavating for 1D/SP/D/18 at Torphichen Street | 546.1064 | 546.1064 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.336 |  | Removal of Artificial Obstructions when excavating for 1D/CW/D/10 at Torphichen Street | 1911.3723 | 1911.3723 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | CW
154.337 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.338 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.339 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.34 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.341 |  | Artificial Obstruction whilst excavating for additional gas instructed in Change Order 5428 | 3219.0833 | 3219.0833 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.342 |  | Specialist reinstatement of underground structure at Haymarket Bar | 6105 | 6105 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
154.343 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.344 |  | Resources required to undertake remedial works to Energis Ducts Clifton Terrace | 1422 | 1422 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.345 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.346 |  | Litter Picking | 116 | 116 | 0 | 0% | Agreed | [5 empty] | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.347 |  | Removal of 2nr Gully Pots | 77 | 77 | 0 | 0% | Agreed | [5 empty] | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.348 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.349 |  | CUS where required to install plywood sheets to cover exposed cellars | 309 | 309 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.35 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.351 |  | CUS where required to re-excavate 2 no. previously laid 90mm service crossings and install 125mm sleeves around pipe. | 3719.5935 | 3719.5935 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.352 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.353 |  | Runner to pick-up additional ducts and return to site | 42 | 42 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.354 |  | AJ Jointing for 33kv joint on 1D/SP/D/15 & 16. Terminate 33kv | 3329.28 | 3329.28 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.355 |  | CUS are required to procure a steel spool piece to connect the 500mm PE mains at Haymarket Junction (Grosvenor Street) | 568 | 568 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.356 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.357 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.358 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.359 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.361 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.362 |  | CUS to provide a 3 man team to test 8 way BT ducts | 303 | 303 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.363 |  | Assessed Elsewhere (see Master Change Register) | 0 |  | 0 | 0% | Agreed(*)
154.364 |  | Due to onsite constraints and the requirement for a SW/19 tie to be undertaken prior to completion of other diversion works, CUS have been required to temporary backfill to enable continuation of works. (Torphichen Street.) | 1184 | 1184 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.365 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.366 |  | Demolish existing VM box at Torphichen Street | 895 | 895 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
154.367 |  | CUS require 2m3 EO foam concrete to fill void under 500mm gas main. | 100.1613 | 100.1613 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.368 |  | Supply of additional comms ducting materials | 330.3168 | 330.3168 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
154.369 |  | CUS are to fabricate a specialist flange adaptor for the existing 20" water connection at Dalry. | 772.48 | 772.48 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.37 |  | Protection works required to cover excavation to remain open over the embargo period | 1671 | 1671 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.371 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.372 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.373 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.374 |  | Additional resources to remove and relay cables on 1D/SP/D/15 | 367.6352 | 367.6352 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
154.375 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.376 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.377 |  | Whist excavating for the additional 125mm Gas diversion at Palmerston Place, CUS were required to break through excessive amounts of concrete. | 4846.694 | 4846.694 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
154.378 |  | CUS required 10m3 Foam concrete for Scottish Water diversion due to existing services | 500.8064 | 500.8064 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
154.379 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.38 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.381 |  | nil (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
154.383 |  | Supply of shoring materials post CUS completion on Haymarket site to maintain safety until inception by Clancy Docwra. | 2767.4912 | 2767.4912 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.384 |  | CUS to temporary backfill the Carriageway next to the cellars to make safe for the public. | 1620.3145 | 1620.3145 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
154.385 |  | required materials to protect existing services at Torphichen Junction. | 1328.0563 | 1328.0563 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 219044.0825 | 179219.8144
0
CR 156 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
156.02 | 39575 | Downtime in building manhole due to investigation in to proximity of IP Gas main. | 439 | 439 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
156.03 | 39587 | Removal an re-laying of 450mm diameter water main. | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
156.04 | 39577 | Removal & repositioning of 1 x street light column & 1 x traffic light column. | 122.32 | 122.32 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.05 |  | Remove trees at south end of Gyle car park | 571.2 | 571.2 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
156.06 | 39570 | Slewing existing 20way into new MRX405B. | 3184.1626 | 3184.1626 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
156.07 | 39570 | Slewing existing conflict - 5C/TE/01 into new Virgin Media chambers. | 371.5275 | 371.5275 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
156.08 | 39608 | Instruction to install a vehichle restraint barrier that will protect both the workforce and public during construction of BT manhole. Duration approx 6 weeks. | 6249.6562 | 6249.6562 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
156.09 | 39609 | Downtime on cable pulling due to Traffic Management only being permitted off-peak. | 1156 | 1156 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
156.10 | 39601 | Downtime due to Traffic Management only being permitted off-peak. | 1105 | 1105 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.11 | 39595 | Downtime incurred awaiting approval of a Traffic Management safety zone. | 405 | 405 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.12 | 39624 | Temporarily backfilling joint bays. | 3752.324 | 3752.324 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
156.13 |  | Jointing pilot cables | 8105.6 | 8105.6 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SP
156.14 | 39616 | Downtime due to Traffic Management only being permitted during off-peak hours. | 522 | 522 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.15 | 39570 | Abandoned Trial Holes. | 1334 | 1334 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.16 | 39577 | Locate existing IP Gas main to ensure it would not be comprimised by 5C/BT/D/06 or MH/5C/06/03. | 711.5607 | 711.5607 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
156.17 | 39606 | Hire of a RD Anderson flatbed to deliver Scottish power cables to site | 1225 | 1225 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
156.18 | 39632 | Abandoned Trial Holes. | 1215 | 1215 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.20 | 39568 | Abandoned Trial Holes. | 299 | 299 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.22 | 39616 | Removal of trees to progress works. | 510 | 510 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.23 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.24 | 39641 | Nightworks to carry out water connections at Lochside Cresent. | 3551.9808 | 3551.9808 | 0 | 0% | NPO |  |  | 3rd | [6 empty] | SW | 100
156.25 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.26 |  | Trials holes to identify whether ductline is Easynet, as requested by tie Change Order 3453 | 216.0298 | 216.0298 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Easynet
156.27 | 39633 | Additional excavation for working room around BT/MH/5C/06/01. | 1427.7073 | 1427.7073 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
156.28 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.29 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.3 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.31 |  | All Disrupted Plant Relating to 5C-01-01 | 2433.4413 | 2433.4413 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | Agreed JC/JC 23/04 email |  |  |  | Gen
156.32 |  | Weekend Working as per Record Sheet 23487 | 1040.3891 | 0 | -1040.3891 | -100% | NPO |  |  | new | [6 empty] | Gen
156.33 | 39657 | Removal of 2 x No Entry Bollards/Signs | 728.0678 | 728.0678 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.34 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.35 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.36 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.37 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.38 | 39676 | Supervison of Street Lighting Removal | 218.4975 | 218.4975 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.39 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.4 | 39669 | Weekend working to slew 2 way Thus and 3 way cable and wireless | 3616.9472 | 0 | -3616.9472 | -100% | NPO |  |  | 3rd | [6 empty] | THUS & C&W
156.41 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.42 | 39697 | Additional bends to achieve the required depth | 1710 | 1710 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
156.43 | 39683 | Resources for Weekend works Sat & Sun | 5084.4416 | 0 | -5084.4416 | -100% | NPO |  |  | 3rd | [6 empty] | Gen
156.44 |  | 0 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.45 |  | 0 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.46 | 39727 | Removal of Thrust Blocks | 4838.18 | 4838.18 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
156.47 | 39717 | Spreading of BT ducts to reach required depth under the DKE | 5916.81 | 5916.81 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | BT
156.48 |  | 0 | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.49 | 39732 | Acceptance of Quote for street lighting works at Gyle Car Park. | 3247.68 | 3247.68 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.5 | 39678 | Remove 5 No. existing street lighting columns, provide temporary lighting | 45000 | 45000 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
156.51 | 39766 | Additional works due to revised 24way, as per Change Order 3489. | 10609.1424 | 10609.1424 | 0 | 0% | Other (WS) |  |  | 3rd >£10k | [6 empty] | BT
156.52 | 39772 | Demolishing of additional chamber to facilitate diversion 5C/BT/D/06. | 732 | 732 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
156.54 | 39771 | Disconnections, remove existing enclosure, supply cable and 2 No. steel enclosures, re-connect test and certify. | 5332.5274 | 5332.5274 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
156.55 | 39805 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
156.56 | 39818 | Excavating for re-instatement of Street Lights at Lochside & backfill with foam concrete. | 515.7687 | 515.7687 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
156.57 | 39791 | Increased shaft size on BT/MH/5C/06/01 | 2895.9716 | 2895.9716 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
156.58 | 39800 | Neccessity to slew or re-lay existing utilities to provide route for BT 24way at South Gyle Broadway. | 13974.272 | 13974.272 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | BT
156.59 | 39842 | Trial Holes to prove pea-gravel as per tie Change Order 3552. | 1087 | 1087 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
156.6 | 39834 | Re-excavate and reinstate joint pits a as recorded on CVI 02236 | 12213.3661 | 12213.3661 | 0 | 0% | Agreed |  |  | top 68 |  |  | TL noted 30/04 agreed top 68 |  |  |  | SP
156.61 | 39793 | Additional Temporary works required due to water tie-in point being located 4 metres deep within embankment. | 7083.15 | 7083.15 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
156.62 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.63 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
156.64 | WE 09/05/2008 | Downtime due to Traffic Management along South Gyle Broadway only being permitted Off Peak. |  |  | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
156.65 | 39833 | Removal & Re-erecting No Entry Sign to provide working room around diversion 5C/SP/D/03. | 93 | 93 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
156.66 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen |  | 67148.8061 | 61023.9754
156.67 |  | Extra Over Fence & Hedge Reinstatement at South Gyle Centre. | 12640.9806 | 12640.9806 | 0 | 0% | Other (WS) |  |  | new | [6 empty] | BT & SW
156.68 |  | Additional Fire Hydrant. | 641.6806 | 641.6806 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
[5 empty] | 0 | 0% | [9 empty] | 0 | Gen
CR 160 | [6 empty] | Agreed(*) | [9 empty] | Gen
160.1 | 39609 | Drill main & remove redundant cast from site | 1800 | 1800 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 2787.6502 | 987.6502 | SW
160.2 | 39608 | Demolish chamber | 1041 | 1041 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.3 | 39610 | To construct BT diversion 32 as Orientation changed | 1400 | 1400 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 2457.2575 | 1057.2575 | BT
160.4 |  | Logistic support for Elm Row | 212718.5906 | 176678 | -36040.5906 | -16.94% | Logistic Support |  |  | 3rd >£10k | [6 empty] | Gen
160.5 | 39602 | Removal of 6" and 10" cast iron. | 283 | 283 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.6 | 39601 | Removal of 6" and 10" cast iron. | 898 | 898 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.7 | 39609 | Removal of Artificial Obstructions | 338 | 338 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.8 | 39611 | Abandoned Trial Holes and artificial Obstructions | 507 | 507 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.9 | 39601 | Removal of Artificial Obstructions (concrete) | 5500 | 5500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 6058.3675 | 558.3675 | Gen
160.10 | 39610 | Removal of 6" and 10" cast iron. | 748 | 748 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.11 | 39601 | Removal of Artificial Obstructions | 1461 | 1461 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.12 | 39618 | Removal of Artificial Obstructions (concrete) | 3303.9435 | 3303.9435 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.13 |  | No cost implications | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.14 | 39629 | Abandoned Trial Holes | 1303 | 1303 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.15 | 39630 | Removal of artificial obstructions (old tram foundation) | 1115.95 | 1115.95 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2220.8139 | 1104.8639 | Gen
160.16 | 39625 | Delay due to Flooding Manhole | 1990 | 1990 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.17 | 39625 | Pumping of flooded manhole | 276 | 276 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.18 |  | No cost Implications | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.19 | 39639 | Diversion of water main around proposed services | 925 | 925 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.2 | 39636 | Removal of Artificial Obstructions (Concrete) | 6401.9142 | 6401.9142 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.21 |  | Removal Cast Iron | 947 | 947 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.22 |  | Removal of Artificial Obstructions (Concrete) | 1903 | 1903 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.23 | 39639 | Demolish Chamber | 952 | 952 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
160.24 | 39640 | Removal of Artificial Obstructions (Concrete) | 5668.0392 | 5668.0392 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.25 | 39637 | Pumping Flooding of Manhole | 226 | 226 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
160.26 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.27 | 39651 | Abandoned trial hole to locate existing bt ducts for new diversion 1C/BT/D/25b | 434 | 434 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
160.28 | 39651 | Removal of Steel beams and concrete from diversions | 3785.1648 | 3785.1648 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.29 | 39651 | Removal of concrete and hand digging around uncharted services | 1843 | 1843 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 0 | -1843 | Gen
160.3 | 39653 | Removal of Concrete and steel beams | 858 | 858 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.31 |  | Disrupted Plant | 33580.2399 | 7269 | -26311.2399 | -78.35% | Disrupted Plant |  |  | 3rd | [6 empty] | Gen
160.32 | 39651 | Temporary BT Manhole Shaft | 252 | 252 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
160.33 | 39657 | Concrete and steel beams removed from diversions | 26811.0361 | 26811.0361 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.34 |  | Superseded | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.35 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.36 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.37 | 39658 | Abandoned Trial Holes | 370 | 370 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.38 | 39679 | Removal of Artificial Obstructions (Concrete) | 241 | 241 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.39 | 39678 | Removal of Artificial Obstructions comprising of Concrete and Steel | 1842 | 1842 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.4 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.41 | 39609 | Drilling of unidentified pipes | 502.5227 | 502.5227 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.42 | 39609 | Removal of scrap (cast iron pipes) | 216 | 216 | 0 | 0% | Agreed |  |  | 3rd <£2k
160.43 | 39687 | Hand digging around chartered and unchartered services |  |  | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.44 | 39694 | Artificial Obstructions (concrete) | 929 | 929 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.45 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.46 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.47 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.48 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.49 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.5 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.51 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.52 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.53 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.54 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.55 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.56 | 39744 | Artificial obstructions (cast iron) | 7565.95 | 7565.95 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
160.57 | 39769 | Additional Reinstatement | 0 | 0 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
160.58 | 39743 | Removal of Artificial Obstructions (Concrete) | 677 | 677 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.59 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.6 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.61 | 39748 | Artificial Obstructions (Excess Carriageway and Concrete) | 5570.285 | 5570.285 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.62 | 39741 | Abandoned Trial Holes | 3466.6343 | 3466.6343 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.63 | 39741 | Abandoned Trial Holes - Picardy Place | 5667.513 | 5667.513 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.64 | 39756 | Removal of Artificial Obstructions (Concrete) | 1315 | 1315 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.65 | 39751 | Hand Digging around existing services |  |  | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.66 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.67 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.68 | 39727 | Hand Digging around existing services |  |  | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
160.69 | 39755 | Delay And Disruption | 306 | 306 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.7 | 39757 | Additional Works | 1958 | 1958 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 1194 | -764 | Gen
160.71 | 39756 | Hand Digging around existing services |  |  | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.72 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.73 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.74 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.75 | 39748 | Removal of artificial obstructions (9'' Cast iron pipe) | 822 | 822 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.76 | 39763 | Demolishing Existing BT Chambers | 1928 | 1928 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
160.77 | 39764 | Abandoned trial hole | 1258 | 1258 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
160.78 | 39757 | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
160.79 | 39770 | Delay and disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
160.8 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.81 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.82 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.83 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.84 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.85 | 39778 | Additional Works | 610 | 610 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.86 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.87 | 39778 | Additional works | 592.6249 | 592.6249 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.88 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.89 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.9 | 39770 | Additional works | 1332.77 | 1332.77 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
160.91 | 39794 | Demolish of BT box at Gayfield Square | 2000 | 2000 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 1500 | -500 | BT
160.92 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.93 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.94 | 39833 | Demolition of BT Box | 3000 | 3000 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 2200 | -800 | BT
160.95 | 39837 | Non Productive Overtime | 2000 | 2000 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC Agreed 04/05 |  | 1500 | -500 | Gen
160.96 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.97 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.98 |  | Due to the indecision by BT cus were delayed regarding bends over the leith tunnel | 2243.515 | 2243.515 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT | 100
160.99 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.1 |  | Compact undermining in 1C/SW/D/02. | 2243.7065 | 2243.7065 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
160.101 |  | Re-excavation & works associated with reducing sewer shaft in route of 1C/SW/D/02. | 8658.3185 | 8658.3185 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
160.102 |  | Re-excavation of 400mm & 180mm Scottish Water mains due to TM phasing. | 1616.83 | 1616.83 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW | 100
160.103 |  | Hand- Digging around unchartered service connections & additional reinstatement due to poor existing road surface. | 1106 | 1106 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.104 |  | Provide Gatesman for site access. | 795.872 | 795.872 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.105 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.106 |  | Additional 2nr. 180mm SW Couplers due to unchartered sewer shaft. | 266 | 266 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
160.107 |  | Artificial Obstruction | 6977.3963 | 6977.3963 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.108 |  | Artificial Obstruction | 2581.0694 | 2581.0694 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.109 |  | Artificial Obstruction | 3025.4293 | 3025.4293 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.11 |  | Hand Digging |  |  | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
160.111 |  | Additional excavation (abandoned) due to 500mm Gas (1C/LP/D/104) not able to be laid as per IFC. | 13125.2885 | 13125.2885 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
160.112 |  | Extra Over for supply connections | 7461.5325 | 7461.5325 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW | 100
160.113 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
160.114 |  | Removal & Reinstatement of gulley pots | 541.0733 | 541.0733 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
160.115 |  | Abandoned Trial Hole for Fire Hydrant. 1C/SW/D/02 | 1701.5734 | 1701.5734 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
160.116 |  | Artificial Obstruction | 1871.9844 | 1871.9844 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
160.117 |  | Artificial Obstructions & Additional Reinstatement | 3744.6413 | 3744.6413 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
160.118 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.119 |  | Ammendment to BT diversion 1C/BT/D/35. | 500 | 500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 0 | -500 | BT
160.12 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.121 |  | Removal of Historic Tram Rails | 299.0538 | 299.0538 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.122 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.123 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.124 |  | Altering Formation of 1C/SW/D/02 at request of Scottish Water. | 1024 | 1024 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1236.8806 | 212.8806 | SW | 100
160.125 |  | Removing Cast | 454.0426 | 454.0426 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.126 |  | Abandoned Trial Hole for Fire Hydrant | 220.8292 | 220.8292 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SW
160.127 |  | Wasted excavation in slip trench. | 500 | 500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1005.9996 | 505.9996 | SW
160.128 |  | Hand Digging for 6" water connection conflict 1C/SW/20. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SW
160.129 |  | Abandoned Trial Hole | 1030.5362 | 1030.5362 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SW
160.13 |  | Extra Over Bends on twin 180mm SW mains. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 807.8286 | 807.8286 | SW
160.131 |  | Foam Concrete to support existing cobbles | 1802.903 | 1802.903 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05; so long as not in measure |  |  |  | Gen
160.132 |  | Specialist Welded 22.5 deg bend / EQ tee as standard PE fitttings would not provide sufficient cover. | 3000 | 3000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2561.696 | -438.304 | SW
160.133 |  | Re-excavation of 400mm SW diversion to adjust previously agreed formation | 37358.8654 | 0 | -37358.8654 | -100% | Exc Abandonment |  |  | new | [6 empty] | SW | 100
160.134 |  | Stepping back off excavation to maintain safety due to inability to shore caused by proximity of existing SP tunnel. | 2000 | 2000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 0 | -2000 | SW
160.135 |  | Artificial Obstruction 1C/BT/D/26 & 1C/BT/D/27 | 1290.1763 | 1290.1763 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.136 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.137 |  | Artificial Obstruction within 1C/SP/D/03 | 518.801 | 518.801 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.138 |  | Artificial Obstruction 1C/TH/D/03B | 1165.7664 | 1165.7664 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Thus
160.139 |  | Widened 1C/SP/D/03 due to uncovering unchartered structure. | 1346 | 1346 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2256.8008 | 910.8008 | SP
160.14 |  | Hand Digging within 1C/SP/D/03 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.141 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.142 |  | Concrete & tram sleepers removed from 1C/SP/D/04 | 1800 | 1800 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 983.0993 | -816.9007 | SP
160.143 |  | Requirement to use 16 no. 160mm Slow Bends on 1C/SP/D/04. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 346.0009 | 346.0009 | SP
160.144 |  | Additional track width due to encroaching on Baxters Place underground toilets. | 1700 | 1700 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1612.0235 | -87.9765 | SP
160.145 |  | Concrete removed from 1C/VM/D/07 | 447.9779 | 447.9779 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 248.1797 | -199.7981 | VM
160.146 |  | Extra Over Bends to manouvre existing 30 inch SP tunnel - 1C/SW/D/03. | 3400 | 3400 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1999.7087 | -1400.2913 | SW
160.147 |  | Change Order to Demolish JUF10 and Build MRX402A Demolition of JRF110 to enable construction of MH. | 1708 | 1708 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1083.62 | -624.38 | BT
160.148 |  | Additional slewing of existing ducts to achieve adequate depth within new MRX402A. | 3335.4762 | 0 | -3335.4762 | -100% | Slew Utilities |  |  | new | [6 empty] | BT
160.149 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.15 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.151 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.152 |  | Overbreak of existing TAR & agreed use of Foam Concrete to fill voids caused by cobbles situated underneath existing Tarmac. Refer to CC190.143 for invoices. | 12000 | 12000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 0 | -12000 | Gen
160.153 |  | Additional Trial holes as requested to prove route for 6 way BT. | 1087.7064 | 1087.7064 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.154 |  | CUS to carry out additional cores to new MRX402B to facilitate shallow duct line. | 195.84 | 195.84 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.155 |  | Reduce additional 6 way BT 10metres & Re-lay to shallow re-cores to eliminate requirement for bends | 1506.44 | 1506.44 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2408.8644 | 902.4244 | BT
160.156 |  | Additional Slweing of 4 way thus & 4 way Scottish Telecoms to provide a route for the additional 6 way BT. | 9138.5798 | 9138.5798 | 0 | 0% | Slew Utilities |  |  | new | [6 empty] | BT | 100
160.157 |  | Slewing of existing 2 way Thus into 1C/TH/D/04. | 1693.0368 | 1693.0368 | 0 | 0% | Slew Utilities |  |  | new | [6 empty] | Thus
160.158 |  | Abandoned Trial Hole required to locate existing LV cables prior to laying 1C/SP/D/03 | 736.0973 | 736.0973 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.159 |  | Abandoned excavation as per TQ 1493 | 1182.3864 | 1182.3864 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.16 |  | Hand Digging due to uncharted cellars & existing services | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
160.161 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.162 |  | Delay to Gas Diversions at Leith Walk/London Road | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new |  |  | This is a D&D item agreed as nil in email TL/JC 22/03 |  |  |  | Gen
160.163 |  | Demolition of JUF12 chamber as per IFC - 1C/BT/D/18 | 2225.5 | 2225.5 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1405 | -820.5 | BT
160.164 |  | Extra Over excavation required to tie in centre section of BT diversions around London Road Roundabout. | 4549.0812 | 4549.0812 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.165 |  | Abandoned Trial Holes as conflicts 1C1/LP/104 & 1C1/LP/105 not as per IFC or PU drawings (CUS letter 2594) | 4174.0396 | 4174.0396 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP | 100
160.166 |  | Hand Digging 1C1/LP/D/103 | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SP
160.167 |  | Demolition of JUF12 as per IFC due to kerb re-alignment conflicting with conflict 1C/TH/04. | 1360.6007 | 1360.6007 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Thus
160.168 |  | Re-excavation of 1C/SW/D/02 & 03 due to culvert obstructing route prior to embargo. | 11000 | 11000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2500 | -8500 | SW
160.169 |  | Banksman required to maintain public safety. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.17 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.171 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.172 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.173 |  | 1C/BT/D/11 as per TQ 1536 - CUS cannot complete the diversion due to existing services. Trial Hole abandoned - revert back to IFC. | 704.4451 | 704.4451 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.174 |  | Excavation around, LV disconnection & removal of phone kiosk. | 937.14 | 937.14 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1035.7656 | 98.6256 | SP
160.175 |  | Unsuccessful Trial Holes to relocate gas diversion onto footpath. | 576.3642 | 576.3642 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SGN
160.176 |  | CUS where required to backfill the SW road crossing at Annandale St with no pipe. This occurred due concrete structure in route of water diversions & originally laid BT diversion reverting back to IFC. BT was mad prioroty (refer to photographs, CUS letter 2625 and tie Change Orders 3584, 3585 & 3781) | 2543 | 2543 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 3335.3859 | 792.3859 | SW | 100
160.177 |  | Additional slewing of existing 6 way BT into new JUF14C and Artificial Obstruction within excavtion. | 2942.4666 | 0 | -2942.4666 | -100% | Slew Utilities |  |  | new | [6 empty] | BT
160.178 |  | Abandoned 17 way BT and connection to existing due to instruction to revert back to IFC. | 4283 | 4283 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 3500 | -783 | BT
160.179 |  | Extra Over excavation in diversions to enable tie-in in next phase Traffic Management. | 2000 | 2000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 3853.7146 | 1853.7146 | BT
160.18 |  | Slewing & Support of existing 125mm PE gas from route of 400mm & 180mm SW diversions. | 1595.1114 | 0 | -1595.1114 | -100% | Slew Utilities |  |  | new | [6 empty] | SW
160.181 |  | Addititonal excavation to ascertain route & enable investigation by archaeologists. | 2430 | 2430 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2000 | -430 | Gen
160.182 |  | Artificial Obstructions at Annandale St. | 4244.8848 | 4244.8848 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 4020 | -224.8848 | Gen
160.183 |  | Artificial Obstructions within gas excavations at London Road. | 9071.5094 | 9071.5094 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 8000 | -1071.5094 | SGN
160.184 |  | Artificial Obstructions within BT diversions at London Road. | 9867.9714 | 9867.9714 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 8500 | -1367.9714 | BT
160.185 |  | Concrete within diversion 1C/VM/D/07 (phase 2). | 895.6144 | 895.6144 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | VM
160.186 |  | Artificial Obstruction within 1C/SW/D/06 (phase 2). | 1570.0558 | 1570.0558 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SW
160.187 |  | Additional 8 way requested as per tie Change Order 1382, temporarily altered to 10 way. | 1800 | 1800 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 0 | -1800 | BT | 100
160.188 |  | Pumping out Water ingress from manhole & route of diversions. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 365 | 365 | Gen
160.189 |  | Drilling, Tapping & subsequent removal of unidentified mains. | 189.7936 | 189.7936 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SW
160.19 |  | Artificial Obstruction within 1C1/LP/D/105 | 3114.8542 | 3114.8542 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.191 |  | Stepping back of excavation to maintain safety required due to extension of connection pit as per record sheet 02656. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.192 |  | Artificial Obstruction within 1C/SP/D/04 & 1C/BT/D/35. | 4027.5345 | 4027.5345 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP & BT
160.193 |  | Additional excavation for archaeological investigations and to determine route around findings. | 8993.1108 | 8993.1108 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.194 |  | Drill & tap a 9" cast main on behalf of Infraco. | 159.428 | 159.428 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.195 |  | Assisting Virgin Media with blockages on their existing ductline on Princes St as requested by tie. Works to progress new cabling. | 985 | 985 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 500 | -485 | VM | 100
160.196 |  | Reinforced Concrete within additional 8 way BT diversion. | 2974 | 2974 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1200 | -1774 | BT
160.197 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.198 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.199 |  | Additional site tidy requested by tie site inspector despite site being acceptable due to Richard Jeffries (tie) attending site. | 593.9827 | 593.9827 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.2 |  | CUS required to demolish & rebuild traffic chamber from route of 8way BT. | 850 | 850 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.201 |  | Extra Over couplers & bends on 1C1/LP/D/104. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.202 |  | Abandoned Trial Hole for 1C1/LP/D/107. | 1030.5362 | 1030.5362 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.203 |  | Additional 9" Scottish Water cut & cap from route of 8way BT. | 1479.36 | 1479.36 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1877.3124 | 397.9524 | BT
160.204 |  | CUS were requested to assist BT Jointers assess whether or not the design of the 18 way BT being placed through existing manhole (conflict 1C/BT/12) would affect their cability to cable transfer at a later date. | 798.8003 | 798.8003 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT | 100
160.205 |  | Concrete within additional 8 way BT | 1286.7631 | 1286.7631 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.206 |  | Abandoned excavation due to existing utilities making SW specification & IFC design unachievable. | 735 | 735 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1748.231 | 1013.231 | SW
160.207 |  | Hand Digging for route of 1C/SW/D/02 & 03. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | SW
160.208 |  | Artificial Obstruction within 1C1/LP/D/108. | 2432 | 2432 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 2586.4162 | 154.4162 | SP
160.209 |  | Removal & Replacement of 1 no. gully pot & additional sewer piping. | 300 | 300 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 200 | -100 | SW
160.21 |  | Abandoned trial hole required to locate existing SP cables. 1C/SP/D/03. | 1300 | 1300 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1000 | -300 | SP
160.211 |  | Extra over excavation on 1C/SW/D/02 & 1C/SW/D/03 due to TM phasing. Caused by alterations to TM made by tie Change Orders 3584 & 3585. | 1800 | 1800 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1250 | -550 | SW
160.212 |  | Extra over excavation on 1C1/LP/D/108 & 1C/SP/D/03 in order to enable connection between two phases of TM. | 1100 | 1100 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1000 | -100 | SP
160.213 |  | Cancellation costs for Radius Systems due to the indemnity issue between tie & SGN still being unresolved. | 3133.44 | 3133.44 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 0 | -3133.44 | Gen
160.214 |  | Instruction for 0.5m3 C20 concrete around VM ducts at Haddington Place. | 39.712 | 39.712 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | VM
160.215 |  | Additional Scottish Water works Item 2 of Change Order 5316: Additional Pressure reducing valve, 3 no 150mm SV's, 150mm Water meter, 1 no. hydrant, and tee-piece & pipe will have to be reworked. | 20908.88 | 20908.88 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 07/05 |  | 4500 | -16408.88 | SW | 100
160.216 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.217 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.218 |  | Resources required to re- excavate and remove temporary BT shaft to MRX405. | 1840 | 1840 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 1200 | -640 | Gen
160.219 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.22 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.221 |  | Drilling, Tapping & subsequent removal of exisiting 9" C/I main from additional 180mm SW. | 157.1174 | 157.1174 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 100 | -57.1174 | SW
160.222 |  | Resouces required to repair 4" SW main on behalf of Infraco. Works requested as per Change Order 4504. | 342.6631 | 342.6631 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  | 200 | -142.6631 | SW
160.223 |  | Artificial Obstructions within 1C/SW/D/06 on Baxters Place TM. | 1133 | 1133 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 2000 | 867 | SW
160.224 |  | Commissioning of 500mm gas (1C1/LP/D/105), 400mm gas (1C1/LP/D/108) and 355 gas (1C1/LP/D/107). Bypasses claimed under CC246 as agreed | 2533 | 2533 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
160.225 |  | Additional 3 no. cores to manhole o/s Youth Hostel at Annandale street due to decision to revert back to IFC. | 435.2 | 435.2 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 250 | -185.2 | BT
160.226 |  | CUS required to demolish & rebuild existing virgin media chamber at Greenside lane, as existing chamber was of inadequate size to accept 1C/VM/D/07. IFC shows connection to existing. | 1000.9996 | 1000.9996 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | VM | 100
160.227 |  | Concrete removed from additional Scottish Water works at Antigua Street (works requested under item 2 Change Order 5316). | 328 | 328 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -328 | SW
160.228 |  | Instruction to repair water mian on behalf of Infraco. Resources required to repair 4" Scottish Water main on behalf of Infraco as instructed by Change Order 4504. | 0 | 0 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 381 | 381
160.229 |  | CUS required to re-instate and re-excavate Scottish Water chlorination and testing point above McDonald Road to enable TM for additional 8 way BT. | 2000 | 2000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -2000 | BT | 100
160.23 |  | CUS to procure additional 2 no. pallets of BT 54D ducts due to requirement to slew previously laid diversion 1C/BT/D/30 from route of extended 400mm PE gas. | 1200 | 1200 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -1200 | BT
160.231 |  | Delay due to S. Rodgers (Fujitsu) insisting CUS stop works on the BT at Annandale Street. | 736.9894 | 736.9894 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT | 100
160.232 |  | slew required on 1C/BT/D/30 - BT 24 way to facilitate extension of 400mm gas. | 11604.5482 | 0 | -11604.5482 | -100% | Slew Utilities |  |  | new | [6 empty] | SGN
160.233 |  | Artificial Obstructions and overbreak of excavation due to uncharted red brick structure in route of 400mm PE gas main. | 8902 | 8902 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 2500 | -6402 | SGN
160.234 |  | Concrete within excavation for additional 180mm Scottish Water Diversion at Baxters Place. | 819.1596 | 819.1596 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  |  |  | SW
160.235 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.236 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.237 |  | Removal of concrete from 355 x 355 connection point at Elm Row. | 3500 | 3500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -3500 | SW
160.238 |  | CUS were required to use 1m3 of concrete to backfill undermining. | 50.0806 | 50.0806 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | Gen
160.239 |  | Concrete within BT excavavtion at London Road | 4730.6464 | 4730.6464 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -4730.6464 | BT
160.24 |  | Requirement to sepertate 1C/BT/D/29 into 2 no. 8 ways to facilitate entrance into existing manhole around existing 16 way. (alteration required as per TQ 1663) | 500 | 500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -500 | BT
160.241 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.242 |  | Constructing temporary brickwork chamber in carriageway on 400mm SW diversion for testing purposes. | 2500 | 2500 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 2300 | -200 | SW
160.244 |  | Instruction to engage jointers for 1C/SP/D/05 & 1C/SP/D/06. | 1632 | 1632 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 250 | -1382 | SP
160.245 |  | CUS to procure a purge ejector. | 774.656 | 774.656 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  |  | -774.656 | SGN
160.246 |  | CUS requested to place an additional air valve on the existing 16" main at Baxters place. Exisiting main is to remain live during operation so under pressure connection applicable. | 4638 | 4638 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW | 100
160.247 |  | CUS are to sacrafice shoring to support thrust block. | 650 | 650 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  |  |  | SW
160.248 |  | CUS abandoned excavation due to uncharted stone as per CO 4514. | 1300 | 1300 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 2576.3405 | 1276.3405 | Gen
160.249 |  | CUS were required to remove cast from existing SP cables to identify cable types then re split duct after correct cables identified. | 1187.7953 | 1187.7953 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.25 |  | CUS to use foam concrete as backfill for the gas abandonment trench at London Road. | 1352.1773 | 1352.1773 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  |  |  | SGN
160.251 |  | CUS to install 2m3 of concrete protection to BT diversions. | 182.3597 | 182.3597 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | BT
160.252 |  | Delay due to leaking 4" SW asset (awaiting SW) and resources to repair as requested by Change Order 3899. | 1200 | 1200 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 0 | -1200 | SW | 100
160.253 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) | [9 empty] | Gen
160.254 |  | Requested to deliver 30m of 240V 4 core cable to Princes St for Infraco. | 117.7981 | 117.7981 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 04/05 |  |  |  | SP
160.255 |  | Concrete within excavation for 1C/BT/D/11, 12 & 13 at Annandale St. | 1200 | 1200 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 1850 | 650 | BT
160.256 |  | CUS required to excavte & backfill 2 no. 180mm connection point trial foles for 1C1/LP/D/103 due to TM & SGN indemnity issue. | 1962.9261 | 1962.9261 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  |  |  | SGN
160.257 |  | Additional Reinstatement & Additional Backfill at Annandale street due to isolation of existing TAR and loose ground above existing Sp tunnel. | 1000 | 1000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 800 | -200 | Gen |  | 398417.3313 | 336065.5008
160.258 |  | Abandoned Trial Hole as CUS cannot connect to 16" main at Baxters Place as per IFC design. (1C/SW/D/06). Consequently the conection point was ammended by site TQ: SW8 (copy attached). | 3000 | 3000 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 3500 | 500 | SW
160.259 |  | Additional cores to manhole 1C/BT/D/34 due to additional ducting added to crossing 1C/BT/D/35 post completion of manhole. | 1300 | 1300 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC Agreed 05/05 |  | 1000 | -300 | BT
160.26 |  | Additional flow stop connection on 1C1/LP/D/108 (355mm PE at Elm Row) due to required process of commissioning gas network. | 8255.9616 | 0 | -8255.9616 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
160.261 |  | Additional flow stopping to decomission conflict 1C1/LP/104 at London Road Roundabout as per attached NRO's. | 14243.3997 | 0 | -14243.3997 | -100% | Utility Abandonment |  |  | new | [6 empty] | SGN
CR 164 | [6 empty] | Agreed(*)
164.01 | 39570 | Works to disband services to the Caledonian Ale House. | 2905 | 2905 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.02 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
164.03 | 39609 | Removal of Blister to progress works. | 2863.6312 | 2863.6312 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.04 | 39604 | Demolish existing chamber and spilt duct through. | 886.95 | 886.95 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
164.05 | 39611 | Demolish 2 x Virgin Media Chambers (JF2) to replace with carriageway chambers. | 1264.7644 | 1264.7644 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
164.06 | 39606 | Working on weekend 7th & 8th June to lay 2way Thus & additional 2 x 150mm Scottish Power ducts across road where TM was only obtainable at weekend. | 2461.1339 | 2461.1339 | 0 | 0% | Agreed |  |  | AS | [6 empty] | THUS & SP
164.07 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
164.08 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
164.09 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed |  |  | AS
164.10 | 39631 | Abandoned Trial Holes to assist with technical queries. | 1139.724 | 1139.724 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.11 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.12 | 39678 | Logistic Support for Haymarket area | 333979.7684 | 173669 | -160310.7684 | -48% | Logistic Support |  |  | 3rd >£10k | [6 empty] | Gen
164.13 |  | Nil (see Master Change Register) |  |  | 0 | 0% | Agreed(*)
164.14 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.15 | 39692 | Demolishing chamber to rebuild CH/VM/2A/04/01. | 401.4304 | 401.4304 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
164.16 | 39692 | Re-excavation of 2A/TE/D/01. | 11026.4162 | 11026.4162 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SW
164.17 | 39700 | Backfilling excavations at request of tie | 529.0093 | 529.0093 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.18 |  | All Disrupted Plant Relating to 2A-01-01 | 46929 | 46929 | 0 | 0% | Agreed |  |  | AS |  |  | Agreed tie & CUS add £39402 TL/JC 11/03 | £39k tie not paid in cert? | 7527 | -39402 | Gen
164.19 |  | Abandoned Trial Holes | 279.4974 | 279.4974 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
164.2 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.21 |  | Demolish existing JUF6 chamber to rebuild THUS carriageway RC12 | 501.6115 | 501.6115 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | THUS
164.22 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.23 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.24 |  | Installation of 3 No Virgin Media cabinets as per schedule | 3852 | 3852 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
164.25 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.26 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.27 | 39779 | Removal of trees, shrubbery and memorial plaque from route of diversions. | 276.2668 | 276.2668 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.28 | 39790 | Hand Digging. | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.29 | 39790 | Artificial Obstructions | 238.2526 | 238.2526 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.3 | ` | Assessed Elsewhere (see Master Change Register) |  |  | 0 | 0% | Agreed(*)
164.31 | 40114 | Abandoned Trial Holes | 757 | 757 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
164.32 | 39798 | N.P.O associated with essential weekend working as per Change Order 3498. | 1400 | 1400 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.33 |  | Assessed Elsewhere (see Master Change Register) |  |  | 0 | 0% | Agreed(*)
164.34 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.35 | 39795 | N.P.O associated with weekend working. | 3172.5612 | 3172.5612 | 0 | 0% | NPO |  |  | 3rd | [6 empty] | Gen
164.36 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.37 |  | Enabling Works at entrance to Haymarket Yards. | 2718.1547 | 2718.1547 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
164.38 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.39 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.40 | 39797 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.41 | 39818 | Additonal Backfill and Reinstatement. | 977 | 977 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.42 | 39818 | Careful removal of concrete trough. | 414 | 414 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.43 |  | Removal of steps at Roseberry House. | 107 | 107 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.44 | 39820 | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.45 | 39818 | Removal of 3 Nr. Lighting Columns. | 389 | 389 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.46 | 39779 | Standing time awaiting L&M co-ordinates for 2A/SGN/D/02. | 88.9832 | 88.9832 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
164.47 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.48 |  | Excavating Joint Bay to enable disconnection of lampost at entrance to Haymarket Yards. | 189 | 189 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.49 | 40156 | Delay in laying 180mm Gas main (2A/SGN/D/02) due to unchartered brick structure. | 276 | 276 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
164.50 | 39827 | Additional width in excavation 2A/SP/D/01 due to undermining caused by unchartered brick structure. | 6316.3002 | 6316.3002 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SP
164.51 | 39783 | Downtime due to delay in opening Haymarket Yards | 973 | 973 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.52 |  | Artificial Obstructions | 810.7266 | 810.7266 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.53 |  | Downtime / Hand-Digging / Wasted excavations whilst trying to locate Gas supply to Roseberry House. | 2453.615 | 2453.615 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
164.54 | 39830 | Downtime due to unchartered brick structure | 679 | 679 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.55 | 39832 | Extension of CW2 Chamber to accept new duct line. | 1418 | 1418 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | C&W
164.56 | 39830 | 2 man team to bore 2" C/I suspected Gas main from route of 2A/SGN/D/02 | 27 | 27 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
164.57 |  | Additional footway reinstatement due to subsidence. | 2502 | 2502 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | Gen
164.58 |  | Reinforced Concrete under Footpath | 1831.3007 | 1831.3007 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
164.59 | 39840 | Demolishing Chamber - 2A/BT/D/01 | 1463.3332 | 1463.3332 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
164.60 | 39836 | Hand Digging / Downtime due to red bricks and roots in route of diversion 2A/PW/D/02. | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
164.61 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.62 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.63 |  | Additional Power cables required due to extension of 2A/SP/D/01 | 2913 | 2913 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SP
164.64 |  | Removal of lamposts from Haymarket Yards. | 499.3483 | 499.3483 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.65 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.66 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.67 | 39855 | Agreement to temporary reinstatement traffic island to progress other diversions. | 5352 | 5352 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
164.68 |  | Reinforced Concrete in 2A/PW/D/01. | 2299.3196 | 2299.3196 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | SW
164.69 | 39860 | Reinforced Concrete in 2A/TH/D/03. | 772.58 | 772.58 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | THUS
164.70 | 39841 | Delay Awaiting BT Re-jointing historic duct line. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | BT | 100
164.71 | 39857 | Removing unchartered brick structure from route of 2A/SGN/D/02. | 294.7949 | 294.7949 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SGN
164.72 |  | Re-excavation of 2A/PW/D/01 due to change to protectaline coil. | 2571.6403 | 2571.6403 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
164.73 |  | Artificial Obstruction | 540.7955 | 540.7955 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.74 | Week ending 06/06/2008 | Double Handling due to limited work area | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd >£10k | [6 empty] | Gen
164.75 |  | Downtime & wasted materials due to uncertainty caused by unchartered structure. | 546.3483 | 546.3483 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.76 |  | Demolition of Virgin Media JUF6 as per TQ 1016 | 1557 | 1557 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
164.77 |  | Demolition of Cable & Wireless JUF6 as per TQ 1015 | 1557 | 1557 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | C&W
164.78 | 39864 | Abandoned Trial Hole for 2A/BT/D/01, CW12 no longer required. | 795.2059 | 795.2059 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
164.79 | 39864 | Additional Track due to undermining caused by unchartered brick structure. | 1165.2112 | 1165.2112 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.80 | 39867 | Concrete | 242.0343 | 242.0343 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.81 | 39867 | Additional Slewing of existing power & street lighting from route of 2A/PW/D/01. | 3406.028 | 3406.028 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.82 |  | As per change order Carillion were required to excavate to remove bull head sculpatures at the enterance to Haymarket Yards | 703.616 | 703.616 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.83 | 39882 | Cutting into ducting on 2A/SP/D/02 to enable jointing of additional SP road crossing. | 119 | 119 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.84 | 39883 | Concrete | 1867.6838 | 1867.6838 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05
164.85 | 39883 | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
164.86 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
164.87 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
164.88 | 39883 | 2A/TH/D/04 additional diversion of existing ductline in order to enable transfer of cables post demolition of existing FW4 box. Also additional bends to manouvre BT 6 box. | 1904.4066 | 1904.4066 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | BT
164.89 | 39866 | Removal and replacement of sewer to allow route for 2A/SGN/D/03. | 660 | 660 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SW
164.90 | 39823 | Cold Taring & permanent hire of road plates to facilitate weekend working. | 4213.6414 | 4213.6414 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.91 | 39865 | Delay during weekend working as exposed a concrete shaft in route of 2A/SGN/D/03 and no tie representative was available to authorise removal. | 368.4936 | 368.4936 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
164.92 | 39818 | Delay due to temperature below 2 degress celcius stopping pouring of concrete for JRC11 - 2A/BT/D/01. This resulted in a consequential delay to the start date of 2A/SP/D/01, 2A/BT/D/01, 2A/TH/D/03, 2A/PW/D/02 | 567.2288 | 567.2288 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
164.93 | 39888 | Removal of additional shrubbery. | 240.9937 | 240.9937 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.94 | 39888 | Reinforced Concrete | 1347.8896 | 1347.8896 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.95 | 39883 | Additional works to existing telecoms to enable route for 2A/SGN/D/02 & 2A/PW/D/01. | 4714.0625 | 4714.0625 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
164.96 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
164.97 | 39896 | Additional footway reinstatement due to subsidence. | 2784.7142 | 2784.7142 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.98 | 39896 | Undermining in additional road crossing for 2A/SP/D/01 due to red brick and loose ground. | 3991.14 | 3991.14 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.99 | 39896 | Re- erecting 2nr lamposts. | 418 | 418 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.100 | 39896 | Reinforced Concrete | 2998 | 2998 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.101 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.102 |  | Hand Digging for route of 2A/PW/D/02 due to multitude of existing utilities. | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd
164.103 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.104 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.105 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.106 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.107 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.108 |  | Provision of temporary power supply & fuel to aid Virgin Media's cable transfering | 98.6335 | 98.6335 | 0 | 0% | Agreed |  |  | AS | [6 empty] | VM
164.109 |  | Additional excavtion in extension of 2A/SP/D/01 due to obstructions within existing ground. | 2880.3294 | 2880.3294 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.110 |  | Artificial Obstruction | 874.8784 | 874.8784 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.111 |  | Temporary Walkway for maitaining pedestrian access to Roseberry House. | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.112 |  | Cut back on exiting duct line in order to swing cables into new joint bay at Roseberry House. | 2325.7816 | 2325.7816 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
164.113 |  | Re-inforced concrete. | 259.0702 | 259.0702 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.114 |  | Re-excavation of 2A/SGN/D/01 to enable commissioning. | 2292.0732 | 2292.0732 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SGN
164.115 |  | Undermining in additional road crossing for 2A/SP/D/01 due to red brick & loose ground. | 3405.3515 | 3405.3515 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.116 |  | Re-excavation of Scottish Power joint bay at adjacent to INFRACO worksite and Haymarket train station. | 2239.7589 | 2239.7589 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.117 |  | Street Furniture | 88 | 88 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
164.118 |  | Additional Reinstatement | 231.7338 | 231.7338 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
164.119 |  | 2A/PW/D/01 - De-scoping/ abandonment of the North Twin crossings as per TQ 1279. | 5321.0518 | 5321.0518 | 0 | 0% | Utility Abandonment |  |  | 3rd | [6 empty] | SW
164.120 |  | Temporary Backfill of uncomplete diversions to enable Traffic Management switch to progress 2A/SP/D/01. | 2846.7001 | 2846.7001 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.121 |  | Artificial Obstructions | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.122 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
164.123 |  | Dig back on six metres of 2A/SP/D/01 that was already laid and lower ducts to NE 2.5m deep due to existing sewer. (further six metre section not yet excavated will have to be NE 2.5m deep - captured in remeasure) | 2606.1082 | 2606.1082 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
164.124 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.125 |  | Artificial Obstruction | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.126 |  | Hand-Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.127 |  | Artificial Obstruction | 2063.956 | 2063.956 | 0 | 0% | Agreed |  |  | AS | [6 empty] | SP
164.128 |  | Reinstatement of Steps at Roseberry House. | 747 | 747 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | SP
164.129 |  | Re-excavation of Temporary Backfill. | 2052.0093 | 2052.0093 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
164.13 |  | Carillion have experienced a large amount of hand digging at the above diversion |  | 0 | 0 | 0% | Agreed |  |  | new |  |  | Agreed hand dig as nil JC/TL 11/03 |  |  |  | SP
164.131 |  | As per Tie change order 3642 Carillion were requested to expose the power supply to the Virgin media cabinets | 1746.1865 | 1746.1865 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
164.132 |  | Gas abandonment as per schedule. (bypass claimed under CC246 as agreed) | 5881.8314 | 5881.8314 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SGN
164.133 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.134 |  | Carillion were required to stand down due to H&S | 533.6825 | 533.6825 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05
164.135 |  | Additional Reinstatement due to poor existing road surface & diversionary works prior to MUDFA | 3262.998 | 3262.998 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | CEC
164.136 |  | Assessed Elsewhere (see Master Change Register) | 0 | 0 | 0 | 0% | Agreed(*)
164.137 |  | Extra Over 2 no. 180mm MDPE 45 deg Bends due to unchartered sewer shaft. | 545.7732 | 545.7732 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
164.138 |  | Carillion were requested to remove 3no Virgin Media cabinets to allow the above diversion | 1648.6191 | 1648.6191 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | VM
164.139 |  | Due to space constraints Carillion were required to transport material to and from worksite by wheelbarrow. | 182.3025 | 182.3025 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 427802.4704 | 267491.7021
CR 169 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
169.04 | 39756 | Cus were required to stop works on site due land ownership issues. | 1256.9146 | 1256.9146 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
169.06 | 39728 | Excavation of Trial Holes as requested | 3258.4573 | 3258.4573 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
169.07 |  | disrupted plant | 626.6155 | 626.6155 | 0 | 0% | Agreed |  |  | AS |  |  | Agreed at £627 JC/TL 11/03 |  |  |  | Gen |  | 5141.9874 | 5141.9874
0
CR 185 | [6 empty] | Agreed(*)
0
185.3 |  | Abandoned Trial holes (ocean terminal) | 1016.2783 | 1016.2783 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
185.4 |  | Trial holes on Ocean Drive | 2946.7089 | 2946.7089 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
185.5 |  | Repair of steel Plate | 181.449 | 181.449 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 4144.4362 | 4144.4362
0
CR 190 | [6 empty] | Agreed(*)
|  |  | 0 | 0 | 0 | 0%
190.02 |  | Demolish of BT manhole (MRX608B) | 6778.715 | 6778.715 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
190.03 | 39692 | Demolish of BT manhole | 7034.2666 | 7034.2666 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
190.04 |  | Trial holes | 2787 | 2787 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.05 | 39820 | Trial Holes | 748 | 748 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.06 | 39823 | Drilling unidentified mains | 208 | 208 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.07 | 39829 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.08 |  | Abandoned trial hole | 515 | 515 | 0 | 0% | Agreed |  |  | AS | [6 empty] | BT
190.09 | 39827 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.1 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.11 |  | Delay and disruption | 511 | 511 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.12 | 39828 | Trial Holes | 845 | 845 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.13 | 39827 | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.14 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.15 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.16 |  | Additional Works | 1062 | 1062 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.17 | 39852 | All disrupted plant associated with 1C-05-01 | 8344.1288 | 8344.1288 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
190.18 |  | Hand Digging | 5298.0029 | 5298.0029 | 0 | 0% | Agreed |  |  | 3rd |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.19 | 39860 | Delay and Disruption | 554.0096 | 554.0096 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.2 | 39869 | Double Handling | 0 | 0 | 0 | 0% | Agreed(*) |  |  | 3rd | [6 empty] | Gen
190.21 | 39861 | Double Handling Materials | 673 | 673 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
190.22 | 37676 | Delay and Disruption | 729.5432 | 729.5432 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
190.23 | 39878 | Additional Works | 1564.07 | 1564.07 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
190.24 |  | Artificial Obstructions | 3041.12 | 3041.12 | 0 | 0% | Agreed |  |  | top 68 | [6 empty] | Gen
190.25 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.26 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.27 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.28 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.29 |  | Concrete Protection over shallow diversion | 720 | 720 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.3 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed |  |  | 3rd <£2k | [6 empty] | Gen
190.31 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.32 |  | Artificial Obstructions | 7471.226 | 7471.226 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.33 |  | Hand Digging | 4586.8651 | 4586.8651 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.34 |  | Removal of undermined Carraigeway | 2672.508 | 2672.508 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.35 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.36 |  | Trial Holes | 505.6988 | 505.6988 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.37 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.38 |  | Picking up litter | 3096.72 | 3096.72 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.39 |  | Reconstruction of Sewer Shaft | 3355.9222 | 3355.9222 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.4 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.41 |  | Artificial Obstructions | 655.3276 | 655.3276 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.42 |  | Temporary backfilling of excavation | 7037.6221 | 7037.6221 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.43 |  | Extra over foam concrete for Picardy Place - 1C-05-01, as per CVI 01356. To be read in conjunction with CC160.152 as 109m3 already claimed against 1C-04-01. | 3555.7254 | 3555.7254 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.44 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.45 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.46 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.47 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.48 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.49 |  | Delay and disruption due to additional depth of diversion |  |  | 0 | 0% | Agreed(*) |  |  | new
190.5 |  | Artificial Obstructions | 2283.4073 | 2283.4073 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.51 |  | Delay and disruption awaiting instruction from tie |  |  | 0 | 0% | Agreed(*) |  |  | new
190.52 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.53 |  | Trial Holes | 1815.7066 | 1815.7066 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.54 |  | Temporary backfill of excavation | 2287.1253 | 2287.1253 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.56 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.57 |  | Investigative works | 2928.9529 | 2928.9529 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.58 |  | Trial Hole | 1076.5423 | 1076.5423 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.59 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.6 |  | Abandoned Manhole | 6808.8998 | 6808.8998 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
190.61 |  | Trial Hole | 1840.2432 | 1840.2432 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.62 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.63 |  | Artificial Obstruction | 254.7516 | 254.7516 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.64 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.65 |  | CUS requested to undertake additional trial hole 10 metres up Elder St junction as contingency plan (abandoned) | 3978.1005 | 3978.1005 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.66 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*) |  |  | new
190.67 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) | [9 empty] | Gen
190.68 |  | Delay due to unchartered concrete structure | 334.9952 | 334.9952 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
160.69 |  | Investigative works | 677.429 | 677.429 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.7 |  | Daily removal of rubbish site wide | 127.4222 | 127.4222 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.71 |  | Daily removal of rubbish site wide | 705.7317 | 705.7317 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.72 |  | Slew and lower of existing 16 way | 1965.2 | 1965.2 | 0 | 0% | Slew Utilities |  |  | new | [6 empty] | BT
190.73 |  | Removal of excess carraigeway | 1150.2365 | 1150.2365 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.74 |  | Topographical survey - Broughton St | 548.9395 | 548.9395 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.75 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.76 |  | Removal of Underground Structure roof | 8190.7676 | 8190.7676 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.77 |  | Backfill and re-excavation of trench | 1551.007 | 1551.007 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.78 |  | Delay and disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | D&D
190.79 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | D&D
190.8 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.81 |  | Foam Concrete Backfill | 300.4838 | 300.4838 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.82 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.83 |  | Delay and Disruption/ Investigative works | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | D&D
190.84 |  | Site welfare - removing litter from site | 555.968 | 555.968 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.85 |  | Due to revised position of BT Manhole 1C/BT/D/62 cus has abandoned part of diversion 1C/BT/D/68 - east section | 1685.6471 | 1685.6471 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.86 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.87 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.88 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.89 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.9 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.91 |  | Drilling unchartered gas mains | 408.7108 | 408.7108 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
190.92 |  | Artificial Obstruction | 1529.0978 | 1529.0978 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.93 |  | Reduced productivity due to site restrictions | 3992.6453 | 3992.6453 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.94 |  | CUS instructed as per Change Order 4656 to temporary backfill the 180 & 400 water to allow procgression of the 16 way SP. | 1229.2194 | 1229.2194 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
190.95 |  | Demolish & rebuild of JRF11A as instructed by TQ 1575 to provide a route for the 180mm SW diversion. | 2930.2538 | 2930.2538 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.96 |  | Temporarily backfilled Joint Bay | 3746.7352 | 3746.7352 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
190.97 |  | Directing traffic on York Pl | 47.0125 | 47.0125 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.98 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.99 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.1 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.101 |  | Removing silt from undergound structure | 2879.545 | 2879.545 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.102 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.103 |  | CUS infilled underground structure at London Rd/ Playhouse as per drawings detailed under Change Order 3419 | 7176.7552 | 7176.7552 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.104 |  | Additional works to underground cellar | 8687.3797 | 8687.3797 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.105 |  | Delay and disruption awaiting information on underground cellars o/s Conan Doyle | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.106 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.107 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.108 |  | CUS as agreed procured 30 no. steel plates to protect existing live HV ducts whilst new comms diversions where being laid. | 1120.64 | 1120.64 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.109 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.11 |  | Manhole Survey | 325.1143 | 325.1143 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
190.111 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.112 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.113 |  | Delay and Disruption | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new
190.114 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.115 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.116 |  | Removal of redundant gully o/s Conan Doyle | 474.9204 | 474.9204 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.117 |  | Foam Concrete backfill | 400.6451 | 400.6451 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.118 |  | Hand Digging | 0 | 0 | 0 | 0% | Agreed(*) |  |  | new | [6 empty] | Gen
190.119 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.12 |  | requirement for foam concrete to backfill diversions o/s the Conan Doyle to enable TM switch | 2554.1126 | 2554.1126 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.121 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.122 |  | Total measure requierd to Slew existing 3 way thus from route of Scottish Power diversion equates to 71 metres, however 44 metres has previously been cliamed under CC129.180. | 4504.4424 | 4504.4424 | 0 | 0% | Slew Utilities |  |  | new | [6 empty] | THUS
190.123 |  | Repair of existing link box cover | 573.6117 | 573.6117 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.124 |  | Modification to existing sewer | 22681.4848 | 22681.4848 | 0 | 0% | Other (WS) |  |  | new | [6 empty] | SW
190.125 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.126 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
190.127 |  | nil (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
190.128 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
190.129 |  | Assessed Elsewhere (see Master Change Control Register) |  |  | 0 | 0% | Agreed(*)
190.13 |  | As per Change Order 3593 CUS have pre-fabricated 6 no. concrete slabs for future sewer works. | 620.83 | 620.83 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.131 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.132 |  | Completion of modification to existing sewer at Elder street. | 2850.7872 | 2850.7872 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.133 |  | Concrete removed from centre section Traffic Management - York Place. | 2730.5318 | 2730.5318 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.134 |  | Additional backfill and reinstatement due to underground structure within route of 1C/BT/D/36. | 5470.136 | 5470.136 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
190.135 |  | Additional Scottish Water works Item 5: Fire Hydrant at Cathedral Lane. CUS excavated, SW installed. | 1896.1866 | 1896.1866 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
190.136 |  | Removal of lampost and road sign. | 1253.5989 | 1253.5989 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen
190.137 |  | Increased shaft size on the MRX608A at Elder Street due to congestion of utilities. | 4630.6533 | 4630.6533 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.138 |  | Foam concrete for backfill on York Place due to time constraints. | 9014.5152 | 9014.5152 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.139 |  | Abandonment of: 32 way BT (1C/BT/D/58), 1 way BT (1C/BT/D/59) & MRX402A (1C/BT/D/60) due to design issues. | 0 |  | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.14 |  | Demolition of 2 no JRF106's as per schedule and construction of a temporary JUF6 to enable a blown fibre tube joint. | 2575.3555 | 2575.3555 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.141 |  | Abandonment of trial hole for MRX412. | 5862.2787 | 5862.2787 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | BT
190.142 |  | Requirement to demolish and rebuild a JRCX12 to facilitate the laying of diversion 1C/SP/D/02 underneath. | 2041.4294 | 2041.4294 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
190.143 |  | CUS to carry out 9 additional core drills to the 613 manhole at Elder Street. | 1044.48 | 1044.48 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
190.144 |  | requirement for AJ Jointing to carry out electrical jointing of diversion 1C1/SP/D/02. | 3329.28 | 3329.28 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
190.145 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.146 |  | CUS to use foam concrete as backfill on the twin water crossing 1C/SW/D/11. | 1953.145 | 1953.145 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.147 |  | CUS required to break out redundant culvert o/s the Conan Doyle, which had previously been infilled with C40 concrete. | 7536.2679 | 7536.2679 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | SW
190.148 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.149 |  | nil (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.15 |  | CUS were required to excavate a buried valve at Elder St for Scottish Water to prove the network for cut & cap operation. | 200.8247 | 200.8247 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW | 100
190.151 |  | CUS to install a stop end on the 315mm gas diversion due to the emabargo. | 174.8711 | 174.8711 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SGN
190.152 |  | As discussed with Ken Reddington (SP) & Lloyd Glen (tie), CUS are to provide 2 operatives to assist SP with jointing. | 635.9578 | 635.9578 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
190.153 |  | CUS were required to use foam concrete to accelarate the program and insure the TM switch to area 9 is achieved. | 5008.064 | 5008.064 | 0 | 0% | Agreed |  |  | new |  |  | Agreed to apply 44% factor TL/JC 18/05 |  |  |  | Gen
190.154 |  | Assessed Elsewhere (see Master Change Control Register) | 0 | 0 | 0 | 0% | Agreed(*)
190.155 |  | Additional works to repair non MUDFA related drainage issue. | 1414.0333 | 1414.0333 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SW
190.156 |  | Staking of slabs from the conan doyle to o/s #16 York Place for CEC Flatbed to collect. | 276.0038 | 276.0038 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | Gen |  | 128846.1846 | 128846.1846
190.157 |  | CUS were required to excavte back on the existing 8 way SP cables at elder st to slew to enable spiking and jointing required for 1C/SP/D/02. | 2384.8416 | 2384.8416 | 0 | 0% | Slew Utilities |  |  | new | [6 empty] | SP
190.158 |  | Due to relocation of diversion as per tie Change Order 3427 (item 2) CUS were required to abandon 16 metres of 1C/SP/D/02 & 1 no. joint bay. | 14482.4115 | 14482.4115 | 0 | 0% | Utility Abandonment |  |  | new | [6 empty] | SP
CR 192 | [6 empty] | Agreed(*)
[5 empty] | 0 | 0%
192.2 | TBC | 10 No Trial Holes at S1A Chancelot Mill | 0 | 0 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen
192.4 | 39800 | Trial holes at Chancelot Mill | 4303.6271 | 4303.6271 | 0 | 0% | Agreed |  |  | AS | [6 empty] | Gen |  | 4303.6271 | 4303.6271
CR 198 | [6 empty] | Agreed(*)
198 |  | 1A-01-01 | 3885 |  | -3885 | -100% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 2A-01-01 | 21691 | 21539.049 | -151.951 | -0.7005% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1D-01-01 | 67052 | 51317.2855 | -15734.7145 | -23.47% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1D-04-01 | 30070 | 21578.7827 | -8491.2173 | -28.24% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1C-01-01 | 69866 | 68207.685 | -1658.315 | -2.374% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1C-04-01 | 63738 | 27696.2368 | -36041.7632 | -56.55% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1B-01-01 | 18941 | 16337 | -2604 | -13.75% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1B-02-01 | 10932 | 10490 | -442 | -4.043% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1C-05-01 | 62971 | 46014 | -16957 | -26.93% | NPO |  |  | 3rd >£10k | [6 empty] | Gen
198 |  | 1C-03-02 | 110307 | 116134 | 5827 | 5.283% | NPO |  |  | 3rd >£10k | [6 empty] | Gen |  | 459453 | 379314.039
CC 228 | [6 empty] | Agreed(*)
0
228.07 |  | CUS to prove existing SP ductline by means of Cobra | 1025.1675 | 1025.1675 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | SP
228.08 |  | All Disrupted Plant Relating to Worksite 7B | 541.9833 | 541.9833 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC agreed 26/05 |  |  |  | Gen
0
CC 231 | [6 empty] | Agreed(*)
0
231.03 |  | Core Drilling | 95.64 | 95.64 | 0 | 0% | Agreed |  |  | new |  |  | TL/JC apply 43% factor agreed 18/05 |  |  |  | BT
0
CC 246 | [6 empty] | Agreed(*)
0
246 |  | Bypass - All Sites | 672039.0285 | 65840 | -606199.0285 | -90.2% | Bypass |  |  | new | [6 empty] | SGN
ENABLING | [6 empty] | Agreed(*)
108 |  | Removal of Princes St. Central Reservation | 129958.1082 | 101913.4539 | -28044.6543 | -21.58% | Enabling |  |  | top 14 | [6 empty] | Gen
109 |  | Enabling works for St Andrew Square Utility Diversions Instruction to proceed with works | 1580067.9622 | 1646539.4513 | 66471.4891 | 4.207% | Enabling |  |  | top 14 | [6 empty] | Gen
109.4 |  | Enabling Works CVI's | 202366.1613 | 202366.1613 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
109.23 |  | Whitelining Works | 588235.4253 | 588235.4253 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
158 |  | Constitution Street Enabling Works | 396396.139 | 224729.4403 | -171666.6987 | -43.31% | Enabling |  |  | top 14 | [6 empty] | Gen
163 |  | Enabling works for 1C (Top of Leith Walk) | 225217.6218 | 134129.5782 | -91088.0436 | -40.44% | Enabling |  |  | top 14 | [6 empty] | Gen
166 |  | 5B Enabling Works | 93241.1234 | 63028.5205 | -30212.6029 | -32.4% | Enabling |  |  | top 14 | [6 empty] | Gen
170 |  | 2A Enabling works (Haymarket) | 490688.4094 | 419573.5374 | -71114.872 | -14.49% | Enabling |  |  | top 14 | [6 empty] | Gen
175 |  | General Enabling Works | 1335089.3971 | 1479133.8053 | 144044.4082 | 10.79% | Enabling |  |  | top 14 | [6 empty] | Gen
183 |  | 5C Enabling Works, Gogar Roundabout | 99493.9117 | 99493.9117 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
189 |  | Side entry manholes, Leith Walk | 2225608.5993 | 2313174.5236 | 87565.9243 | 3.934% | Enabling |  |  | top 14 | [6 empty] | Gen
213 |  | Enabling Works 1A-01-01 | 15866.1734 | 15866.1734 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
218 |  | Enabling Works 1C-01-01 | 3390.5239 | 3390.5239 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
220 |  | Enabling Works 1C-03-02 | 8976 | 8976 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
221 |  | Enabling Works 1C-04-01 | 108857.9781 | 114280.5592 | 5422.5811 | 4.981% | Enabling |  |  | top 14 | [6 empty] | Gen
222 |  | Enabling Works York Place | 74002.6257 | 74002.6257 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
223 |  | Enabling Works Haymarket | 6681.5124 | 6681.5124 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
224 |  | Enabling Works 1D-04-01 | 40967.3864 | 40967.3864 | 0 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
[5 empty] | 0 | 0%
Enabling |  | Global Enabling Deduction |  | -953807.07 | -953807.07 | 0% | Enabling |  |  | top 14 | [6 empty] | Gen
[5 empty] | 0 | 0%
WORKSITE MEASURE | [6 empty] | Agreed(*)
1A-03-00 |  | (Trial Site) | 52679.7525 | 52679.7525 | 0 | 0% | Agreed |  | 52679.7525 | AS
1A-01-01 |  | Constitution Street | 1567880.4945 | 1380957.89 | -186922.6045 | -11.92% | Measure |  | 1380957.89 | Measured Works
1A-01-02 |  | Rennie's Isle | 36366.68 | 29661.52 | -6705.16 | -18.44% | Measure |  | 29661.52 | Measured Works
1A-02-01 |  | Ocean Terminal | 0 | 0 | 0 | 0% | Agreed |  | 0 | Measured Works
1A-03-01 |  | Tower St. to Rennies Isle as previous | 619998.9011 | 619998.9011 | 0 | 0% | Agreed |  | 619998.9011 | Measured Works
1A-04-01 |  | Newhaven Roudabout to Ocean Terminal | 0 | 0 | 0 | 0% | Agreed |  | 0 | Measured Works
1B-01-01 |  | Leith Walk; McDonald Rd. - Iona St. | 2184407.9334 | 1909132.98 | -275274.9534 | -12.6% | Measure |  | 1909132.98 | Measured Works
1B-02-01 |  | Leith Walk; Balfour St - Constitution St | 2482536.98 | 2172030.73 | -310506.25 | -12.51% | Measure |  | 2172030.73 | Measured Works
RAT 1B 01 |  | Jane Street BT Manholes |  |  | 0 | 0% | Agreed |  | 0 | Measured Works
1C-01-01 |  | The Mound | 494716.7428 | 489067.74 | -5649.0028 | -1.142% | Measure |  | 489067.74 | Measured Works
1C-01-02 |  | Mound to Castle St. East | 23372.18 | 23372.18 | 0 | 0% | Agreed |  | 23372.18 | Measured Works
1C-02-01 |  | Mound to South St Andrews St | 237772.0314 | 221158.49 | -16613.5414 | -6.987% | Measure |  | 221158.49 | Measured Works
1C-03-02 |  | York Place to South St Andrews Street | 1503085.5748 | 1205672.61 | -297412.9648 | -19.79% | Measure |  | 1205672.61 | Measured Works
1C-04-01 |  | Broughton Street - McDonald Road | 1644752.014 | 1475814.35 | -168937.664 | -10.27% | Measure |  | 1475814.35 | Measured Works
1C-05-01 |  | Union Street - York Place | 768307.2174 | 741950.42 | -26356.7974 | -3.431% | Measure |  | 741950.42 | Measured Works
RAT 1C 01 |  | St Andrews Square | 536885.3 | 536885.3 | 0 | 0% | Agreed |  | 536885.3 | Measured Works
1D-01-01 |  | Manor Place to Haymarket | 1515562.6034 | 1395442.83 | -120119.7734 | -7.926% | Measure |  | 1395442.83 | Measured Works
1D-04-01 |  | Shandwick Place | 1632206.8179 | 1498597.64 | -133609.1779 | -8.186% | Measure |  | 1498597.64 | Measured Works
1D-05-02 |  | Castle Street East to Castle St. West | 47281.87 | 47281.87 | 0 | 0% | Agreed |  | 47281.87 | Measured Works
2A-01-01 |  | Haymarket RaT 2A | 544647.4688 | 523545.62 | -21101.8488 | -3.874% | Measure |  | 523545.62 | Measured Works
5A-08-02 |  | Roseburn St to Russell Rd as previously certified | 109962.2125 | 109962.2125 | 0 | 0% | Agreed |  | 109962.2125 | Measured Works
5B-01-01 |  | Broomhouse Rd to Edinburgh Park | 441257.98 | 441257.98 | 0 | 0% | Measure |  | 441257.98 | Measured Works
5C-01-01 |  | Gogarburn to Edinburgh Park TS | 1202957.76 | 1202957.76 | 0 | 0% | Agreed |  | 1202957.76 | Measured Works
6A-01-01 |  | 6A-01-01 Gogar Depot MUDFA | 571786.14 | 571786.14 | 0 | 0% | Agreed |  | 571786.14 | Measured Works
7A-02-01 |  | Gogarburn - Ingliston Park & Ride Prov. Allowance | 41174.1 | 41174.1 | 0 | 0% | Agreed |  | 41174.1 | Measured Works
7B-01-01 |  | Edinburgh Airport | 0 | 0 | 0 | 0% | Agreed | 0 |  | Measured Works
|  |  | 0 |  | 0
PRELIMS | [6 empty] | Agreed(*)
PCS |  | Pre-construction Services | 987610.595 | 987610.595 | 0 | 0% | Agreed |  |  | PCS/MOS | [6 empty] | Gen
Prelims |  | Prelims | 8936461.6246 | 8936461.6246 | 0 | 0% | Agreed |  |  | Prelims |  |  | TL/JC agreed in meeting 02/06 (PK/FD present) |  |  |  | Gen
OTHER ITEMS | [6 empty] | Agreed(*)
Other |  | Gogar Depot (phase 1) | 3290996.6121 | 3290996.6121 | 0 | 0% | Agreed |  |  | AS
Other |  | Gogar Depot (phase 2) | 1997771 | 1997771 | 0 | 0% | Agreed |  |  | 3rd >£10k |  |  | JC/JC agreed email 18/05 (to balance final account)
Other |  | Gain Share | 256000 | 256000 | 0 | 0% | Agreed |  |  | top 14 | [6 empty] | Gen
Other |  | Indices | 1587000 | 1587000 | 0 | 0% | Agreed |  |  | top 14 | [6 empty] | Gen
Claim |  | Entitlement (Up to September 2008) | 1880000 | 1880000 | 0 | 0% | Agreed |  |  | top 14 | [6 empty] | Gen
Claim |  | Entitlement (From 1st October 2008) | 13244871.0446 | 1109426 | -12135445.0446 | -91.62% | Entitlement |  |  | top 14
Other |  | Hand Digging | 152000 | 152000 | 0 | 0% | Agreed |  |  | 3rd |  |  | TL/JC agreed 26/05 |  |  |  | Gen
[5 empty] | 0 | 0%
Other |  | Tie Deductions | -15000 | -794933.16 | -779933.16 | 5200% | tie Deductions |  |  | top 14
-146251.682
Note:
-'Agreed(*)' has the meaning:- Agreed for the purposes of this schedule and the AFP, where CUS have now sort to recover the associated value elsewhere. For avoidance of doubt the associated value has been included against other items in the sums above (eg D&D items in Entitlement and individual gas bypasses in CR246).
|  |  | 7087139.0609 | 6555523.7653