## Sheet1
INTC - Status of Estimates (Updated as of 12th March 2010)
OUTSTANDING ACTION
Section |  | INTC No | Description | Change Order Issue | Estimate received | Original submitted BSC Order Value | BSC Estimate (Complete) | BSC Estimate (D/O) | Change Order Value | Estimate Outstanding |  |  | INTC Deleted / Not Issued / Withdrawn / By Others | Change Order Nr | Design Only Estimate |  | tie |  | BSC |  | DISPUTED | COMMENTS | Latest Reference
unall | 1 | 1 | V31design delivery programme | 1 | 1 | 7049000 | 7049000 |  | 3524000 |  |  |  |  | 116
| 1 | 2 | Hilton Hotel Car Park |  | 1 |  | 90067 | [12 empty] | 1 | DISPUTED | DRP - No Change
unall | 1 | 3 | Road Surveys | 1 | 1 | 97691.85 | 97692 |  | 77498 |  |  |  |  | 43
1B | 1 | 4 | Russel Road Bridge | [6 empty] | 1 | Est Outstanding
2A | 1 | 5 | Haymarket viaduct | [6 empty] | 1 | Est Outstanding
7A | 1 | 6 | Gogarburn surcharge | [6 empty] | 1 | Est Outstanding
2A | 1 | 7 | Hardstanding at Haymarket Yards | 1 | 1 | 880.5 | 881 |  | 881 |  |  |  |  | 17
| 1 | 8 | Drawing Revisions (DELETED) | [8 empty] | 1 | Deleted
7 | 1 | 9 | Archeological delays at gogar sect 7 | [6 empty] | 1 | Est Outstanding
5C | 1 | 10 | Archeological delays at gogar sect 5c | [6 empty] | 1 | Est Outstanding
| 1 | 11 | Duplicate of 10 (DELETED) | [8 empty] | 1 | Deleted
5C | 1 | 12 | Archeological delays at gogar tramstop | [6 empty] | 1 | Est Outstanding
| 1 | 13 | Planning Consents delay Roseburn (DELETED) | [8 empty] | 1 | Deleted
6 | 1 | 14 | Depot 800dia watermain | [6 empty] | 1 | Est Outstanding
6 | 1 | 15 | depot 250dia watermain | [6 empty] | 1 | Est Outstanding
6 | 1 | 16 | 1500dia Sewer | [6 empty] | 1 | Est Outstanding
5B | 1 | 17 | Sewer at South Gyle Access Bridge |  |  |  |  | 286599 | [6 empty] | Validated | [6 empty] | Prelim/Utilities des instructed. Tie undertaking GI wks to clarify preferred option
unall | 1 | 18 | Consortium Office |  | 1 |  | 36732 | [10 empty] | 1 | BSC |  |  | Await confirmation of P.Sums
2A | 1 | 19 | Archeological Works CAH | 1 | 1 | 5201 | 5201 |  | 5976.61 |  |  |  |  | 1
| 1 | 20 | Disconnect utilities CAH (DELETED) | [8 empty] | 1 | Deleted
2A | 1 | 21 | Asbestos work at CAH | 1 | 1 | 5268 | 5268 |  | 6053.64 |  |  |  |  | 2
| 1 | 22 | Asbestos in steps at CAH (DELETED) | [6 empty] | 1 | Est Outstanding
2A | 1 | 23 | Demolish Access steps at CAH | 1 | 1 | 4040 | 2020 |  | 2360.75 |  |  |  |  | 12
| 1 | 24 | Verity House Access road | [6 empty] | 1 | Est Outstanding
| 1 | 25 | Demolition of CAH | [6 empty] | 1 | Est Outstanding
| 1 | 26 | SDS delay Picardy Place | [6 empty] | 1 | Est Outstanding
1D | 1 | 27 | SDS delay Section ID | [6 empty] | 1 | Est Outstanding
1B | 1 | 28 | SDS delay Section IB | [6 empty] | 1 | Est Outstanding
| 1 | 29 | sds delay to Haymarket Access Road | [8 empty] | 1 | Withdrawn
| 1 | 30 | Acceleration of IFC delivery | [8 empty] | 1 | Withdrawn | [8 empty] | BSC confirm Withdrawl if INTC (e-mail 22/1/10)
| 1 | 31 | SDS handrail at Telford Road Bridge | [8 empty] | 1 | Withdrawn
| 1 | 32 | CEC late approval | [6 empty] | 1 | Est Outstanding
| 1 | 33 | CEC late approval | [6 empty] | 1 | Est Outstanding
| 1 | 34 | Public Realm Workbook | [6 empty] | 1 | Est Outstanding
| 1 | 35 | Public Realm Workbook | [8 empty] | 1 | Withdrawn
| 1 | 36 | Delay Crewe Road Gardens Bridge | [6 empty] | 1 | Est Outstanding
7 | 1 | 37 | SDS Delay at Roseburn | [6 empty] | 1 | Est Outstanding
unall | 1 | 38 | SDS Delay to Roads design | [6 empty] | 1 | Est Outstanding
| 1 | 39 | SDS Delay to shandwick place Tram stop | [6 empty] | 1 | Est Outstanding
| 1 | 40 | SDS Delay to ground investigation | [6 empty] | 1 | Est Outstanding
| 1 | 41 | SDS Delay to Ravelston Tram stop | [6 empty] | 1 | Est Outstanding
| 1 | 42 | SDS Delay to ravelston Tramstop | 1 | 1 | 2855.17 | 2855.17 |  | 2409.05 |  |  |  |  | 58
1D | 1 | 43 | SDS Delay to Shandwick Place Lighting | [8 empty] | 1 | Withdrawn
1A | 1 | 44 | Amendements to Ocean Terminal |  | 1 |  | 125932 | [10 empty] | 1 | BSC |  |  | Await response to tie e-mail | Refer tie e-mail 20/1/09, 7/4/09
| 1 | 45 | SDS Delay to Balfour Street Tramstop | [6 empty] | 1 | Est Outstanding
1B | 1 | 46 | SDS Delay - 1B Roads, street light etc | [6 empty] | 1 | Est Outstanding
1A | 1 | 47 | SDS Delay - 1A Roads, street light etc | [6 empty] | 1 | Est Outstanding
| 1 | 48 | Additional TRO drgs | 1 | 1 | 3572.55 | 3996.3 |  | 3550 |  |  |  |  | 15
1A | 1 | 49 | Revised work scope at Bernard Street |  | 1 |  | 1224685 | [12 empty] | 1 | DISPUTED | BDDI Planning Drawing
| 1 | 50 | Traffic Signal Works | 1 | 1 | 33875 | 30550 |  | 30550 |  |  |  |  | 22
5A | 1 | 51 | Utility Diversions - Section 5A | 1 | 1 | 94849.82 | 64192 |  | 75488.5 |  |  |  |  | 2
5A | 1 | 52 | Utility Diversions - Section 5B | 1 | 1 | 190008.42 | 75694 |  | 88027.17 |  |  |  |  | 3
5C | 1 | 53 | Utility Diversions - Section 5C | 1 | 1 | 236901.22 | 33723 |  | 33723 |  |  |  |  | 4
5C | 1 | 53 | Utility Diversions - Section 5C (Provisional Sum - Watermain Diversion) |  | 1 |  | 110000 |  | 39217.65 | [8 empty] | 1 | BSC |  |  | Await further quotations (refer tie letter INF CORR 550)
1C | 1 | 54 | St Andrews Square - Estimate |  | 1 |  | 7709747 |  |  |  |  | 1 | [7 empty] | 1 | DISPUTED | BDDI Planning Drawing
3C | 1 | 55 | Delay and Disruption (SDS) - Section 3C | [6 empty] | 1 | Est Outstanding
1A | 1 | 56 | Delay and Disruption (SDS) - Section 1A | [6 empty] | 1 | Est Outstanding
1D | 1 | 57 | Delay and Disruption (SDS) - Section 1D | [6 empty] | 1 | Est Outstanding
unall | 1 | 58 | Delay and Disruption (SDS) - Road Safety Audits | [6 empty] | 1 | Est Outstanding
| 1 | 59 | Removal of Asbestos to buildings to be demolished | 1 | 1 | 26227.08 | 26048 |  | 29947.8 |  |  |  |  | 5
7A | 1 | 60 | Gogar Bridge Sewer Diversion | 1 | 1 | 44661 | 44661 |  | 36292 |  |  |  |  | 146 | [7 empty] | Agreed
7A | 1 | 61 | Re-location of Archeological Arisings |  | 1 |  | 99678.75 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter 21/1/10 (ref 3235/MP) | INF CORR 3235 / SJ
| 1 | 62 | S.Power quotation for connections (Refer INTC 88) | [8 empty] | 1 | Withdrawn
unall | 1 | 63 | Tensioning of overhead contact system | [6 empty] | 1 | Est Outstanding
1A | 1 | 64 | Revised Finishes at Ocean Terminal |  | 1 |  | 4166 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4695 17/02/10
5A | 1 | 65 | Murrayfield - Patterned Finish |  |  |  |  | 3348 | [6 empty] | Validated
7A | 1 | 66 | Revised specification - RBS Gogarburn Tramstop | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  | Revised workscope sent out. | INF CORR 2706/JO (29/10/09)
7A | 1 | 66A | RBS - Abortive Estimate cost |  | 1 |  | 7683 | [12 empty] | 1 | DISPUTED | tie reject abortive cost | BSC ref 5000 12/03/2010
5A | 1 | 67 | Provide second access stair, Murrayfield Tramstop |  |  |  |  | 32648 | [6 empty] | Validated
5B | 1 | 68 | Lack of Scottish Water Consents - Edinburgh Park to Carrick Knowe | [6 empty] | 1 | Est Outstanding
5B | 1 | 69 | MUDFA not complete to Gyle Stop Retaining Wall | [6 empty] | 1 | Est Outstanding
5B | 1 | 70 | MUDFA not complete to Bankhead Retaining Wall | [6 empty] | 1 | Est Outstanding
1A | 1 | 71 | Lack of Scottish Water Consents - Foot of the Walk to Balfour Street | [6 empty] | 1 | Est Outstanding
2A | 1 | 72 | Lack of Scottish Water Consents - Haymarket to Roseburn Junction | [6 empty] | 1 | Est Outstanding
5A | 1 | 73 | Contamination of land Knotweed - Russell Rd Retaining Wall | [8 empty] | 1 | Withdrawn
7A | 1 | 74 | Divert existing 300mm diam sewer - gogar landfill | 1 | 1 | 1433.79 | 1434 |  | 1434 |  |  |  |  | 63
6A | 1 | 75 | Install temporary ramp - Depot | 1 | 1 | 14348.39 | 14348 |  | 16303.75 |  |  |  |  | 27
5C | 1 | 76 | Gogar Trainstop |  |  |  |  | 743869 | [6 empty] | Validated | [6 empty] | estimate accepted with caveat re Siemens rates. | CORR2599/DS (9/10/09)
5C | 1 | 77 | Amend line of route design section 5C (Add Hedge) | 1 | 1 | 57692 | 5369 |  | 5369 |  |  |  |  | 122 | [7 empty] | Await a response to tie letter 29/4/09
7A | 1 | 78 | Alterations to design of Edinburgh Airport |  |  |  |  | 48620 | [6 empty] | Validated
1D | 1 | 79 | Haymarket Junction Re-Design |  |  |  |  | 52168 | [6 empty] | Validated
7A | 1 | 80 | CEC requesting change to finish of Gogarburn Retaining wall |  |  |  |  | 4998 | [6 empty] | Validated
| 1 | 81 | CEC requested using 42 watt pit lamp (Bat Lighting) |  |  |  |  | 11010 | [6 empty] | Validated
| 1 | 82 | Contamination: Fly tipping, oil pollution etc | [8 empty] | 1 | Withdrawn
| 1 | 83 | Roseburn Street Temporary Traffic Lights | [8 empty] | 1 | Withdrawn
7A | 1 | 84 | Burnside Road Diversion | 1 | 1 | 820 | 963 |  | 720 |  |  |  |  | 18
1A | 1 | 85 | Lindsay Road Retaining Walls | 1 | 1 | 1291200 | 1291200 |  | 484065 |  |  |  |  | 125
1 | 1 | 86 | MUDFA Transfer of Utilities Diversions Section 1A, 1B, 1C, 1D | [6 empty] | 1 | Est Outstanding
1B | 1 | 87 | Duct Installation to Leith Walk | 1 | 1 | 300 | 300 |  | 344 |  |  |  |  | 13 | [7 empty] | CO 11 Withdrawn
| 1 | 88 | Power Supplies (tie Notice of Change Number 14) - DUPLICATE INTC 62 |  | 1 |  | 2333611 | [10 empty] | 1 | BSC |  |  |  | Await civils costs
|  | 88A | Power Supply Ducts | 1 | 1 | 13297 | 13297 | [6 empty] | 137
7A |  | 88B | Ingliston park & Ride Sub-station Ductwork |  | 1 |  | 3080 | [10 empty] | 1 | BSC |  |  | refer to tie letter 4092
1B | 1 | 89 | Balfour Street Crossing |  |  |  |  | 9242 |  | 1 | Est Outstanding |  |  |  | Validated | [7 empty] | CORR1194/DS
| 1 | 90 | SDS Development Workshop (Pre-Novation Change) - DELETED | [8 empty] | 1 | Deleted
5B | 1 | 91 | ENT 002 - Edinburgh Park Strucrure (Foundations / sub-structure) | 1 | 1 | 405630.51 | 405631 |  | 52389 |  |  |  |  | 98 | [7 empty] | Await a response to tie e-mail 4/2/2009
5A | 1 | 92 | Re-design Russell Road retaining Wall to avoid clash with exg sewer | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  | Deleted - Refer BSC letter 22/10/08 (ref 25.1.201/JHi/737
| 1 | 93 | Design Estimate - Prior Approvals/Planning Application (SDS) |  | 1 |  | 47637 | [12 empty] | 1 | Disputed | Pre-Novation, await confirmation on BSC position
| 1 | 94 | Hilton Hotel Car Park full planning |  | 1 |  | 11462 | [12 empty] | 1 | Disputed | Pre-Novation, await confirmation on BSC position
| 1 | 95 | Depot Prior Approvals | [8 empty] | 1 | Withdrawn | [8 empty] | BSC confirmed withdrawn - meeting 11/1/10
1D | 1 | 96 | Amendments to Shandwick Place Design |  | 1 |  | 335214 | [7 empty] | Validated |  |  |  |  | 1 | Disputed | BDDI - Planning Drawings
5A | 1 | 97 | Balgreen Road Bridge Technical Design |  |  |  |  | 2988 | [6 empty] | Validated
unall | 1 | 98 | Notified Departure, V32 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 99 | Notified Departure, V33 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 100 | Notified Departure, V34 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 101 | Notified Departure, V35 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
5C | 1 | 102 | Section 5C - Gogar Church & Gogar Castle | [6 empty] | 1 | Est Outstanding
5C | 1 | 103 | Change to IFC Drgs - A8 Underpass |  | 1 |  | 764805 | [10 empty] | 1 | BSC |  |  | Await response to tie letter | INF CORR 2534/GMcG (01/10/09)
5A | 1 | 104 | Change to IFC Drgs - Baird Drive Retaining Wall |  | 1 |  | 1920579 | [12 empty] | 1 | Disputed | Referred to DRP | BSC letter GA/4202
5A | 1 | 105 | Change to IFC Drgs - Balgreen Road Retaining wall | 1 | 1 | 800976 | 800976 |  | 298574 |  |  |  |  | 138 | [7 empty] | Agreed | BSC letter GA/4202
5A | 1 | 106 | Change to IFC Drgs - Murrayfield Stadium Retaining Wall | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
5B | 1 | 107 | Change to IFC Drgs - Bankhead Retaining Wall |  | 1 |  | 718755 | [12 empty] | 1 | Disputed
5C | 1 | 108 | Change to IFC Drgs - Gyle Stop Retaining Wall |  | 1 |  | 230995 | [10 empty] | 1 | BSC |  |  | Await response to tie letter dated 22/1/10 (Ref 3230/MP)
5A | 1 | 109 | Change to IFC Drgs - Murrayfield Underpass |  | 1 |  | 134298.71 | [12 empty] | 1 | Disputed |  | BSC letter 4715
5C | 1 | 110 | Change to IFC Drgs - South Gyle Access Bridge |  | 1 |  | 474483 | [8 empty] | 1 | tie |  |  |  |  | Await response to tie queries (refer e-mail to IL 29/1/10) | BSC letter IO/3975 (09/11/09)
7A | 1 | 111 | Change to IFC Drgs - Gogarburn Bridge (Structure) |  | 1 |  | 313080 | [12 empty] | 1 | Disputed |  | INF CORR 3234/GMcG (21/01/10)
2A | 1 | 112 | Change to IFC Drgs - Haymarket Viaduct | 1 | 1 | 399727.77 | 210564 |  | 96173 |  |  |  |  | 112
5A | 1 | 113 | Change to IFC Drgs - Russell Road Bridge |  | 1 |  | 126346 | [10 empty] | 1 | BSC |  |  | Await response to tie letter dated 21/1/10 (Ref 3238/MP)
2A | 1 | 114 | Change to IFC Drgs - Roseburn Viaduct | [6 empty] | 1 | Est Outstanding
5B | 1 | 115 | Change to IFC Drgs - Carricknowe Bridge |  | 1 |  | 339028 | [12 empty] | 1 | Disputed |  | INF CORR 3233/GMcG (21/01/10)
5A | 1 | 116 | Change to IFC Drgs - Water of Leith Bridge |  | 1 |  | 274726 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4121
5A | 1 | 117 | Demolition to Roseburn Rd retaining wall / units / garages | [6 empty] | 1 | Est Outstanding
1B | 1 | 118 | IFC Drawing Change Catherdral Lane Sub Station | 1 | 1 | 1229.73 | 1230 |  | 1230 |  |  |  |  | 96
1A | 1 | 119 | IFC Drawing change Leith Walk Sub Station | [8 empty] | 1 | withdrawn | [9 empty] | BSC ref 4993
1A | 1 | 120 | IFC Drawings Demolition and Reinforcing of existing building for Leith Walk Sub Station | [6 empty] | 1 | Est Outstanding
| 1 | 121 | UTC associated with delivery of alignment | 2 | 1 | 533640 | 533640 |  | 533640 |  | Part Agreed |  |  | 103, 124 | [7 empty] | Advanced Instruction Issued - Princes St | Await clarification - Siemens
[5 empty] | 1 |  | 5998765 | [8 empty] | 1 | tie
1A | 1 | 122 | Delay in receipt of CEC prior approval Sections 1A1 & 1A2 | [6 empty] | 1 | Est Outstanding
1A | 1 | 123 | Forth Ports Agreement & Design Completion |  |  |  |  | 55842 | [6 empty] | Validated
| 1 | 124 | Requirement of Principal Contractors License - NR |  | 1 |  | 1021439 | [12 empty] | 1 | Disputed
2A | 1 | 125 | Unforseen ground conditions at Haymarket | 1 | 1 | 113501.77 | 113501.77 |  | 94317.38 |  |  |  |  | 109
1B | 1 | 126 | Revised drawing for OLE poles in Section 1B | [8 empty] | 1 | Withdrawn
1A | 1 | 127 | Split packages for Prior Approvals; Ocean Terminal to Port of Leith |  | 1 |  | 5734 | [12 empty] | 1 | Disputed | Refer tie letter dated 18/12/08
| 1 | 128 | CEC request for change to roads design at Edinburgh Park Station Interchange | [8 empty] | 1 | Withdrawn
1 | 1 | 129 | CEC's request for extension of time for Prior Approvals 1/01a, 1/01b & 1/01C | [6 empty] | 1 | Est Outstanding
7A | 1 | 130 | Delayed issue of IFC Drawings - Ingilston Park and Ride Tram Stop | [6 empty] | 1 | Est Outstanding
1B | 1 | 131 | Section 1B Delay & Disruption | [6 empty] | 1 | Est Outstanding
| 1 | 132 | War Memorial Relocation (Prov Sum) | [8 empty] | 1 | Duplicate
| 1 | 133 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
| 1 | 134 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
| 1 | 135 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
1C | 1 | 136 | Section 1C - Picardy Place | [6 empty] | 1 | Est Outstanding
1A | 1 | 137 | Sections 1A1 & 1A2 - CEC's proposed amendments to tree build outs adjacent to Constitution St. | [8 empty] | 1 | Withdrawn | [9 empty] | BSC letter 4849
5A | 1 | 138 | Redesign Water of Leith Bridge Foundations |  |  |  |  | 33567 |  | 1 | Est Outstanding |  |  |  | Validated
1A | 1 | 139 | Revised Location of OLE poles in section 1A at the request of CEC |  |  |  |  | 4575.43 | 4575 | 1 | Est Outstanding |  |  | 144 | Validated | [6 empty] | Change agreed at 3/5 of original value. | INF CORR 4392
| 1 | 140 | Delay to issue of IFC Submissions | [6 empty] | 1 | Est Outstanding
1D | 1 | 141 | West End Tram Stop | 1 | 1 | 17760.86 | 16636 |  | 16636 |  |  |  |  | 24 | [7 empty] | BSC letter disputes excl of est prep cost | BSC ref2331 (20/04/09)
1 | 1 | 142 | Christmas & Festival Embargo's - conflict of information | [8 empty] | 1 | Withdrawn
5B | 1 | 143 | CEC's intent to adopt private roads between Lochside Crescent & Lochside Ave |  |  |  |  | 40071 |  | 1 | Est Outstanding |  |  |  | Validated | [7 empty] | CORR2360 (17/9/09)
7A | 1 | 144 | Land Drain encountered in pastured areas | [8 empty] | 1 | Withdrawn
5C | 1 | 145 | Additional work arising from CEC's additional comments on Section 5C technical approvals |  |  |  |  | 18246
5A | 1 | 146 | IFC Drawings for Russell Road Retaining Wall 4 | 1 | 1 | 2721125 | 2721125 |  | 1461857 |  |  |  |  | 132
|  | 146 | IFC Drawings for Russell Road Retaining Wall 4 (Contamination) |  | 1 |  | 1876222 | [10 empty] | 1 | BSC |  |  | Await revised Estimate
5A |  | 146B | IFC Drawings for Russell Road Retaining Wall 3 |  | 1 |  | 440513 | [8 empty] | 1 | tie | [5 empty] | BSC letter 4777 & 4856
5A | 1 | 147 | IFC Drawings for Murrayfield Training Pitches |  | 1 |  | 1342200 | [10 empty] | 1 | BSC |  |  | BSC to revise est based on closure of shunt line | BSC letter 4762 (23/2/10)
5A | 1 | 148 | IFC Drawings for Balgreen Road Tram Bridge | [6 empty] | 1 | Est Outstanding
7A | 1 | 149 | Relocation of Spoil in Section 7 (Assume RBS Bund) |  | 1 |  | 99481.77 | [12 empty] | 1 | Disputed |  | INF CORR 3225
| 1 | 150 | IFC Drawings - Roseburn Street Viaduct | [8 empty] | 1 | Withdrawn
| 1 | 151 | Excavate and replace existing BO material within existing utility trenches | [8 empty] | 1 | By MUDFA | [8 empty] | Based Date Design Issue
| 1 | 152 | IFC Drawings - Vertical & Horizontal track alignment sheets for Section 5 |  | 1 |  | 39845 | [8 empty] | 1 | tie | [5 empty] | BSC letter GA/4862
5 | 1 | 153 | IFC Drawings - Soft Landscaping sheets for section 5 | [6 empty] | 1 | Est Outstanding
5 | 1 | 154 | IFC Drawings - OLE sheets for section 5 | [6 empty] | 1 | Est Outstanding
7A |  | 155 | IFC Drawings for Gogarburn Retaining Walls 15A, 15C & 14D |  | 1 |  | 1005432 | [10 empty] | 1 | BSC |  |  | Await revised Estimate | INF CORR 4074/GmcG (12/02/10)
7A | 1 | 155 | IFC Drawings for Gogarburn Retaining Walls 15A, 15C & 14D | 1 | 1 | 141188 | 141188 |  | 141188 |  |  |  |  | 127 | [8 empty] | BSC ref 4867 03/03/2010
5 | 1 | 156 | IFC Drawings for Section 5 Tramstops - Balgreen, Saughton, South Gyle & Edinburgh Park | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
7A | 1 | 157 | Survey of Existing Drainage (Gogar Landfill) | 1 | 1 | 4333.74 | 4334 |  | 3463 |  |  |  |  | 50
2A | 1 | 158 | Provisional Sum - Crew Facilities at Haymarket Station Viaduct |  | 1 |  | 140401 | [8 empty] | 1 | tie |  |  |  |  | Further sub-contractor quote awaited
| 1 | 159 | Provisional Sum - Relocation of Ancient Monuments | 1 | 1 | 3992.6 | 3993 |  | 3993 |  |  |  |  | 87
| 1 | 160 | IFC Drawings for Edinburgh Park Bridge |  | 1 |  | 320010 | [12 empty] | 1 | Disputed | Await a response to tie letter 14/5/09
| 1 | 161 | Traffic Management - Temporary traffic signals | [8 empty] | 1 | Withdrawn
| 1 | 162 | Bus Tracker, TPDS & Radio | [8 empty] | 1 | Not required | [8 empty] | Not required (Refer tie letter)
2A | 1 | 163 | Haymarket Taxi Stance |  |  |  |  | 26662 |  | 1 | Est Outstanding |  |  |  | Validated
unall | 1 | 164 | Delayed Listed Building Consent Applications | [6 empty] | 1 | Est Outstanding
unall | 1 | 165 | Delay to issue of IFC Submissions | [6 empty] | 1 | Est Outstanding
1A | 1 | 166 | Demolition of Garage Building - Ocean Drive | 1 | 1 | 17023 | 17023 |  | 19560.5 |  |  |  |  | 8
5A | 1 | 167 | Alterations to Murrayfield Wanderers Clubhouse | 1 | 1 | 174206.7 | 174207 |  | 191060.84 |  |  |  |  | 56
1A | 1 | 168 | Demolition of Building 33 Ocean Drive | 1 | 1 | 5870 | 5858 |  | 6745 |  |  |  |  | 16
1A | 1 | 169 | Demolition of Police Box Coffee Bar - Picardy Place | 1 | 1 | 12172 | 12172 |  | 10615.92 |  |  |  |  | 48 | [7 empty] | Removal Palozzi's stones by others
1A | 1 | 170 | Demolition of Cathedral Lane Toilet Block | 1 | 1 | 2802 | 2802 |  | 2802 |  |  |  |  | 88
| 1 | 171 | Contract with Faber Maunsell for Transyt & Linsig Modelling Assessments | 1 | 1 | 66769 | 64809 |  | 64809 |  |  |  |  | 73
| 1 | 172 | Traffic Modelling - Pedestrian Crossing Timing Standards |  |  |  |  | 43290 | [6 empty] | Validated
5A | 1 | 173 | Discovery of underground petrol tank at NCR site | 1 | 1 | 6080.3 | 6080 |  | 5530.9 |  |  |  |  | 26
| 1 | 174 | Discovery of new BT ducts under kerb line in Section 1B | [18 empty] | Estimate Incl 234
1B | 1 | 175 | SDS Prov Sums - Extended Construction support and design team support | [8 empty] | 1 | Withdrawn
5C | 1 | 176 | Various Works to Section 5c - Gogar Church & Gogar Castle | 1 | 1 | 6642.7 | 6643 |  | 6643 |  |  |  |  | 22
| 1 | 177 | Harbour Trackwork | [8 empty] | 1 | Withdrawn
unall | 1 | 178 | Prov Sum: Mandatory tie Change (Missed Trigger Dates) | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
5A | 1 | 179 | Gatehouse works to Murrayfield Stadium | 1 | 1 | 108663.68 | 108664 |  | 108664 |  |  |  |  | 85 | Validated
5A | 1 | 179 | Gatehouse works to Murrayfield Stadium | 1 | 1 | 34830.23 | 34830 |  | 34830 |  |  |  |  | 86 | Validated
5A | 1 | 180 | Reduced land available at Murrayfield | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
| 1 | 181 | CEC requested additional Temp Traffic Light |  | 1 |  | 176950 | [12 empty] | 1 | Disputed
7A | 1 | 182 | Edinburgh Tramstop Kiosk |  |  |  |  | 13621 | [6 empty] | Validated | [7 empty] | 25.1.201/Boc/2203 (08/04/09)
1B | 1 | 183 | Temporary Lining to Leith Walk | [8 empty] | 1 | Withdrawn
1B | 1 | 184 | Leith Walk Utilities | 1 | 1 | 265.38 | 265 |  | 192.37 |  |  |  |  | 47
1B | 1 | 185 | Leith Walk Utilities | [18 empty] | Estimate Incl 234
1C | 1 | 186 | Specification Requirements to additional bus shelters at George St | [8 empty] | 1 | Withdrawn
6A | 1 | 187 | Additional Excavated material at Depot | 1 | 1 | 2318599 | 1425174 |  | 1657395.56 |  |  |  |  | 28
5B | 1 | 188 | Contaminated Material at Carrickknowne |  | 1 |  | 130426 |  |  |  |  | 1 | By Others | [8 empty] | Order placed with Frontline
5B |  | 188A | Contaminated Material at Carrickknowne |  | 1 |  | 14488 | [10 empty] | 1 | BSC |  | Disputed |  | INF CORR 4134
1B | 1 | 189 | Leith Walk Utilities | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
1B | 1 | 190 | Leith Walk Utilities | [18 empty] | Estimate Incl 234
1B | 1 | 191 | Leith Walk Utilities | 1 | 1 | 179 | 179 |  | 179 |  |  |  |  | 110
1B | 1 | 192 | Leith Walk Utilities | 1 | 1 | 161 | 161 |  | 187.35 |  |  |  |  | 14
1B | 1 | 193 | Leith Walk Utilities | 1 | 1 | 619.71 | 620 |  | 449.22 |  |  |  |  | 46
1B | 1 | 194 | Leith Walk Utilities | [18 empty] | Estimate Incl 234
1B | 1 | 195 | Leith Walk Utilities | 1 | 1 | 1041.08 | 1041 |  | 702.51 |  |  |  |  | 45
1C | 1 | 196 | Little King Street Works (Design Only, Construction within Picardy Place Prov) |  |  |  |  | 10768 |  | 1 | Est Outstanding |  |  |  | Validated
5C | 1 | 197 | Cyclepath near gyle tramstop |  |  |  |  | 12146 |  | 1 | Est Outstanding |  |  |  | Validated
5C | 1 | 198 | Gogar Roundabout Lighting |  | 1 |  | 1750.51 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4350
5A | 1 | 199 | IFC Drawings - Balgreen Bridges S22A/S22B | [6 empty] | 1 | Est Outstanding
5B | 1 | 200 | IFC Drawings - Saughton Bridge | [6 empty] | 1 | Est Outstanding
6A | 1 | 201 | IFC Drawings - Depot Access Bridge |  | 1 |  | 2478205.05 | [12 empty] | 1 | Disputed | Await a response to tie letter | INF CORR 3150/GMcG (12/01/10)
7A | 1 | 202 | IFC Drawings - Culverts S30, S31 & S34 | 1 | 1 | 47429.45 | 47429 |  | 13368 |  |  |  |  | 90
6A | 1 | 203a | IFC Drawings - Depot Founds | 1 | 1 | 52066.87 | 52067 |  | 47182 |  |  |  |  | 78
6A | 1 | 203b | IFC Drawings - Depot Steel | 1 | 1 | 294617.68 | 294618 |  | 270372 |  |  |  |  | 79
6A | 1 | 203c | IFC Drawings - External Hard landscaping |  | 1 |  | 214092 | [10 empty] | 1 | BSC |  |  | Issue of different drawings to be resolved. | 25.1.201.GC.3918 (29/10/09)
6A | 1 | 203d | IFC Drawings - Changes to sub-station | [8 empty] | 1 | Withdrawn
6A | 1 | 203e | IFC Drawings - 1800 Dia M/H | [8 empty] | 1 | Withdrawn
6A | 1 | 203f | IFC Drawings - Soil Nailing |  | 1 |  | 497194 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 3204/AS
6A | 1 | 203g | IFC Drawings - Secondary Steelwork | 1 | 1 | 72936.43 | 72936 |  | 2356 |  |  |  |  | 93 | [7 empty] | tie re-measure returned to BSC
6A | 1 | 203h | IFC Drawings - Drainage |  | 1 |  | 103265 | [10 empty] | 1 | BSC |  |  | Await revised Estimate | INF CORR 2923/GMcG (27/11/09)
6A | 1 | 203i | [9 empty] | 1 | Not Issued
6A | 1 | 203j | IFC Drawings - Access Road | 1 | 1 | 78674.86 | 78675 |  | 78675 |  |  |  |  | 114
6A |  | 203K1 | IFC Drawings - Depot (Introduction of piling to OLE bases) |  | 1 |  | 390629 | [12 empty] | 1 | Disputed |  | INF CORR 3279 / MP
6A |  | 203K2 | IFC Drawings - Depot (Increase in number of OLE bases) |  | 1 |  | 69245 | [12 empty] | 1 | Disputed |  | INF CORR 3278 / MP
6A |  | 203M | Gogar depot gas connections |  | 1 |  | 97473.16 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4349/MP
6A |  | 203L1 | IFC Issue of Drawings for Reinforcement to Pit Walls | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 4170/GMcG (22/02/10)
6A |  | 203L2 | IFC Issue of Drawings for Edge Beam Reinforcement Changes | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 4172/GMcG (22/02/10)
6A |  | 203L3 | IFC Issue of Drawings for Introdcution of Waterproof Concrete | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 4173/GMcG (22/02/10)
6A |  | 203P | Section 6 - Alteration to Scottish Water Valve Chambers | 1 | 1 | 18272 | 18272.21 |  | 5366 |  |  |  |  | 140 | [8 empty] | 25.1.201/SW/4546 (03/02/10)
6A |  | 203Q | Section 6 - IFC Drawings for Earthing and Bonding | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 3259/GMcG (22/02/10)
6A |  | 203R | Section 6 - IFC Issue of Drawings for Siemens Additional Containment | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 3205/GMcG (25/01/10)
6A |  | 203S | Section 6 - Change to Kaba Doors |  | 1 |  | 152505.19 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4320 / GMcG
6A |  | 203T | Section 6 - Change to Sub-station slab | [6 empty] | 1 | Est Outstanding | [11 empty] | 25.1.201/SW/4705
6A |  | 203U | Section 6 - Smoke vents | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
6A |  | 203V | Section 6 - Change to Drainage Rev 6 | [6 empty] | 1 | Est Outstanding | [11 empty] | 25.1.201/SW/4704 (18/02/10)
6A |  | 203W | Section 6 - Change to Blockwork Reinforcement | [6 empty] | 1 | Est Outstanding | [11 empty] | 25.1.201/SW/4703 (18/02/10)
5B | 1 | 204 | IFC Drawings - Section 5B Highways |  | 1 |  | 766200 | [8 empty] | 1 | tie |  |  |  |  | tie to respond and agree bulk fill/lighting rates locally. Tie to consider next steps re Des Dev issue. | BSC letter IL/3623 (29/09/09)
5C | 1 | 205 | IFC Drawings - Section 5C Highways |  | 1 |  | 578005 | [8 empty] | 1 | tie |  |  |  |  | tie to respond and agree bulk fill/lighting rates locally. Tie to consider next steps re Des Dev issue. | BSC letter IL/3624 (29/09/09)
5B | 1 | 206 | IFC Drawings - Section 5B Bankhead Tramstop | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
7A | 1 | 207 | Trial Investigations Culvert No.2 (SGN Main Protection) | 1 | 1 | 1083.46 | 1262 |  | 1259.91 |  |  |  |  | 30 | [7 empty] | INTC 295 / 207 included in same CO
1B | 1 | 208 | Christmas Embargo Leith Walk |  | 1 |  | 233356 | [10 empty] | 1 | BSC |  |  | Await response to tie e-mail 18/12/09 to Donna McGregor
1A | 1 | 209 | IFC Drawings - Balfour Street / MacDonald Road Tramstops | [6 empty] | 1 | Est Outstanding
1B | 1 | 210 | IFC Drawings - Roads, St Lighting, Landscping, Drainage, section 1B | [6 empty] | 1 | Est Outstanding
2 | 1 | 211 | IFC Drawings - Haymarket Tramstop, Section 2 | [6 empty] | 1 | Est Outstanding
2A | 1 | 212 | IFC Drawings - Roads, St Lighting, Landscping, Drainage, section 2A |  | 1 |  | 408024.76 | [8 empty] | 1 | tie |  |  |  |  | tie to conduct an audit | CORR4167 (22/02/10)
1D | 1 | 213 | IFC Drawings - Haymarket Terrace Substation | [6 empty] | 1 | Est Outstanding
1C | 1 | 214 | Princes St Construction Works | [8 empty] | 1 | Included PSSA
1B | 1 | 215 | Demolition and Alteration at Leith Walk Bus Depot |  | 1 |  | 251679 | [8 empty] | 1 | tie |  |  |  |  | tie await cec proposal
1B | 1 | 216 | Leith Walk Utilities | 1 | 1 | 853.73 | 854 |  | 618.85 |  |  |  |  | 31
1B | 1 | 217 | Leith Walk Utilities | [6 empty] | 1 | Est Outstanding
1B | 1 | 218 | Leith Walk Utilities | 1 | 1 | 425.24 | 425 |  | 294.57 |  |  |  |  | 32
1B | 1 | 219 | Leith Walk Utilities | [6 empty] | 1 | Est Outstanding
1B | 1 | 220 | Leith Walk Utilities | 1 | 1 | 126.73 | 127 |  | 91.87 |  |  |  |  | 33
1B | 1 | 221 | Leith Walk Utilities | [8 empty] | 1 | Withdrawn
1B | 1 | 222 | Leith Walk Utilities | 1 | 1 | 1166.07 | 1166 |  | 617 |  |  |  |  | 66
1B | 1 | 223 | Stone Culvert Section 1B | 1 | 1 | 1770.37 | 1770 |  | 1169.22 |  |  |  |  | 34
1B | 1 | 224 | Scottish Power Cable Section 1B | [8 empty] | 1 | Withdrawn
1B | 1 | 225 | Repairs to footpath to allow pedestrian access Section 1B | 1 | 1 | 474 | 474 |  | 329.17 |  |  |  |  | 35
2A | 1 | 226 | Operational design review of Haymarket | [6 empty] | 1 | Est Outstanding
6A | 1 | 227 | Operational design review of Depot b |  |  |  |  | 31011 |  | 1 | Est Outstanding | [10 empty] | Change not accepted by tie | BSC 4448 (21/1/10)
unall | 1 | 228 | Relocation of Busstop outwith LOD |  | 1 |  | 1929 | [10 empty] | 1 | BSC |  |  | Await response to tie letter ref: TBC Sba | INF CORR 4136/SB
unall | 1 | 229 | [9 empty] | 1 | Not issued
1A | 1 | 230 | IFC Drawings - Tower Bridge |  | 1 |  | 595358 | [12 empty] | 1 | Disputed | Await a response to tie letter ?
1C | 1 | 231 | IFC Drawings - Section 1C Drainage | [6 empty] | 1 | Est Outstanding
1C | 1 | 232 | IFC Drawings - Section 1C Roads | [6 empty] | 1 | Est Outstanding
1C | 1 | 233 | IFC Drawings - Section 1C Lighting | [6 empty] | 1 | Est Outstanding
1B | 1 | 234 | Leith Walk Utilities | 1 | 1 | 9052.59 | 9052.59 |  | 6562 |  |  |  |  | 89 | [7 empty] | Await response to tie letter dated 12/6
1B | 1 | 235 | Leith Walk Utilities | [18 empty] | Estimate Incl 234
7A | 1 | 236 | Outfall at the airport | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 1235/DS (14/04/09)
2A | 1 | 237 | Move Site Boundary at Haymarket Station | 1 | 1 | 849.53 | 849 |  | 987.96 |  |  |  |  | 10
1B | 1 | 238 | Temporary Traffic Lights opposite Manderson Street (Incomplete MUDFA) | 1 | 1 | 14437 | 14078 |  | 14437 |  |  |  |  | 67 | [7 empty] | Letter to BSC deleting 18.5% Oncost 12/6/09
1B | 1 | 239 | Additional Trial Holes at Ch 145 - 160 (Section 1B) | [6 empty] | 1 | Est Outstanding | [10 empty] | INTC withdrawn by G Conway.
| 1 | 240 | Removal and reinstatement of BT Phone Box |  | 1 |  | 11405 | [10 empty] | 1 | BSC |  |  | Await response to tie letter | INF CORR 4030
| 1 | 241 | MUDFA Delay at Bankhead Drive | [6 empty] | 1 | Est Outstanding
| 1 | 242 | TRO Presentations by SDS at Public Meetings | 1 | 1 | 25000 | 23480 |  | 23480 |  |  |  |  | 111
1A | 1 | 243 | Forth Ports Substation | 1 | 1 | 8537.93 | 8270 |  | 7824 |  |  |  |  | 69
| 1 | 244 | Building Fixing Owner Agreements |  |  |  |  | 17750 | [6 empty] | Validated
5a | 1 | 245 | Major Event - Murrayfield - 17 June 2009 | [8 empty] | 1 | Withdrawn
| 1 | 246 | Notified Departure, V36 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
| 1 | 247 | Notified Departure, V37 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
| 1 | 248 | Notified Departure, V38 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
| 1 | 249 | Notified Departure, V39 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
1B | 1 | 250 | Closure / additional works - Leith walk |  | 1 |  | 61627 | [10 empty] | 1 | BSC |  |  |  | INF CORR 2771
1C | 1 | 251 | IFC Drawings - Section 1C OLE Layout | [6 empty] | 1 | Est Outstanding
1C | 1 | 252 | IFC Drawings - Section 1C Track Horizontal Alignment | [6 empty] | 1 | Est Outstanding
1C | 1 | 253 | IFC Drawings - Section 1C Track Vertical Alignment | [6 empty] | 1 | Est Outstanding | [11 empty] | refer to tie letter 4013
1C | 1 | 254 | IFC Drawings - Section 1C Traffic Management | [8 empty] | 1 | Withdrawn
1C | 1 | 255 | IFC Drawings - Section 1C, 1D - Princes St Central Reservation | [6 empty] | 1 | Est Outstanding
| 1 | 256 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
1A | 1 | 257 | Forth Ports access to ADM Milling | 1 | 1 | 2071 | 2070.94 |  | 1625 |  |  |  |  | 44
7A | 1 | 258 | Future Proofing on behalf of New Ingilston / Highland Properties |  | 1 |  | 1305393 | [10 empty] | 1 | BSC |  |  | Await design completion then Estimate. | INF CORR 3209/AS (25/01/10)
5B | 1 | 259 | IFC Drawing - Section 5B Cycleway at Edinburgh Park Station | 1 | 1 | 64324.21 | 64324 |  | 52095 |  |  |  |  | 72
1B | 1 | 260 | Relocate existing control box | 1 | 1 | 2062 | 2062 |  | 1274.98 |  |  |  |  | 36
1B | 1 | 261 | IFC Drawings - Balfour St Tram Stop | [6 empty] | 1 | Est Outstanding
5B | 1 | 262 | IFC Drawing Change - Section 5B Track Drainage |  | 1 |  | 1440422 | [8 empty] | 1 | tie |  |  |  |  | tie to respond to BSC letter 4250 | CORR 3283/GCN, 27/1/10
1A | 1 | 263 | IFC Drawings - Victoria Dock Bridge | [6 empty] | 1 | Est Outstanding
1A | 1 | 264 | Section 1A - 4 Groundworks |  | 1 |  | 2084785.64 | [15 empty] | BSC ref 4964 1./03/2010
2A | 1 | 265 | IFC Drawings - 2A access retaining wall (Verity House) |  | 1 |  | 72461.89 | [12 empty] | 1 | Disputed
6A | 1 | 266 | Track Monitoring at Gogar Depot | 1 | 1 | 13556.22 | 5369 |  | 5369.02 |  |  |  |  | 25
5C | 1 | 267 | Scottish Water Diversion - Gogar Roundabout |  | 1 |  | 96606.36 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4900 08/03/2010
5C | 1 | 268 | Scottish Power Diversion - Gogar Roundabout | 1 | 1 | 87478 | 87478 |  | 70163 |  |  |  |  | 133 | [7 empty] | Meeting arranged 5/1/09 | 25.1.201.CF.4221 (11/12/09)
| 1 | 269 | Instructions arising from Trackform Development Workshop | 1 | 1 | 383068.36 | 383068 |  | 371058 |  |  |  |  | 20
| 1 | 270 | RBS Tramstop,Diversion of LV Power/Water |  | 1 |  | 17353.36 | [10 empty] | 1 | BSC |  |  | BSC await design Estimate SDS | INF CORR 2855/GMcG (24/11/09)
| 1 | 271 | Road Construction Details - Construction Methodology | 1 | 1 | 426451 | 426451 |  | 372540 |  |  |  |  | 19
5B | 1 | 272 | Unsuitable Material Carrick Knowe | 1 | 1 | 109808 | 83028 |  | 96557.69 |  |  |  |  | 11 | [8 empty] | tie letter 4072
7A | 1 | 273 | Gogarburn Retaining Wall W14 - Redesign | 1 | 1 | 1157 | 1157 |  | 1157 |  |  |  |  | 65
1D | 1 | 274 | Princes St Construction Works - Closure to Traffic during Construction Works | 1 | 1 | 8001.96 | 8002 |  | 7522.4 |  |  |  |  | 21
7A | 1 | 275 | EAL Tramstop - BAA Interface |  |  |  |  | 6824 |  | 1 | Est Outstanding |  |  |  | Validated
1 | 1 | 276 | OLE Design Changes in Area between Haymarket and Newhaven | [8 empty] | 1 | Withdrawn
7A | 1 | 277 | Airport Canopy tie in options |  |  |  |  | 50428 |  | 1 | Est Outstanding |  |  |  | Validated
unall | 1 | 278 | Wider Area Modelling Proposals | [6 empty] | 1 | Est Outstanding
| 1 | 279 | West Pilton Tramstop |  |  |  |  | 859 | [6 empty] | Validated | [6 empty] | Meeting 28/5/09 - INTC withdrawn
1B | 1 | 280 | Change to demarcation requirements (Duplicate INTC 320) | [8 empty] | 1 | Duplicate | [8 empty] | Duplicate INTC 320
1B | 1 | 281 | Revised Proposals for Cathedral Lane Substation |  |  |  |  | 139907 | [14 empty] | BSC ref 4876 03/03/2010 and 4249 05/03/2010
6A | 1 | 282 | Japanese Knotweed at rear of Scotrail Depot | 1 | 1 | 24283 | 24283 |  | 24283 |  |  |  |  | 128 | [7 empty] | Change Order 282
5B | 1 | 283 | Edinburgh Park Bridge (S27) - Pier 3 Base Formation |  | 1 |  | 10675 | [14 empty] | Await signed time sheets | Tie e-mail 25/11/09 (MP to GA)
5A | 1 | 284 | Russell Road Retaining Wall - Options Report | [6 empty] | 1 | Est Outstanding
unall | 1 | 285 | Notified Departure, V40 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
1C | 1 | 286 | Princes Street Construction Works - Full Depth Reconstruction | [8 empty] | 1 | Withdrawn
1A | 1 | 287 | Forth Ports Traffic Signal - Section 1A4 - Widened Crossing Required |  |  |  |  | 9577 |  | 1 | Est Outstanding |  |  |  | Validated | [6 empty] | BSC to provide further info on what problem is
unall | 1 | 288 | Deviation Road Rail Vehicle Payload | [6 empty] | 1 | Est Outstanding
1A | 1 | 289 | Cycleway change at Hawthornevale - Section 1A4 |  |  |  |  | 41557.25 |  | 1 | Est Outstanding | [10 empty] | tie respond to estimate | BSC 4825 (26/2/10)
unall | 1 | 290 | CAF - Air Supply | [6 empty] | 1 | Est Outstanding
unall | 1 | 291 | CAF - Lifting System | [6 empty] | 1 | Est Outstanding
5 | 1 | 292 | Additional Ramp / Steps at Lindsay Road Retaining Wall |  |  |  |  | 33274 | [14 empty] | BSC 4845 (2/3/10)
7A | 1 | 293 | Gogar Castle Road tree felling | 1 | 1 | 1453 | 1453 |  | 1335.51 |  |  |  |  | 37
6A | 1 | 294 | Reinstate access ramp at Gogar Depot | 1 | 1 | 10972 | 10972 |  | 9880.34 |  |  |  |  | 38
7A | 1 | 295 | Carry out works to protect existing SGN gas main at Culvert No, 2 | 1 | 1 | 17380 | 17380 |  | 15170.06 |  |  |  |  | 30
7A | 1 | 296 | Formation Level of Gogarburn Bridge West Abutment | 1 | 1 | 18743 | 18743 |  | 13439.93 |  |  |  |  | 39
7A | 1 | 297 | Formation Level of Gogarburn Bridge East Abutment | 1 | 1 | 10994 | 10994 |  | 8466.27 |  |  |  |  | 40
| 1 | 298 | Revised Access arrangement to Depot | [8 empty] | 1 | Withdrawn
5B | 1 | 299 | IFC Drawing Changes - Edinburgh Park Bridge (Piers, Bearings) | [8 empty] | 1 | Withdrawn
| 1 | 300 | Network Rail requirement for CAT 3 checking | [6 empty] | 1 | Est Outstanding
1D | 1 | 301 | Diversionary route from Princes Street to George Street / Queen Street |  | 1 |  | 138040 | [10 empty] | 1 | BSC |  |  | Await further information | Tie e-mail 18/12/09, 20/8/09
5B | 1 | 302 | Protection of live utilities at Russell Road Bridge during construction | [6 empty] | 1 | Est Outstanding
unall | 1 | 303 | Change to interior tram layout | 1 | 1 | 335635 | 335635 |  | 335635 |  |  |  |  | 29
1C |  | 304 | Provisional Sum for Extra Over for Shell Grip at Junctions |  | 1 |  | 887621 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4966 09/03/2010
1C | 1 | 304 | Provisional Sum for Extra Over for Shell Grip at Junctions | 1 | 1 | 156259 | 156259 |  | 156259 |  | Part Agreed |  |  | 104 | [7 empty] | Await response to tie re-measure
unall | 1 | 305 | Crawley Tunnel - Insufficient ground cover | [6 empty] | 1 | Est Outstanding
1B | 1 | 306 | Discovery of Underground structure on Leith Walk | [6 empty] | 1 | Est Outstanding
2A | 1 | 307 | Contaminated Soil at Haymarket Depot | 1 | 1 | 60449 | 54987 |  | 54987 |  |  |  |  | 76
5C | 1 | 308 | Additional excavation at Carrick Knowe South Abutment | [8 empty] | 1 | Withdrawn
5B | 1 | 309 | Edinburgh Park Bridge South Abutment Base Formation | 1 | 1 | 20222 | 20222 |  | 9408 |  |  |  |  | 123
6A | 1 | 310 | Gogar Landfill Scottish Water Utility Diversion |  |  |  |  | 23195 |  | 1 | Est Outstanding | [10 empty] | On hold pending design review of landfill area. | INF CORR 2924 (25/11/09)
1A | 1 | 311 | IFC Drawings - Section 1A | [6 empty] | 1 | Est Outstanding
1B | 1 | 312 | IFC Drawings - Leith Walk | [6 empty] | 1 | Est Outstanding
7 | 1 | 313 | IFC Drawings - Section 7, Soft Landscaping | [6 empty] | 1 | Est Outstanding | [10 empty] | Estimated awaited. | INF CORR 2528/GMcG (12/10/09)
unall | 1 | 314 | IFC Drawings - Horizontal / Vertical Alignment |  | 1 |  | 345593 | [10 empty] | 1 | BSC |  |  | Await response to tie letter | INF CORR 2611/GMcG(11/11/09)
7A | 1 | 315 | IFC Drawings - Section 7 Drainage - Gogarburn |  | 1 |  | 1350078 | [6 empty] | 117 | [7 empty] | Await response to tie letter | BSC Letter OH/4437
1D | 1 | 316 | IFC Drawings - Princes Street, section 1D | [6 empty] | 1 | Est Outstanding
unall | 1 | 317 | Earthwork quantity variances between IFC Trackwork drawings and IFC MX Data | [6 empty] | 1 | Est Outstanding
6 | 1 | 318 | IFC Drawings - Gogarburn Retaining Walls 14 & 15 | [8 empty] | 1 | Withdrawn
1D | 1 | 319 | Shandwick Place TRO Signage |  |  |  |  | 8386 |  | 1 | Est Outstanding | [10 empty] | Await a response to tie letter 4/5/09 (Ref 1380)
unall | 1 | 320 | Proposed CEC Changes to demarcation requirements |  |  |  |  | 26881 |  | 1 | Est Outstanding
1C | 1 | 321 | Revised Alignment to Picardy Place, York Place & London Road Junctions |  |  |  |  | 298291 |  | 1 | Est Outstanding | [10 empty] | Stage 3 &4 to be agreed on basis of ! & 2's findings | corr 2521 (1/10/09) - agrees stage1 &2 design
5C | 1 | 322 | Carrickknowe Underbridge Obstructions |  | 1 |  | 2744 |  | 2744 |  |  |  |  | 145 | [7 empty] | Refer tie letter | BSC ref 4730
5C | 1 | 323 | A8 Underpass Phase 1 Pile Toe Levels |  | 1 |  | 38331 | [12 empty] | 1 | Disputed | Refer tie letter
5C | 1 | 324 | A8 Underpass Phase 1 Piling Obstructions | 1 | 1 | 5127 | 5127 |  | 4613.58 |  |  |  |  | 51
unall | 1 | 325 | Advertising Consents | [8 empty] | 1 | Withdrawn
1A | 1 | 326 | Expose existing gully connections at CH272 - 328 RHS |  | 1 |  | 5111 | [12 empty] | 1 | Disputed | Refer tie letter 1/6/09 (Ref 1563 / CB) | INF CORR 1563
1B | 1 | 327 | Section 1B - Carry out dye test | 1 | 1 | 1015 | 1015 |  | 711.82 |  |  |  |  | 41
1B | 1 | 328 | Section 1B - Reinstate slabbed footway after MUDFA works | 1 | 1 | 2045 | 2045 |  | 1386.54 |  |  |  |  | 42
1B | 1 | 329 | Section 1B - Breakout Foamed Concrete Backfill |  | 1 |  | 7326 | [10 empty] | 1 | BSC |  |  | Await response to tie letter | INF CORR 2419
1B | 1 | 330 | Section 1B - Install additional gully CH250 RHS | 1 | 1 | 3060 | 3060 |  | 2170.14 |  |  |  |  | 49
6 | 1 | 331 | Section 6 - Partial handover fo Depot Site | [6 empty] | 1 | Est Outstanding
7 | 1 | 332 | Section 7 - Path / Cycleway Change | [8 empty] | 1 | Withdrawn
6A | 1 | 333 | Investigate and reinstate existing batters north of Gogar Depot (W/Drawn) | [8 empty] | 1 | Deleted | [8 empty] | Incl INTC 187
7A | 1 | 334 | Access at New Ingilston | 1 | 1 | 8545 | 8545 |  | 5828 |  |  |  |  | 94 | [7 empty] | Await a response to tie letter 21/5/09 (Ref 1480)
5C | 1 | 335 | IFC Drawings - 5C Track Drainage |  | 1 |  | 1189259 | [10 empty] | 1 | BSC |  |  | tie to review changes and respond | INF CORR 4369 11/03/2010
unall | 1 | 336 | Office Extension | 1 | 1 | 150000 | 150000 |  | 150000 |  |  |  |  | 60
1B | 1 | 337 | Section 1B - Testing to carriageway at Leith Walk | 1 | 1 | 14422 | 14422 |  | 15452 |  |  |  |  | 99
1B | 1 | 338 | Section 1B - Removal of Ornamental Iron Balls from Groathill Depot | 1 | 1 | 766 | 766 |  | 354 |  |  |  |  | 57
1B | 1 | 339 | Section 1B - Remove Spoil from Groathill Depot | [8 empty] | 1 | Deleted | [8 empty] | Work carried out by others
5B | 1 | 340 | Section 5B - Edinburgh Park bridge South Abutment Base - Existing Service | 1 | 1 | 677 | 677 |  | 609.69 |  |  |  |  | 52
1D | 1 | 341 | Princes Street - Reinforced Concrete Slab above Track Box | [8 empty] | 1 | S/S | [8 empty] | Works covered out under Princes St Agreement
5C | 1 | 342 | Section 5C - Edinburgh Park Private Utilities | [8 empty] | 1 | By Others | [9 empty] | BSC ref 4788
6A | 1 | 343 | Section 6A - Street Lighting |  |  |  |  | 2049 |  | 1 | Est Outstanding | 1 | Validated
6A | 1 | 344 | Disposal of Surplus excavated material at Depot (Refer INTC 187) | [8 empty] | 1 | Deleted | [8 empty] | Works incl INTC 187
unall | 1 | 345 | MUDFA use of Hippo Wheelwash | [8 empty] | 1 | Withdrawn
5C | 1 | 346 | Edinburgh Park Bridge Structural Fill |  | 1 |  | 106527 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 1831)
1D | 1 | 347 | Section 1D - Traffic Flow and Remodel at Lothian Road Junction | [8 empty] | 1 | Withdrawn
1D | 1 | 348 | Section 1D - Additional signs on Queen Street |  | 1 |  | 289 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 2172 | INF CORR 2172
1C | 1 | 349 | Section 1C / 1D - TM Contingency for Emergency Utility Works | 1 | 1 | 405 | 378 |  | 405 |  |  |  |  | 61
unall | 1 | 350 | Protected Species Mitigation Measures | 1 | 1 | 9870 | 9870 |  | 9262 |  |  |  |  | 64
1C | 1 | 351 | Section 1C / 1D - Reversal of One Way System to Rose Street | [8 empty] | 1 | Withdrawn
1D | 1 | 352 | Off peak taxi rank at George Street | 1 | 1 | 2591 | 2591 |  | 2213 |  |  |  |  | 69
1D | 1 | 353 | Section 1C / 1D - Additional Measures at George Street |  | 1 |  | 5241 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 2263 | INF CORR 2263
1D | 1 | 354 | Section 1C / 1D - Provide Corex Signs and Double Yellow Lines on George Street |  | 1 |  | 3332 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 2263 | INF CORR 2263
1D | 1 | 355 | Section 1C / 1D - Additional Signage at George Street / St Andrews Square |  | 1 |  | 3215 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 3126 | INF CORR 3126 & CB email 8/1/10
1C | 1 | 356 | Section 1C / 1D - Replace MASS Barriers at George St., Hanover St & Frederick St. |  | 1 |  | 2536 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 3126 | INF CORR 3126 & CB email 8/1/10
1C | 1 | 357 | Section 1C / 1D - Trial Holes at Princes Street | [6 empty] | 1 | Est Outstanding
1C | 1 | 358 | Section 1C - Incomplete MUDFA Works at Princes Street | [6 empty] | 1 | Est Outstanding
1D | 1 | 359 | Haymarket Junction - Underground Chamber at Clifton Terrace | [6 empty] | 1 | Est Outstanding
1A | 1 | 360 | Alteration of Design at Forth Ports Road 8 | 1 | 1 | 3264 | 3264 |  | 2817 |  |  |  |  | 54
5A | 1 | 361 | Diversion - SP Murrayfield Underpass | 1 | 1 | 9622 | 9622 |  | 7473 |  |  |  |  | 55
5B | 1 | 362 | Edinburgh Park Bridge - North and South Approach ramps additional Earthworks | 1 | 1 | 364663.87 | 225719 |  | 185000 |  |  |  |  | 106 | [7 empty] | Await response to tie revised breakdown
1D | 1 | 363 | Provide Wider Area Signage to Princes Street |  | 1 |  | 12948 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 3126 | INF CORR 3126 & CB email 8/1/10
2A | 1 | 364 | Manhole at Balbirnie Place | 1 | 1 | 1498 | 1498 |  | 1498 |  |  |  |  | 70
unall | 1 | 365 | Wider Area Fly P&R Survey | [8 empty] | 1 | Withdrawn
7A | 1 | 366 | Water Ingress Gogarburn East Abutment |  | 1 |  | 4096 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter 3/9/09 | INF CORR 2273 / AS
2A | 1 | 367 | Haymarket Rail Station - Network Rail Access Door | 1 | 1 | 2814 | 2814 |  | 2814 |  |  |  |  | 134
5A | 1 | 368 | Demolish all Structures on Plots 97 & 102 near Roseburn Street | [6 empty] | 1 | Est Outstanding
5C | 1 | 369 | Existing Services A8 Underpass Phase 1 | 1 | 1 | 20325 | 20325 |  | 20325 |  |  |  |  | 126
5B | 1 | 370 | Existing Ground Levels at Edinburgh Park Bridge | 1 | 1 | 88297 | 88297 |  | 62851 |  |  |  |  | 113
5C | 1 | 371 | Utility Diversion 5C/BT/D/05 | 1 | 1 | 1898 | 1898 |  | 1898 |  |  |  |  | 43
5A | 1 | 372 | Utility Diversion 5A/SP/D/08 | [8 empty] | 1 | Withdrawn
5C | 1 | 373 | Utility Diversion 5C/TE/D/05 | 1 | 1 | 5542 | 5542 |  | 5542 |  |  |  |  | 45
7 | 1 | 374 | Soil Nailing and Reinforced Earth Gogar Landfill | [8 empty] | 1 | Withdrawn
7 |  | 374b | Gogar Landfill Surcharges and monitoring |  | 1 |  | 458002.38 | [8 empty] | 1 | tie | [5 empty] | BSC 4818
7 |  | 374c | Gogar Landfill Soil Nailing & Reinforced Earth |  | 1 |  | 524034.28 | [8 empty] | 1 | tie | [5 empty] | BSC 4838
1 | 1 | 375 | Revise OLE founds and layout section 1 |  |  |  |  | 73526 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
unall | 1 | 376 | Revise OLE founds and layout - line 2 |  |  |  |  | 85723 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
unall | 1 | 377 | Amend SDS Design documents |  |  |  |  | 7644 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
unall | 1 | 378 | OHLE Building fixing loads and locations |  |  |  |  | 7349 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
unall | 1 | 379 | Combined OLE Lighting Poles |  |  |  |  | 55486 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
unall | 1 | 380 | OHLE Fixings at Depot Access Bridge |  |  |  |  | 23513 |  | 1 | Est Outstanding | [10 empty] | Design- Demonstrable cost
1D | 1 | 381 | Charlotte Square West End - On Parking |  | 1 |  | 2954 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter | INF CORR 3126 & CB email 8/1/10
1D | 1 | 382 | Bus Gate at Shandwick Place |  | 1 |  | 3398 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter | INF CORR 3126 & CB email 8/1/10
1D | 1 | 383 | Princes Street Rhino Barrier | [8 empty] | 1 | Withdrawn (Incl OSSA)
1D | 1 | 384 | Saturn Studs at George Street and Frederick Street |  | 1 |  | 60 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter | INF CORR 3126 & CB email 8/1/10
1D | 1 | 385 | Additional MASS barriers on Great Stuart Street | 1 | 1 | 996.01 | 915 |  | 915 |  |  |  |  | 62
1D | 1 | 386 | Additional Traffic Management Princes Street | [6 empty] | 1 | Est Outstanding
1C | 1 | 387 | Bus Stand St Andrews Square | [8 empty] | 1 | Withdrawn
1D | 1 | 388 | VMS Signs on Princes St Contingency Route | [8 empty] | 1 | Withdrawn
1D | 1 | 389 | Production of As-Built Drawings for Princes Street | [6 empty] | 1 | Est Outstanding | [10 empty] | Refer tie letter 27/5/09 (Ref 1530)
5B | 1 | 390 | Carrick Knowe Subgrade Improvement | 1 | 1 | 110331 | 110331 |  | 98501.39 |  |  |  |  | 53
1B | 1 | 391 | Access to Leith Walk from 19/3/09 | [6 empty] | 1 | Est Outstanding
5B | 1 | 392 | Edinburgh Park Bridge - Pier 1 Base Formation | 1 | 1 | 629 | 629 |  | 561 |  |  |  |  | 59
5B | 1 | 393 | Section 5B - Edinburgh Park Approach Ramp Sub-Grade | [8 empty] | 1 | Withdrawn
unall | 1 | 394 | Notified Departure, V41 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 395 | Notified Departure, V42 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 396 | Notified Departure, V43 Design Delivery Programme | [6 empty] | 1 | Est Outstanding
unall | 1 | 397 | IFC Changes to Series 600 Earthworks Specification | [6 empty] | 1 | Est Outstanding
unall | 1 | 398 | IFC Changes to Series 1700 Concrete Specification | [6 empty] | 1 | Est Outstanding
7A | 1 | 399 | Additional Starter & Capping Layer Section 7A (Provisional) | 1 | 1 | 1651190 | 1651190 |  | 1139305 |  |  |  |  | 141 | [7 empty] | Await response to tie e-mail 21/12/09 (MP to GC) | BSC ref 4973 10/03/2010
2A | 1 | 400 | Bicyle Provision at haymarket Steps |  | 1 |  | 8043 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 2180 | INF CORR 2180
7A | 1 | 401 | Section 7A - Additional West Embankment Starter Layers | 1 | 1 | 43054 | 43054 |  | 36616 |  |  |  |  | 92
5B | 1 | 402 | Section 5B Groundworks - Additional Starter and Capping Layers | 1 | 1 | 2745762 | 2745762 |  | 1048164 |  |  |  |  | 142 | [7 empty] | Await response to tie e-mail 21/12/09 (MP to GC) | BSC ref 4974 09/03/2010
5A | 1 | 403 | Section 5C Groundworks - Additional Starter and Capping Layers | 1 | 1 | 879716 | 879716 |  | 930159 |  |  |  |  | 143 | [7 empty] | Await response to tie e-mail 21/12/09 (MP to GC) | BSC ref 4972 10/03/2010
5C | 1 | 404 | Section 5D - Drainage Ditches |  | 1 |  | -6225 | [12 empty] | 1 | Disputed | BSC refuse to withdraw change (DD issue) | BSC MRH/4309, 06/01/10
1A | 1 | 405 | Additional Retaining wall at Tower Bridge Pumping Station |  | 1 |  | 6757 | [10 empty] | 1 | BSC |  |  | Refer e-mail ES to JA (10/3/10)
6A | 1 | 406 | Gogar Depot Earthworks - North Boundary Drainage Design |  |  |  |  | 7849 |  | 1 | Est Outstanding |  |  |  | Validated
6A | 1 | 407 | Excavate hard material - gogar depot | 1 | 1 | 40670 | 40670 |  | 35807 |  |  |  |  | 97
unall | 1 | 408 | IFC Changes to Ductwork Specification | [6 empty] | 1 | Est Outstanding
1A | 1 | 409 | Ocean Drive | 1 | 1 | 3264 | 3264 |  | 2817 |  |  |  |  | 70a
unall | 1 | 410 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
5 | 1 | 411 | Trackform changes section 5 | [6 empty] | 1 | Est Outstanding
6A | 1 | 412 | Depot Floor - Pit for manual bogie turntable |  |  |  |  | 8914 | [6 empty] | Validated
7A | 1 | 413 | Expose & Protect existing private drain - Section 7 | 1 | 1 | 2697 | 2697 |  | 2697 |  |  |  |  | 84
5A | 1 | 414 | Russell Road Bridge - Soil Nailing | 1 | 1 | 73167 | 73167 |  | 44718 |  |  |  |  | 107 | [7 empty] | Await a response to tie letter 28/8/09
6 | 1 | 415 | Pumping Station at Depot |  | 1 |  | 65023.69 | [10 empty] | 1 | BSC |  |  | Await response from BSC on tie comments. | INF CORR 2856/GMcG (24/11/09)
1C | 1 | 416 | Side Entry Manhole Princes Street 1C2/D/MH/6901 | [8 empty] | 1 | Withdrawn
7A | 1 | 417 | BAA Dual Future Proofing - Eastfield Avenue |  |  |  |  | 46431 |  | 1 | Est Outstanding | [10 empty] | Await BAA Response and Estimate | INF CORR 4090/AS (12/02/10)
| 1 | 418 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
1C | 1 | 419 | Replace MASS Barrier at St Andrews Square | 1 | 1 | 24691 | 24691 |  | 22897 |  |  |  |  | 82
1B | 1 | 420 | Leith Walk Gyratory System |  | 1 |  | 51017 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4131/PD
5B | 1 | 421 | Trackform change on Guided Busway | 1 | 1 | 550000 | 550000 |  | 550000 |  |  |  |  | 81
1B | 1 | 422 | Phase 1b design | [8 empty] | 1 | Withdrawn
6A | 1 | 423 | Section 6 - Remove Soft Material from subgrade of Depot Access Road |  | 1 |  | 36804 | [10 empty] | 1 | BSC |  |  | Await a reponse to tie breakdown | INF CORR 2454/GMcG (25/09/09)
7 | 1 | 424A | IFC Drawing - Section 7 HRL Drawings Road Layout Scheme | [6 empty] | 1 | Est Outstanding | [10 empty] | Await Estimate | INF CORR 4010/GmcG (15/02/10)
7 |  | 424B | Gogar Farm Road Layout | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4869 03/03/2010
7 |  | 424C | Ingliston Park & Ride Tram stop access and Car Park | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4869 03/03/2010
7 |  | 424D | Junction 210 traffic signals (additional civil works) | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4869 03/03/2010
7 |  | 424E | Glasgow Road footway realignment | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4869 03/03/2010
1A | 1 | 425 | Bernard Street Revisions | [8 empty] | 1 | Withdrawn
5A | 1 | 426 | Section 5 - S21E Waterof Leith Bridge | [8 empty] | 1 | Withdrawn
unall | 1 | 427 | Installation of duct banks at various junctions | [8 empty] | 1 | Withdrawn
7 | 1 | 428 | Section 7 - Review of track drainage at Eastfield Ave | 1 | 1 | 1065 | 1065 |  | 1065 |  |  |  |  | 121
unall | 1 | 429 | MUDFA Programme - Revision 08 | [6 empty] | 1 | Est Outstanding
2A | 1 | 430 | Additional white ling at Haymarket Car Park |  | 1 |  | 4394 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4902
5C | 1 | 431 | Section 5C - A8 Underpass existing BT Service | 1 | 1 | 26917 | 26917 |  | 22846.79 |  |  |  |  | 108 | [7 empty] | Await a response to tie letter
1C | 1 | 432 | Section 1C / 1D - Princes Street Contingency Route | [8 empty] | 1 | Withdrawn
2A | 1 | 433 | Section 2A - Traffic Management at VerityHouse Access Road |  | 1 |  | 10841.52 | [10 empty] | 1 | BSC |  |  | Await response to tie email 5/3/2010 | INF CORR 3119 / JO
1C | 1 | 434 | Section 1C - Emergency Road Closure of George Street | 1 | 1 | 1516 | 1516.3 |  | 1516 |  |  |  |  | 129 | [7 empty] | Change Order 129
1C | 1 | 435 | Section 1C - Traffic Management for MUDFA Works |  | 1 |  | 50358.96 | [10 empty] | 1 | BSC |  |  |  | INF CORR ??
1D | 1 | 436 | Section 1C - Pedestrian disruption on Lothian Road | 1 | 1 | 8640 | 8640.25 |  | 8640 |  |  |  |  | 130 | [7 empty] | Change Order 130
5B | 1 | 437 | Section 5B - Carrickknowe works outwiththe LOD | 1 | 1 | 4324 | 4324 |  | 4324 |  |  |  |  | 102
unall | 1 | 438 | Noise and vibration Surveys | 1 | 1 | 146128 | 146128 |  | 146128 |  |  |  |  | 83
unall | 1 | 439 | SDS Proposed office move to Edinburgh Park - IT cost | 1 | 1 | 28000 | 28000 |  | 28000 |  |  |  |  | 77
unall | 1 | 440 | Utility conflicts within 1.2m clearance Zone | [6 empty] | 1 | Est Outstanding
unall | 1 | 441 | Site wide contaminated land and materials (SHEENA) | [6 empty] | 1 | Est Outstanding
5A | 1 | 442 | IFC Drgs - 5A Track Drainage |  | 1 |  | 71938 | [10 empty] | 1 | BSC |  |  |  | tie e-mail (MP to GA 3/3/10)
unall | 1 | 443 | SDS Design Programme Revision 44 | [6 empty] | 1 | Est Outstanding
unall | 1 | 444 | SDS Design Programme Revision 45 | [6 empty] | 1 | Est Outstanding
unall | 1 | 445 | SDS Design Programme Revision 46 | [6 empty] | 1 | Est Outstanding
| 1 | 446 | Roseburn Delta Junction Landscaping | [8 empty] | 1 | Withdrawn
unall | 1 | 447 | Revised OLE location due to Scottish Power Installation | [6 empty] | 1 | Est Outstanding
2A | 1 | 448 | Street lighting Haymarket Terrace |  |  |  |  | 2498.86 |  | 1 | Est Outstanding | [10 empty] | tie accepted design costs
5B | 1 | 449 | Reinstatement of Bus Gate at Edinburgh Park Station | 1 | 1 | 830 | 803 |  | 803 |  |  |  |  | 80
7A | 1 | 450 | BAA New Burnside Road Alignment |  |  |  |  | 8004.92 |  | 1 | Est Outstanding | [10 empty] | Disagree with charge for drawings - await BSC comment. | INF CORR 3184/DC (21/01/10)
unall | 1 | 451 | Stage D drawings for Tramstops |  |  |  |  | 55722 |  | 1 | Est Outstanding | [10 empty] | tie have written to request this change is withdrawn, await response
6 | 1 | 452 | West depot entry / exit turnout |  |  |  |  | 3986 |  | 1 | Est Outstanding
| 1 | 453 | INTC NOT ISSUED | [8 empty] | 1 | Not Issued
1C | 1 | 454 | Section 1 C Lothian Road Junction |  | 1 |  | 1742 | [10 empty] | 1 | BSC |  |  | Await a response to tie letter INF CORR 3264
unall | 1 | 455 | Proposals for treating Giant Hogweed | [8 empty] | 1 | Withdrawn
unall | 1 | 456 | Road construciton - re-use of existing kerbs | [6 empty] | 1 | Est Outstanding
5C | 1 | 457 | Edinburgh Park Bridge - Revision to reinforcement to parapets | [6 empty] | 1 | Est Outstanding
1A | 1 | 458 | Revised Junction Layouts - Section 1A | [6 empty] | 1 | Est Outstanding
unall | 1 | 459 | Informal Consulation TRO Changes - DCR0196 (Estimate not validated) | [6 empty] | 1 | Est Outstanding
unall | 1 | 460 | Informal Consulation TRO Changes - DCR0197 (Estimate not validated) | [6 empty] | 1 | Est Outstanding
1A | 1 | 461 | Forth Ports Substation re-design |  |  |  |  | 13793.91 | [13 empty] | agreed | INF CORR 4399/Sba 15/03/10
unall | 1 | 462 | Network Rail Turning Head Lighting | [6 empty] | 1 | Est Outstanding
1A | 1 | 463 | Forth Ports Drainage Approval |  |  |  |  | 13818.57
7 | 1 | 464 | Gogarburn Retaining Walls W14 and W15 | [6 empty] | 1 | Est Outstanding | [10 empty] | Awaiting further info from BSC / SDS | INF CORR 2351/AS (11/09/09)
7 | 1 | 465 | CCRC Walkway Interface |  |  |  |  | 3829 |  | 1 | Est Outstanding
unall | 1 | 466 | Change to TRO Drawings | [8 empty] | 1 | Withdrawn
6 | 1 | 467 | BAA Drainage at depot | [6 empty] | 1 | Est Outstanding | [10 empty] | Currently being designed - may come within 203H1. | INF CORR 2169/AS (02/09/09)
| 1 | 468 | Underground Chamber - West Maitland Street | [6 empty] | 1 | Est Outstanding
1A | 1 | 469 | Utility Diversions - Lindsay Road | [6 empty] | 1 | Est Outstanding
1A | 1 | 470 | Re-location of access steps- 33 Ocean Drive | [6 empty] | 1 | Est Outstanding
5B | 1 | 471 | Section 5B - IFC issues of drawings cable routes and ducting | [6 empty] | 1 | Est Outstanding
| 1 | 472 | Developed Kinematic Envelopment (DKE) Check | 1 | 1 | 15118 | 15118 |  | 15118 |  |  |  |  | 91
1A | 1 | 473 | Construction of 3nr Sewer Protection Slabs / New Chamber - Lindsay Road |  | 1 |  | 151126.4 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4979
5B | 1 | 474 | Section 5B - Additional Manhole | 1 | 1 | 8848 | 8848 |  | 7086 | [12 empty] | revised estimate agreed. | INF CORR 3385/DC, 8/2/10
5C |  | 475 | A8 Underpass Phase 2 BT Ducts - 2 way & 4 way slewing | 1 | 1 | 99950 | 99950 |  | 94934 |  |  |  |  | 105
unall |  | 476 | Tram Stops - Development Workshop - Changes Arising | [6 empty] | 1 | Est Outstanding
unall |  | 477 | Sub-station Deveopment Workshop - Changes Arising |  | 1 |  | 145043.59 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4732
unall |  | 478 | Issues to close out CEC Roads TAA Sign Off | [6 empty] | 1 | Est Outstanding
5A |  | 479 | Sewer lining at Water of Leith Bridge |  | 1 |  | 55709 | [8 empty] | 1 | tie | [5 empty] | INF CORR 4078
6 |  | 480 | IFC Drawings - Airport flood prevention measures | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC
|  | 481 | INTC NOT ISSUED | [8 empty] | 1 | Not issued
6A |  | 482 | Section 6 Turning Head | [8 empty] | 1 | Withdrawn | [9 empty] | BSC letter ref 4848 2/03/2010
unall |  | 483 | Changes to sub-stations arising from development workshops | [6 empty] | 1 | Est Outstanding
7 |  | 484 | Section 7 Culvert 1 Excavation below Formation Level | [6 empty] | 1 | Est Outstanding | [10 empty] | Estimate still outstanding. TNC issued 6th October 2009
unall |  | 485 | Manderston street - operational track cross over | [6 empty] | 1 | Est Outstanding
unall |  | 486 | TRO Changes September 2009 |  |  |  |  | 3430 |  | 1 | Est Outstanding
7 |  | 487 | Gogar depot south embankment reinstatement and water supplies | [6 empty] | 1 | Est Outstanding
unall |  | 488 | Development workshop for drainage - changes arising |  |  |  |  | 46179.2 |  | 1 | Est Outstanding | [11 empty] | BSC ref 4812
5B |  | 489 | Piling Obstructions at Guided Busway |  | 1 |  | 16188 | [10 empty] | 1 | BSC |  |  |  | INF CORR - 4202
1C |  | 490 | Testing to carriageway at Leith walk |  | 1 |  | 54198 | [10 empty] | 1 | BSC |  |  |  | INF CORR 3351
1A |  | 491 | Cabling at Tower Place Bridge | [6 empty] | 1 | Est Outstanding
5A |  | 492 | IFC Drawing Haymarket Depot Car park |  | 1 |  | 145331.73 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4821
5A |  | 493 | IFC Drawings Murrayfield Stadium Tramstop | [6 empty] | 1 | Est Outstanding
5A |  | 494 | Section 5A - IFC issues of drawings cable routes and ducting | [6 empty] | 1 | Est Outstanding
5C |  | 495 | Section 5C - IFC issues of drawings cable routes and ducting | [6 empty] | 1 | Est Outstanding
1A |  | 496 | Section 1A - IFC issues of drawings cable routes and ducting | [6 empty] | 1 | Est Outstanding
|  | 497 | Arch Structures Within Princes Street | [8 empty] | 1 | Cost agreed at NIL | [9 empty] | Refer BSC letter Ref JHI/4654
|  | 498 | Bus lane & Tram lane only zones - system wide |  | 1 |  | 732253.06 | [15 empty] | BSC ref 4965 10/03/2010
1C |  | 499 | Frederick St Pedestrian Crossing |  |  |  |  | 17787.16 | [14 empty] | BSC ref 4959 10/03/2010
1C |  | 500 | Alternative Design for North side of Picardy Place |  |  |  |  | 33396 |  | 1 | Est Outstanding | [10 empty] | BSC to submit revised des est. | BSC ref 4733
7A |  | 501 | RBS Tramstop Futureproofing Works |  |  |  |  | 8509.15 |  | 1 | Est Outstanding | [10 empty] | revised des estimate to follow | BSC ref 5000 12/03/2010
5B |  | 502 | Additional Excavation at Carrick Knowe Bridge | 1 | 1 | 391 | 391 |  | 391 |  |  |  |  | 136
unall |  | 503 | Trackside Signage | [6 empty] | 1 | Est Outstanding
5B |  | 504 | Additional Lighting Columns at Carrick Knowe Bridge |  | 1 |  | 338.14 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4388
1D |  | 505 | Traffic Signalling Control at Junction 41 | 1 | 1 | 137105 | 137105 |  | 137105 |  |  |  |  | 124
5A |  | 506 | Removal of Obstructions at Russell Road Bridge |  | 1 |  | 62947 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4577
5A |  | 507 | Russell Road Retaining Wall - Additional Pile | [6 empty] | 1 | Est Outstanding
6 |  | 508 | Additional footway across Depot Access Bridge | [6 empty] | 1 | Est Outstanding | [10 empty] | Should now be getting deleted. | INF CORR 3109/DS (06/01/10)
unall |  | 509 | OLE Pole Modifications / Supply of Finials | [6 empty] | 1 | Est Outstanding
7 |  | 510 | Section 7 - IFC issue of drawings Cable Routes and Ducting Layout | [6 empty] | 1 | Est Outstanding | [10 empty] | Estimate due 19/03/2010 | BSC ref 4868 03/01/2010
5A |  | 511 | Russell Road Retaining Wall - Piling Obstructions - Estimate with Options |  | 1 |  | 80000 | [10 empty] | 1 | BSC |  |  | Refer tie e-mail from TC to Brian Walker | Refer tie e-mail 4/12/09
unall |  | 512 | Compressed Air Supply | [6 empty] | 1 | Est Outstanding | [10 empty] | tie consider should be withdrawn | INF CORR 3291/AS (01/02/10)
unall |  | 513 | IFC chnages to kerbs, footways, cycleways, laybys, busbays and paved areas specification | [6 empty] | 1 | Est Outstanding | [11 empty] | refer to tie letter 4024
unall |  | 514 | IFC Changes to Road Restraint Specification | [6 empty] | 1 | Est Outstanding
unall |  | 515 | Rheada City Slab (Design Only) |  |  |  |  | 121847 |  | 1 | Est Outstanding
unall |  | 516 | IFC Changes to Road Markings & Stud Specification | [6 empty] | 1 | Est Outstanding
5A |  | 517 | Section 5A Scottish Power utilities diversion 5A | 1 | 1 |  | 23175 |  | 20006 |  |  |  |  | 139 | [8 empty] | BSC ref 4851 02/03/2010
5A |  | 518 | Removal of Asbestos - RRRW - W4 |  | 1 |  | 2523 | [10 empty] | 1 | BSC |  |  |  | INF CORR 3360
AB |  | 519 | Reduced scope - St Andrews Square | [6 empty] | 1 | Est Outstanding
1C |  | 520 | Changes to Traffic Management to accommodate re-introduction of buses on Princes St | [6 empty] | 1 | Est Outstanding
|  | 521 | Disaster Recovery Centre | [6 empty] | 1 | Est Outstanding
1B |  | 522 | Trackform design at Letih Walk Railway Bridge | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4689
6 |  | 523 | A8 Underpass support & protect BT apparatus |  | 1 |  | 80348.11 | [10 empty] | 1 | BSC |  |  | Await check quotations | BSC ref 4823
1B |  | 524 | Leith Walk interface with BT apparatus diversions & impact on restarting Leith Walk | [6 empty] | 1 | Est Outstanding
unall |  | 525 | Development workshop report; earthing & bonding | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4870
unall |  | 526 | TRO changes at Grosvenor St | [6 empty] | 1 | Est Outstanding
unall |  | 527 | Network Rail Access Road | [6 empty] | 1 | Est Outstanding | [11 empty] | INF CORR 3365
5A |  | 528 | IFC Drgs - Roads, Street Lighting, Drainage Section 5A | [6 empty] | 1 | Est Outstanding
7 |  | 529 | Gogar Landfill profile design | [6 empty] | 1 | Est Outstanding
unall |  | 530 | SDS Design Programme - Revision 47 | [6 empty] | 1 | Est Outstanding
unall |  | 531 | SDS Design Programme - Revision 48 | [6 empty] | 1 | Est Outstanding
unall |  | 532 | SDS Design Programme - Revision 49 | [6 empty] | 1 | Est Outstanding
unall |  | 533 | SDS Design Programme - Revision 50 | [6 empty] | 1 | Est Outstanding
unall |  | 534 | SDS Design Programme - Revision 51 | [6 empty] | 1 | Est Outstanding
unall |  | 535 | SDS Design Programme - Revision 47 | [6 empty] | 1 | Est Outstanding
unall |  | 536 | Incomplete utility Works | [6 empty] | 1 | Est Outstanding
unall |  | 537 | Noise and vibration works arising from the study carried out under INTC 438 | [6 empty] | 1 | Est Outstanding
|  | 538 | INTC NOT ISSUED | [8 empty] | 1 | Not Issued
|  | 539 | Edinburgh Airport OLE Foundations | [6 empty] | 1 | Est Outstanding
|  | 540 | Edinburgh Airpport Platform Changes | [6 empty] | 1 | Est Outstanding
6 |  | 541 | Edinburgh Airport CEC Changes |  |  |  |  | 20177.54 |  | 1 | Est Outstanding | [11 empty] | BSC ref 4674
1B |  | 542 | Section 1B - Cundy Works |  | 1 |  | 1902.71 | [10 empty] | 1 | BSC |  |  |  | INF CORR 4376/SG
1B |  | 543 | Transyt & Linsig Modelling |  | 1 |  | 41253.43 | [8 empty] | 1 | tie | [5 empty] | BSC ref 4651
5 |  | 544 | Additional Parapet Upstand on Deck of Carrick Knowe Bridge | [6 empty] | 1 | Est Outstanding
|  | 545 | Removal of 4nr bus Shelters | [6 empty] | 1 | Est Outstanding
|  | 546 | Drainage Conflicts | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4798
|  | 547 | Power Conenctions to substation - Gogar Depot | [6 empty] | 1 | Est Outstanding
|  | 548 | INTC NOT ISSUED | [8 empty] | 1 | Not Issued
|  | 549 | Section 1D street lighting | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4701
|  | 550 | INTC NOT ISSUED | [8 empty] | 1 | Not Issued
5B |  | 551 | Removal & disposal of contaminated soil at Russell Road wall 4 | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4747
5A |  | 552 | Section 5A Viking Yards car park alterations | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4752
5B |  | 553 | Below ground obstructions piling to Russell road retaining wall 4 | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4753
6 |  | 554 | Edinburgh Airport CCRC walkway earthing & bonding | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4779
5B |  | 555 | Section 5B Busgate existing services | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4787
5C |  | 556 | Section 5C Edinburgh park private utility diversion by others | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4788
6 |  | 557 | South Gyle Access Bridge, existing sewer diversion | [6 empty] | 1 | Est Outstanding | [11 empty] | 4854
5B |  | 558 | South Gyle Access Bridge, traffic management |  | 1 |  | 24530.65 | [15 empty] | BSC ref 4943
|  | 559 | A8 Underpass - SGN Diversion | [6 empty] | 1 | Est Outstanding
5C |  | 560 | Grouting of Existing Sewer - A8 underpass | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4901 05/03/2010
|  | 561 | SP cable at Gyle Stop Retaining Wall | [6 empty] | 1 | Est Outstanding
7 |  | 562 | New lighting scheme for gogarburn rouondabout |  | 1 |  | 46023.15 | [8 empty] | 1 | tie | [5 empty] | INF CORR 4351 10/03/2010
1A |  | 563 | Section 1A Lindsay Rd works | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC 4797
1A |  | 564 | Section 1A Lindsay Rd Handover dates | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC 4799
5 |  | 565 | Murrayfield Tramstop | [6 empty] | 1 | Est Outstanding | [10 empty] | Estimate due 18days from BSC letter date. | BSC ref 4866 03/03/2010
|  | 566 | Traffic Island at Princess St | [6 empty] | 1 | Est Outstanding
7 |  | 567 | Section 7 Accommodation Works | [6 empty] | 1 | Est Outstanding | [11 empty] | BSC ref 4898 03/03/2010
|  | 568 | Topographical survey at Scotrail Depot | [6 empty] | 1 | Est Outstanding
|  | 569 | INTC NOT ISSUED | [8 empty] | 1 | Not Issued
1D |  | 570 | Access to Worksite on Shandwick Place | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  |  | BSC ref 4735 08/03/2010
1D |  | 571 | Access to Worksite at Clifton Terrace | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  |  | BSC ref 4734 08/03/2010
1D |  | 572 | Out of Sequence working Section 1D | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  |  | BSC ref 4942 08/03/2010
1A |  | 573 | Forth Ports Fence alteration | [6 empty] | 1 | Est Outstanding | [6 empty] | 1 | BSC |  |  |  | BSC ref 4951 08/03/2010
| 486 |  |  | 135 | 246 |  |  |  |  | 255 |  | 89 |  |  |  | 23 | 0 | 71 | 0 | 25 | 0
|  |  | Total |  |  | 26756741.12 |  |  | 16252918.17
Summary - Position to 5th February 2010
[11 empty] | Total |  | 573
|  |  | Total Number Complete Estimates Received |  |  |  | 246 |  |  |  | Deleted
Duplicated
|  |  | Change Orders Issued against INTC's raised |  |  |  | 135 |  |  |  | Not Issued
Confirm - No cost
[11 empty] | Superseeded |  | -89
|  |  | Number of Live Estimates |  |  |  | 111
484
|  |  | Estimates Issued - Disputed as a Change by tie |  |  |  | 26
|  |  | Outstanding BSC Action - Estimates submitted |  |  |  | 62 |  |  |  | Estimates outstanding |  | 255
|  |  | Outstanding tie Action |  |  |  | 27