## option 1
Edinburgh Tram - Cost of Work Done to Period 6
Financial Year 2012/13
Summary area (as reported to 25 October 2012 Council Meeting) | Area | COWD to date
Project Management | Project Management | 61.8715
Project Management | Archaeology | 0.67845
Preparing for Operations | Preparing for Operations | 3.8072
Project Management | Legals | 7.1542
Project Management | Design - SDS | 26.3919
Project Management | JRC (incl traffic modelling) | 2.8783
Project Management | CEC | 3.5169
Project Management | Technical Support Services | 11.5888
Project Management | Utilities | 0.020521
Project Management | Design Support | 0.29803
Project Management | Third Party- Network Rail | 2.5199
Project Management | Land and Property | 23.2616
Project Management | Business Support | 1.6965
Project Management | TROs | 0.55761
Project Management | Comms | 3.4297
Preparing for Operations | TEL | 2.9969
Project Management | Service Integration | 0.20323
Project Management | PUK | 0.26185
Project Management | Financial Advisor | 0.29715
Project Management | Insurance | 4.9625
Project Management | MUDFA/Utilities | 69.6561
Infraco contract- off street | off street-post Settlement Agreement | 95.75
Infraco contract- on street | on street- post Settlement Agreement | 18.992
Infraco contract- on street | other | 2.063
Infraco contract | Pre Settlement Agreeement Works* | 214.67
Infraco contract- other items | maintenance mobilisation | 0.66273
Infraco contract- other items | initial spare parts | 0
Infraco contract- other items | Approved changes | 0
Project Management | York Place direct works | 0.178
Project Management | Infraco- non-Carillion Utilities | 13.1222
Project Management | Infraco- Phase 1b | 3.2
Project Management | Depot adance works | 5.4384
Project Management | Advance works | 0.28153
Project Management | Infraco- non-contract non-utility | 8.2969
Project Management | Forth Ports | 1.3864
Utilities- post September 2011 | Utilities- post mediation | 12.577
Utilities- post September 2011 | Leith Walk remedials | 0
Utilities- post September 2011 | Legacy utilities- revised tram route | 1.001
Tram vehicles | Tramco | 60.8271
Project Management | Miscellaneous | 3.2617
Items closed - no further costs will be incurred. |  | 669.7568
*This includes all Infraco works pre settlement both on and off street

## option 2
Edinburgh Tram - Cost of Work Done to Period 6
Financial Year 2012/13
|  |  |  | Period 6 2012/13 | [11 empty] | Period 5 2012/13 | [9 empty] | Period 2 2011/12 |  |  |  | Period 4 2011/12
|  |  | Summary area (as per A Bourne template) | Invoiced To Date | Accrual | COWD | [8 empty] | Summary area (as reported to 25 October 2012 Council Meeting) | COWD | P6 Actual | [10 empty] | COWD (as reported to Council 30 June 2011) | Summary area (as reported to Council 30 June 2011)
[6 empty] | 2009-12-05 |  |  | Filter | [10 empty] | Filter | [5 empty] | Invoiced to Date | Accrual |  |  | COWD
|  |  |  | 4 | 5 | 6
6 | T01.01 | Project management Staff Costs | PM Management | 40939380 | 521085.895 | 41460465.895 | [8 empty] | Project Management | 40943371.43 | 517094.465 | [8 empty] | 31409256 | 108378 | 31517634 | Project Management | 32333538
6 | T01.02 | Recruitment Fees | PM Support | 466592.98 | 0 | 466592.98 | [8 empty] | Project Management | 466592.98 | 0 | [8 empty] | 466593 | 3128 | 469721 | Project Management | 466593
6 | T01.03 | Travel & Subsistence / Conference | PM Support | 378764 | 0 | 378764 | [8 empty] | Project Management | 378741 | 23 | [8 empty] | 355402 | 2000 | 357402 | Project Management | 359526.69
6 | T01.04 | Central Overheads | PM Support | 5268506 | 67723 | 5336229 | [8 empty] | Project Management | 5335256 | 973 | [8 empty] | 5133781 | 42444 | 5176225 | Project Management | 5212065
6 | T01.05 | IT & Software Costs / fitout | PM Support | 4252934 | 35404 | 4288338 | [8 empty] | Project Management | 4229825.51 | 58512.49 | [8 empty] | 3364672 | 0 | 3364672 | Project Management | 3409893.67
6 | T01.06 | Citypoint - rent,rates,s/c | PM Support | 3248843 | 0 | 3248843 | [8 empty] | Project Management | 3248843 | 0 | [8 empty] | 2950614 | -8923 | 2941691 | Project Management | 2995934.33
6 | T01.08 | Short Term Contractors | PM Management | 288558 | 59483 | 348041 | [8 empty] | Project Management | 338041 | 10000 | [8 empty] | 196804 | 0 | 196804 | Project Management | 196804
6 | T01.09 | City Point Overheads | PM Support | 67723 | -67723 | 0 | [8 empty] | Project Management | 0 | 0 | [8 empty] | 67715.09 | -42444 | 25271.09 | Project Management | 25271.09
6 | T01.10 | Active Risk Manager | PM Management | 83666 | 0 | 83666 | [8 empty] | Project Management | 83666 | 0 | [8 empty] | 83666 | 0 | 83666 | Project Management | 83666
6 | T01.11 | Archaeological supervisor - Gogar works | PM Supervision | 174229.64 | 0 | 174229.64 | [8 empty] | Project Management | 174229.64 | 0 | [8 empty] | 172961.64 | 1350 | 174311.64 | Project Management | 174230
6 | T01.13 | Archaeology - Non Gogar | PM Supervision | 504219 | 0 | 504219 | [8 empty] | Project Management | 504219 | 0 | [8 empty] | 352733.36 | 1116 | 353849.36 | Project Management | 373580
6 | T01.14 | DRP Costs | PM Management | 6238614 | 0 | 6238614 | [8 empty] | Project Management | 6238614 | 0 | [8 empty] | 5885378 | 243008 | 6128386 | Project Management | 6152699
6 | T01.15 | Tax Planning / Governance Costs (Non DLA) | PM Management | 21960 | 0 | 21960 | [8 empty] | Project Management | 21960 | 0 | [8 empty] | 21960 | 0 | 21960 | Project Management | 21960
| T01 | Total tie/T&T PM costs |  | 61933993.62 | 615977.895 | 62549968.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 61963359.56 | 586602.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50461536.09 | 350057 | 50811593.09 |  | 51805760.78
7 | T02.01 | Core Team | Operations | 3755114 | 52116.38 | 3807230.38 | 3807230.38 | 0 | [6 empty] | Preparing for Operations | 3685527.62 | 121702.76 | 3807230.38 | 0 | [6 empty] | 2761750 | 26620 | 2788370 | Project Management | 2834832.76
| T02 | Total DPOF |  | 3755114 | 52116.38 | 3807230.38 | 3807230.38 | 0 | [7 empty] | 3685527.62 | 121702.76 | 3807230.38 | 0 | [6 empty] | 2761750 | 26620 | 2788370 |  | 2834832.76
10 | T03.01 | DLA-SDS | Legal | 140623.89 | 0 | 140623.89 | 140623.89 | 0 | [6 empty] | Project Management | 140623.89 | 0 | 140623.89 | 0 | [6 empty] | 140623.89 | 0 | 140623.89 | Other Resources | 140623.89
10 | T03.02 | DLA-TSS | Legal | 32000.37 | 0 | 32000.37 | 32000.37 | 0 | [6 empty] | Project Management | 32000.37 | 0 | 32000.37 | 0 | [6 empty] | 32000.37 | 0 | 32000.37 | Other Resources | 32000.37
10 | T03.03 | DLA- Site Investigation | Legal | 1116.25 | 0 | 1116.25 | 1116.25 | 0 | [6 empty] | Project Management | 1116.25 | 0 | 1116.25 | 0 | [6 empty] | 1116.25 | 0 | 1116.25 | Other Resources | 1116.25
10 | T03.04 | DLA-MUDFA | Legal | 822570.21 | 0 | 822570.21 | 822570.21 | 0 | [6 empty] | Project Management | 822570.21 | 0 | 822570.21 | 0 | [6 empty] | 822570 | 0 | 822570 | Other Resources | 822570
10 | T03.05 | DLA-Network Rail / Scotrail | Legal | 114559.32 | 0 | 114559.32 | 114559.32 | 0 | [6 empty] | Project Management | 114559.32 | 0 | 114559.32 | 0 | [6 empty] | 114559.32 | 0 | 114559.32 | Other Resources | 114559.32
10 | T03.06 | DLA-JRC | Legal | 27382.82 | 0 | 27382.82 | 27382.82 | 0 | [6 empty] | Project Management | 27382.82 | 0 | 27382.82 | 0 | [6 empty] | 27382.82 | 0 | 27382.82 | Other Resources | 27382.82
10 | T03.07 | DLA-Infraco | Legal | 1525372 | 0 | 1525372 | 2820148 | 0 | [6 empty] | Project Management | 2793424 | -1268052 | 2820148 | 0 | [6 empty] | 1525372.28 | 0 | 1525372.28 | Other Resources | 1525372.28
10 | T03.08 | DLA-Vehicles & Driver supply contract | Legal | 471228.65 | 0 | 471228.65 | 471228.65 | 0 | [6 empty] | Project Management | 471228.65 | 0 | 471228.65 | 0 | [6 empty] | 471228.65 | 0 | 471228.65 | Other Resources | 471228.65
10 | T03.09 | DLA-BAA | Legal | 24212.74 | 0 | 24212.74 | 24212.74 | 0 | [6 empty] | Project Management | 24212.74 | 0 | 24212.74 | 0 | [6 empty] | 24212.74 | 0 | 24212.74 | Other Resources | 24212.74
10 | T03.10 | DLA-Land & Property (3rd parties) | Legal | 25946.24 | 0 | 25946.24 | 25946.24 | 0 | [6 empty] | Project Management | 25946.24 | 0 | 25946.24 | 0 | [6 empty] | 25946.24 | 0 | 25946.24 | Other Resources | 25946.24
10 | T03.12 | DLA-DPOF | Legal | 96071.26 | 0 | 96071.26 | 96071.26 | 0 | [6 empty] | Project Management | 96071.26 | 0 | 96071.26 | 0 | [6 empty] | 96071.26 | 0 | 96071.26 | Other Resources | 96071.26
10 | T03.13 | DLA-Tram Netwk/Roads Interface | Legal | 22149.45 | 0 | 22149.45 | 22149.45 | 0 | [6 empty] | Project Management | 22149.45 | 0 | 22149.45 | 0 | [6 empty] | 22149.45 | 0 | 22149.45 | Other Resources | 22149.45
10 | T03.14 | DLA-EARL interface | Legal | 39217.39 | 0 | 39217.39 | 39217.39 | 0 | [6 empty] | Project Management | 39217.39 | 0 | 39217.39 | 0 | [6 empty] | 39217.39 | 0 | 39217.39 | Other Resources | 39217.39
10 | T03.15 | DLA-Commissioning Svcs Agmt | Legal | 6892.48 | 0 | 6892.48 | 6892.48 | 0 | [6 empty] | Project Management | 6892.48 | 0 | 6892.48 | 0 | [6 empty] | 6892.48 | 0 | 6892.48 | Other Resources | 6892.48
10 | T03.16 | OCIP | Legal | 27086.06 | 0 | 27086.06 | 27086.06 | 0 | [6 empty] | Project Management | 27086.06 | 0 | 27086.06 | 0 | [6 empty] | 27086.06 | 0 | 27086.06 | Other Resources | 27086.06
10 | T03.17 | Infraco Enabling | Legal | 4383 | 0 | 4383 | 4383 | 0 | [6 empty] | Project Management | 4383 | 0 | 4383 | 0 | [6 empty] | 4383 | 0 | 4383 | Other Resources | 4383
10 | T03.19.01 | DLA - HSQE | Legal | 9022.6 | 0 | 9022.6 | 9022.6 | 0 | [6 empty] | Project Management | 9022.6 | 0 | 9022.6 | 0 | [6 empty] | 9022.6 | 0 | 9022.6 | Other Resources | 9022.6
10 | T03.19.02 | DLA - Governance | Legal | 97321.66 | 0 | 97321.66 | 97321.66 | 0 | [6 empty] | Project Management | 97321.66 | 0 | 97321.66 | 0 | [6 empty] | 88143 | 7877 | 96020 | Other Resources | 96020
10 | T03.19.03 | DLA - CEC Interface | Legal | 15614.35 | 0 | 15614.35 | 15614.35 | 0 | [6 empty] | Project Management | 15614.35 | 0 | 15614.35 | 0 | [6 empty] | 15614 | 0 | 15614 | Other Resources | 15614
| T03.01-19 | DLA |  | 3502770.43 | 0 | 3502770.43 | 4797546.43 | 0 | [7 empty] | 4770822.74 | -1268052 | 4797546.43 | 0 | [6 empty] | 3493591.8 | 7877 | 3501468.8 |  | 3501468.8
10 | T03.20 | D&W-General Advice | Legal | 704900.77 | 0 | 704900.77 | 704900.77 | 0 | [6 empty] | Project Management | 704900.77 | 0 | 704900.77 | 0 | [6 empty] | 704900.77 | 0 | 704900.77 | Other Resources | 704900.77
10 | T03.21 | D&W-TRO's | Legal | 556301 | 0 | 556301 | 556301 | 0 | [6 empty] | Project Management | 555821 | 480 | 556301 | 0 | [6 empty] | 546036 | 0 | 546036 | Other Resources | 542918
10 | T03.22 | D&W-Property | Legal | 1220836 | 1077 | 1221913 | 1221913 | 0 | [6 empty] | Project Management | 1221913 | 0 | 1221913 | 0 | [6 empty] | 1174393 | 1000 | 1175393 | Other Resources | 1187819
10 | T03.23 | D&W-Planning Monitoring | Legal | 181253 | 0 | 181253 | 181253 | 0 | [6 empty] | Project Management | 181253 | 0 | 181253 | 0 | [6 empty] | 181253 | 0 | 181253 | Other Resources | 181253
10 | T03.24 | D&W-TDWG | Legal | 85982 | 0 | 85982 | 85982 | 0 | [6 empty] | Project Management | 85982 | 0 | 85982 | 0 | [6 empty] | 85982 | 0 | 85982 | Other Resources | 85982
10 | T03.26 | D&W-Litigation | Legal | 10490 | 0 | 10490 | 10490 | 0 | [6 empty] | Project Management | 10490 | 0 | 10490 | 0 | [6 empty] | 10490 | 0 | 10490 | Other Resources | 10490
10 | T03.27 | D&W-Secondments | Legal | 152123 | 0 | 152123 | 152123 | 0 | [6 empty] | Project Management | 152123 | 0 | 152123 | 0 | [6 empty] | 152123 | 0 | 152123 | Other Resources | 152123
| T03.20-35 | Subtotal D&W |  | 2911885.77 | 1077 | 2912962.77 | 2912962.77 | 0 | [7 empty] | 2912482.77 | 480 | 2912962.77 | 0 | [6 empty] | 2855177.77 | 1000 | 2856177.77 |  | 2865485.77
10 | T03.07b | Post Mediation | Legal | 1262776 | 32000 | 1294776 | 2820148 | 0 | [6 empty] | Project Management |  | 1294776 | 2820148 | 0 | [9 empty] | Other Resources
| T03 | Total LEGALS |  | 7677432.2 | 33077 | 7710509.2 | 7710509.2 | 0 | [7 empty] | 7683305.51 | 27204 | 7710509.2 | 0 | [6 empty] | 6348769.57 | 8877 | 6357646.57 |  | 6366954.57
9 | T04.01 | Design Services under SDS | Design | 31008630 | -6031705 | 24976925 | 24976925 | 0 | [6 empty] | Project Management | 24976925 | 0 | 24976925 | 0 | [6 empty] | 30506755 | 1135716 | 31642471 | Design | 31500378
9 | T04.02 | Site Investigation under SDS | Design | 1415000 | 0 | 1415000 | 1415000 | 0 | [6 empty] | Project Management | 1415000 | 0 | 1415000 | 0 | [6 empty] | 1415000 | 0 | 1415000 | Design | 1415000
| T04 | Total SDS |  | 32423630 | -6031705 | 26391925 | 26391925 | 0 | [7 empty] | 26391925 | 0 | 26391925 | 0 | [6 empty] | 31921755 | 1135716 | 33057471 |  | 32915378
6 | T05.01 | Integrated Transport Model | PM Other | 2655126 | 47646 | 2702772 | 2702772 | 0 | [6 empty] | Project Management | 2699831 | 2941 | 2702772 | 0 | [6 empty] | 2477049 | 1580 | 2478629 | Traffic Management | 2478049
6 | T05.02 | Surveys (MM) | PM Other | 165589 | 0 | 165589 | 165589 | 0 | [6 empty] | Project Management | 165589 | 0 | 165589 | 0 | [6 empty] | 165589 | 0 | 165589 | Traffic Management | 165589
6 | T05.03 | Consultancy (Halcrow) | PM Other | 9916 | 0 | 9916 | 9916 | 0 | [6 empty] | Project Management | 9916 | 0 | 9916 | 0 | [6 empty] | 9916 | 0 | 9916 | Traffic Management | 9916
| T05 | Total JRC |  | 2830631 | 47646 | 2878277 | 2878277 | 0 | [7 empty] | 2875336 | 2941 | 2878277 | 0 | [6 empty] | 2652554 | 1580 | 2654134 |  | 2653554
6 | T06.01 | Technical Services | PM Management | 11202403 | 99862.5 | 11302265.5 | 11302265.5 | 0 | [6 empty] | Project Management | 11246736.21 | 55529.29 | 11302265.5 | 0 | [6 empty] | 10496833 | 76961 | 10573794 | Project Management | 10591386.17
6 | T06.02 | Land agreement/negotiations | PM Management | 113000 | 0 | 113000 | 113000 | 0 | [6 empty] | Project Management | 113000 | 0 | 113000 | 0 | [6 empty] | 113000 | 0 | 113000 | Project Management | 113000
6 | T06.04 | TSS Second to CEC-Approvals support | PM Management | 92381 | 0 | 92381 | 92381 | 0 | [6 empty] | Project Management | 92381 | 0 | 92381 | 0 | [6 empty] | 92381 | 0 | 92381 | Project Management | 92381
6 | T06.05 | T&T Costs | PM Management | 81176.99 | 0 | 81176.99 | 81176.99 | 0 | [6 empty] | Project Management | 81176.99 | 0 | 81176.99 | 0 | [6 empty] | 81176.99 | 0 | 81176.99 | Project Management | 81176.99
| T06.01-03 | Subtotal TSS |  | 11488960.99 | 99862.5 | 11588823.49 | 11588823.49 | 0 | [7 empty] | 11533294.2 | 55529.29 | 11588823.49 | 0 | [6 empty] | 10783390.99 | 76961 | 10860351.99 |  | 10877944.16
6 | T06.03 | CEC staff costs | PM Management | 3474398 | 42500 | 3516898 | 3516898 | 0 | [6 empty] | Project Management | 3435453 | 81445 | 3516898 | 0 | [6 empty] | 2316166 | 74171 | 2390337 | Project Management | 2467459
| T06.03a | Subtotal CEC |  | 3474398 | 42500 | 3516898 | 3516898 | 0 | [7 empty] | 3435453 | 81445 | 3516898 | 0 | [6 empty] | 2316166 | 74171 | 2390337 |  | 2467459
| T06 | Total TSS and CEC |  | 14963358.99 | 142362.5 | 15105721.49 | 15105721.49 | 0 | [7 empty] | 14968747.2 | 136974.29 | 15105721.49 | 0 | [6 empty] | 13099556.99 | 151132 | 13250688.99 |  | 13345403.16
4 | T07.01 | Consultancies | Utilities | 20521 | 0 | 20521 | 20521 | 0 | [6 empty] | Project Management | 20521 | 0 | 20521 | 0 | [6 empty] | 20521 | 0.46 | 20521.46 | Other Resources | 20521
| T07 | Total UTILITIES |  | 20521 | 0 | 20521 | 20521 | 0 | [7 empty] | 20521 | 0 | 20521 | 0 | [6 empty] | 20521 | 0.46 | 20521.46 |  | 20521
9 | T08.01 | Tech. Advisors-Parl.Support | Design | 268643 | 0 | 268643 | 268643 | 0 | [6 empty] | Project Management | 268643 | 0 | 268643 | 0 | [6 empty] | 268643 | -0.24 | 268642.76 | Other Resources | 268643
9 | T08.02 | Tech. Advisors-Parl.Support-PM | Design | 29383 | 0 | 29383 | 29383 | 0 | [6 empty] | Project Management | 29383 | 0 | 29383 | 0 | [6 empty] | 29383 | -0.01 | 29382.99 | Other Resources | 29383
| T08 | Total DESIGN SUPPORT |  | 298026 | 0 | 298026 | 298026 | 0 | [7 empty] | 298026 | 0 | 298026 | 0 | [6 empty] | 298026 | -0.25 | 298025.75 |  | 298026
6 | T09.01.01 | Network Rail - FDA Work Contract 1 | PM Other | 217378.35 | 0 | 217378.35 | 217378.35 | 0 | [6 empty] | Project Management | 217378.35 | 0 | 217378.35 | 0 | [6 empty] | 217378.35 | 0 | 217378.35 | Other Resources | 217378.35
6 | T09.01.02 | Network Rail - Basic Implementation Agreement | PM Other | 114517.49 | 0 | 114517.49 | 114517.49 | 0 | [6 empty] | Project Management | 114517.49 | 0 | 114517.49 | 0 | [6 empty] | 114517.49 | 0.36 | 114517.85 | Other Resources | 114517.85
6 | T09.03 | Network Rail - Asset Protection Agreement | PM Other | 1863792 | 100000 | 1963792 | 1963792 | 0 | [6 empty] | Project Management | 1932892.01 | 30899.99 | 1963792 | 0 | [6 empty] | 1339928.27 | 19026 | 1358954.27 | Other Resources | 1352544
6 | T19.07.01 | Network Rail - Development Services Agreement | PM Other | 214954.25 | 0 | 214954.25 | 214954.25 | 0 | [6 empty] | Project Management | 214954.25 | 0 | 214954.25 | 0 | [6 empty] | 214954.25 | 0 | 214954.25 | Other Resources | 214954.25
6 | T19.07.03 | Network Rail - Others | PM Other | 9219.17 | 0 | 9219.17 | 9219.17 | 0 | [6 empty] | Project Management | 9219.17 | 0 | 9219.17 | 0 | [6 empty] | 9219.17 | 0 | 9219.17 | Other Resources | 9219.17
| T09 | Total 3RD PARTY NEGOTIATIONS |  | 2419861.66 | 100000 | 2519861.66 | 2519861.66 | 0 | [7 empty] | 2488961.27 | 30899.99 | 2519861.66 | 0 | [6 empty] | 1895997.53 | 19026.36 | 1915023.89 |  | 1908613.62
6 | T10.01 | D&W (10.01 &11.01) | PM Other | 25843 | 0 | 25843 | 25843 | 0 | [6 empty] | Project Management | 25843 | 0 | 25843 | 0 | [6 empty] | 25843 | 0 | 25843 | Other Resources | 25843
6 | T10.02 | Advisors (Colliers / DV) | PM Other | 207405 | 2447 | 209852 | 209852 | 0 | [6 empty] | Project Management | 208352 | 1500 | 209852 | 0 | [6 empty] | 186477 | 2000 | 188477 | Other Resources | 188713.5
6 | T10.04 | Advance Purchases 05/06 (Fees) | PM Other | 60181 | 0 | 60181 | 60181 | 0 | [6 empty] | Project Management | 60181 | 0 | 60181 | 0 | [6 empty] | 60181 | 0 | 60181 | Other Resources | 60181
6 | T10.05.01 | Advance Purchases (GVD) | PM Other | 13081432.04 | 2827998.77 | 15909430.81 | 15909430.81 | 0 | [6 empty] | Project Management | 15909430.81 | 0 | 15909430.81 | 0 | [6 empty] | 0.19 | 11474861.81 | 11474862 | Other Resources | 11474862
6 | T10.05.02 | Advance Purchases (gifted / free issue) | PM Other | 0 | 4807286 | 4807286 | 4807286 | 0 | [6 empty] | Project Management | 4807286 | 0 | 4807286 | 0 | [6 empty] | 0 | 4807286 | 4807286 | Land | 4807286
6 | T10.05.07 | Misc Land Costs | PM Other | 184181 | 0 | 184181 | 184181 | 0 | [6 empty] | Project Management | 178678 | 5503 | 184181 | 0 | [6 empty] | 144781 | 0 | 144781 | Other Resources | 161795
6 | T10.05.03 | BAA Contractor Costs | PM Other | 625305 | 0 | 625305 | 625305 | 0 | [6 empty] | Project Management | 625305 | 0 | 625305 | 0 | [6 empty] | 604586.12 | 0 | 604586.12 | Other Resources | 615317
6 | T10.05.04 | BAA PM costs | PM Other | 361358 | 40000 | 401358 | 401358 | 0 | [6 empty] | Project Management | 371358 | 30000 | 401358 | 0 | [6 empty] | 197667.25 | 0 | 197667.25 | Other Resources | 197667.25
6 | T10.05.05 | BAA Utilities | PM Other | 150000 | 0 | 150000 | 150000 | 0 | [6 empty] | Project Management | 150000 | 0 | 150000 | 0 | [6 empty] | 150000 | 0 | 150000 | Other Resources | 150000
6 | T10.05.08 | Haymarket station compensation | PM Other | 165488.56 | 722715 | 888203.56 | 888203.56 | 0 | [6 empty] | Project Management | 888203.56 | 0 | 888203.56 | 0 | [6 empty] | 165489 | 722715 | 888204 | Other Resources | 888204
| T10.01-.05 | Subtotal Land |  | 14861193.6 | 8400446.77 | 23261640.37 | 23261640.37 | 0 | [7 empty] | 23224637.37 | 37003 | 23261640.37 | 0 | [6 empty] | 1535024.56 | 17006862.81 | 18541887.37 |  | 18569868.75
6 | T10.06.01 | Business Support Primary payment | PM Other | 1651848.42 | 0 | 1651848.42 | 1651848.42 | 0 | [6 empty] | Project Management | 1651848.42 | 0 | 1651848.42 | 0 | [6 empty] | 1651848 | 0 | 1651848 | Other Resources | 1651848
6 | T10.06.03 | Business Support Admin | PM Other | 44698.86 | 0 | 44698.86 | 44698.86 | 0 | [6 empty] | Project Management | 44698.86 | 0 | 44698.86 | 0 | [6 empty] | 44698.86 | 0 | 44698.86 | Other Resources | 44698.86
| T10.06 | Subtotal Business Support |  | 1696547.28 | 0 | 1696547.28 | 1696547.28 | 0 | [7 empty] | 1696547.28 | 0 | 1696547.28 | 0 | [6 empty] | 1696546.86 | 0 | 1696546.86 |  | 1696546.86
| T10 | Total LAND & PROPERTY |  | 16557740.88 | 8400446.77 | 24958187.65 | 24958187.65 | 0 | [7 empty] | 24921184.65 | 37003 | 24958187.65 | 0 | [6 empty] | 3231571.42 | 17006862.81 | 20238434.23 |  | 20266415.61
6 | T11.02 | TRO's - Technnical | PM Other | 1313 | 0 | 1313 | 1313 | 0 | [6 empty] | Project Management | 1313 | 0 | 1313 | 0 | [6 empty] | 1313 | 0 | 1313 | Traffic Management | 1313
| T11 | Total TROs |  | 1313 | 0 | 1313 | 1313 | 0 | [7 empty] | 1313 | 0 | 1313 | 0 | [6 empty] | 1313 | 0 | 1313 |  | 1313
8 | T12.01 | Fees / production Items - WS | PR | 808154.11 | 0 | 808154.11 | 808154.11 | 0 | [6 empty] | Project Management | 808154.11 | 0 | 808154.11 | 0 | [6 empty] | 808154.12 | 0 | 808154.12 | Project Management | 808154.12
8 | T12.02 | Fees / production Items - MH | PR | 440767.92 | 0 | 440767.92 | 440767.92 | 0 | [6 empty] | Project Management | 440767.92 | 0 | 440767.92 | 0 | [6 empty] | 440767.92 | 0 | 440767.92 | Project Management | 440767.92
8 | T12.03 | Tram branding | PR | 38060.39 | 0 | 38060.39 | 38060.39 | 0 | [6 empty] | Project Management | 38060.39 | 0 | 38060.39 | 0 | [6 empty] | 38060.39 | 0 | 38060.39 | Project Management | 38060.39
8 | T12.04 | PR Support | PR | 20381 | 0 | 20381 | 20381 | 0 | [6 empty] | Project Management | 20381 | 0 | 20381 | 0 | [6 empty] | 20381 | 0 | 20381 | Project Management | 20381
8 | T12.05 | Business development and marketing | PR | 10546.25 | 0 | 10546.25 | 10546.25 | 0 | [6 empty] | Project Management | 10546.25 | 0 | 10546.25 | 0 | [6 empty] | 10546.25 | 0 | 10546.25 | Project Management | 10546.25
8 | T12.06 | Media monitoring | PR | 13059 | 0 | 13059 | 13059 | 0 | [6 empty] | Project Management | 13059 | 0 | 13059 | 0 | [6 empty] | 13059 | 0 | 13059 | Project Management | 13059
8 | T12.08 | Promotional materials | PR | 143525 | 0 | 143525 | 143525 | 0 | [6 empty] | Project Management | 143525 | 0 | 143525 | 0 | [6 empty] | 143525 | 0 | 143525 | Project Management | 143525
8 | T12.09 | Websites | PR | 25931 | 0 | 25931 | 25931 | 0 | [6 empty] | Project Management | 25931 | 0 | 25931 | 0 | [6 empty] | 25931 | 0 | 25931 | Project Management | 25931
8 | T12.10 | Events including Edinburgh Fringe | PR | 16115 | 0 | 16115 | 16115 | 0 | [6 empty] | Project Management | 16115 | 0 | 16115 | 0 | [6 empty] | 16115 | 0 | 16115 | Project Management | 16115
8 | T12.11 | Advertising | PR | 54770 | 0 | 54770 | 54770 | 0 | [6 empty] | Project Management | 54770 | 0 | 54770 | 0 | [6 empty] | 54770 | 0 | 54770 | Project Management | 54770
8 | T12.12 | Internal communications | PR | 8571 | 0 | 8571 | 8571 | 0 | [6 empty] | Project Management | 8571 | 0 | 8571 | 0 | [6 empty] | 8571 | 0 | 8571 | Project Management | 8571
8 | T12.23 | Sponsorship | PR | 17225 | 0 | 17225 | 17225 | 0 | [6 empty] | Project Management | 17225 | 0 | 17225 | 0 | [6 empty] | 17225 | 0 | 17225 | Project Management | 17225
8 | T12.24 | Communication consultancy services | PR | 196656 | 52500 | 249156 | 249156 | 0 | [6 empty] | Project Management | 209156 | 40000 | 249156 | 0 | [6 empty] | 0 | 0 | 0 | Project Management | 0
8 | T12.25 | Sundries | PR | 340 | 0 | 340 | 340 | 0 | [6 empty] | Project Management | 340 | 0 | 340 | 0 | [6 empty] | 340 | 0 | 340 | Project Management | 340
8 | T12.26 | Princes Street Costs | PR | 145062 | 0 | 145062 | 145062 | 0 | [6 empty] | Project Management | 145062 | 0 | 145062 | 0 | [6 empty] | 115062 | 10000 | 125062 | Project Management | 155062
8 | T12.27 | Public Information | PR | 149247 | 0 | 149247 | 149247 | 0 | [6 empty] | Project Management | 149247 | 0 | 149247 | 0 | [6 empty] | 129041 | 0 | 129041 | Project Management | 127338.12
8 | T12.28 | Team Costs | PR | 5315 | 0 | 5315 | 5315 | 0 | [6 empty] | Project Management | 5315 | 0 | 5315 | 0 | [6 empty] | 5103.35 | 0 | 5103.35 | Project Management | 5103.35
8 | T12.29 | External Resources | PR | 418840 | 0 | 418840 | 418840 | 0 | [6 empty] | Project Management | 417389 | 1451 | 418840 | 0 | [6 empty] | 296215 | 0 | 296215 | Project Management | 315231.33
8 | T12.33 | Tram Shop | PR | 63405 | 0 | 63405 | 63405 | 0 | [6 empty] | Project Management | 55703 | 7702 | 63405 | 0 | [6 empty] | 0 | 0 | 0 | Project Management | 0
| T12.01-12,23-40 | Subtotal Communications |  | 2575970.67 | 52500 | 2628470.67 | 2628470.67 | 0 | [7 empty] | 2579317.67 | 49153 | 2628470.67 | 0 | [6 empty] | 2142867.03 | 10000 | 2152867.03 |  | 2200180.48
8 | T12.13 | S/H – Wider Community Consultations | PR | 36265.44 | 0 | 36265.44 | 36265.44 | 0 | [6 empty] | Project Management | 36265.44 | 0 | 36265.44 | 0 | [6 empty] | 36265.44 | 0 | 36265.44 | Project Management | 36265.44
8 | T12.14 | S/H – Events | PR | 17028 | 0 | 17028 | 17028 | 0 | [6 empty] | Project Management | 17028 | 0 | 17028 | 0 | [6 empty] | 17028 | 0 | 17028 | Project Management | 17028
8 | T12.15 | S/H – Open for Business | PR | 633994 | 5516 | 639510 | 639510 | 0 | [6 empty] | Project Management | 632156 | 7354 | 639510 | 0 | [6 empty] | 639160 | 0 | 639160 | Project Management | 594160
8 | T12.16 | S/H – Communications - MUDFA | PR | 81786.66 | 0 | 81786.66 | 81786.66 | 0 | [6 empty] | Project Management | 81786.66 | 0 | 81786.66 | 0 | [6 empty] | 81786.86 | 0 | 81786.86 | Project Management | 81786.86
8 | T12.17 | S/H – Communications - Infraco | PR | 26634.66 | 0 | 26634.66 | 26634.66 | 0 | [6 empty] | Project Management | 26634.66 | 0 | 26634.66 | 0 | [6 empty] | 26635 | 0 | 26635 | Project Management | 26635
| T12.13-22 | Subtotal Stakeholder |  | 795708.76 | 5516 | 801224.76 | 801224.76 | 0 | [7 empty] | 793870.76 | 7354 | 801224.76 | 0 | [6 empty] | 800875.3 | 0 | 800875.3 |  | 755875.3
| T12 | Total COMMS / MARKETING |  | 3371679.43 | 58016 | 3429695.43 | 3429695.43 | 0 | [7 empty] | 3373188.43 | 56507 | 3429695.43 | 0 | [6 empty] | 2943742.33 | 10000 | 2953742.33 |  | 2956055.78
7 | T13.01 | Non Executive Board | Operations | 34352 | 0 | 34352 | 34352 | 0 | [6 empty] | Preparing for Operations | 34352 | 0 | 34352 | 0 | [6 empty] | 34352 | 0 | 34352 | Project Management | 34352
7 | T13.02 | Search Fees | Operations | 5000 | 0 | 5000 | 5000 | 0 | [6 empty] | Preparing for Operations | 5000 | 0 | 5000 | 0 | [6 empty] | 5000 | 0 | 5000 | Project Management | 5000
7 | T13.03 | Overheads | Operations | 2616653 | 55384.6154 | 2672037.6154 | 2672037.6154 | 0 | [6 empty] | Preparing for Operations | 2669844.8462 | 2192.7692 | 2672037.6154 | 0 | [6 empty] | 2388381 | 28000 | 2416381 | Project Management | 2428381
7 | T13.04 | Ticketing Machines | Operations | 93362 | 0 | 93362 | 93362 | 0 | [6 empty] | Preparing for Operations | 93362 | 0 | 93362 | 0 | [6 empty] | 80550 | 4215 | 84765 | Project Management | 91750
7 | T13.05 | Tram Display Costs | Operations | 22360.02 | 0 | 22360.02 | 22360.02 | 0 | [6 empty] | Preparing for Operations | 22360.02 | 0 | 22360.02 | 0 | [6 empty] | 22230 | 199 | 22429 | Project Management | 22429
| T13 | Total TEL |  | 2771727.02 | 55384.6154 | 2827111.6354 | 2827111.6354 | 0 | [7 empty] | 2824918.8662 | 2192.7692 | 2827111.6354 | 0 | [6 empty] | 2530513 | 32414 | 2562927 |  | 2581912
3 | T19.01.26 | Maintenance mobilisation and spare parts | Other Infraco | 662733.64 | 0 | 662733.64 | 662733.64 | 0 | [6 empty] | Infraco - Other | 662733.64 | 0 | 662733.64 | 0 | [6 empty] | 268484 | 0 | 268484 | Infrastructure | 268484
7 | T19.01.34 | Power for comissioning | Operations | 93548 | 25000 | 118548 | 118548 | 0 | [6 empty] | Preparing for Operations | 113202 | 5346 | 118548 | 0 | [6 empty] | 13596 | 6000 | 19596 | Infrastructure | 29760
7 | T19.07.05 | Ticket machines | Operations | 51200 | 0 | 51200 | 51200 | 0 | [6 empty] | Preparing for Operations | 51200 | 0 | 51200 | 0 | [6 empty] | 38925 | 8000 | 46925 | Infrastructure | 51925
| T13a | TEL - Project Costs |  | 807481.64 | 25000 | 832481.64 | 832481.64 | 0 | [7 empty] | 827135.64 | 5346 | 832481.64 | 0 | [6 empty] | 321005 | 14000 | 335005 |  | 350169
6 | T14.02 | Financial Consultancy | PM Other | 174893 | 0 | 174893 | 174893 | 0 | [6 empty] | Project Management | 174893 | 0 | 174893 | 0 | [6 empty] | 174893 | 0 | 174893 | Other Resources | 174893
6 | T14.03 | WP1 modelling (FM) | PM Other | 17184.03 | 0 | 17184.03 | 17184.03 | 0 | [6 empty] | Project Management | 17184.03 | 0 | 17184.03 | 0 | [6 empty] | 17184 | 0 | 17184 | Other Resources | 17184
6 | T14.04 | WP2 modelling (MVA) | PM Other | 11148.39 | 0 | 11148.39 | 11148.39 | 0 | [6 empty] | Project Management | 11148.39 | 0 | 11148.39 | 0 | [6 empty] | 11148 | 0 | 11148 | Other Resources | 11148
| T14 | Total SERVICE INTEGRATION |  | 203225.42 | 0 | 203225.42 | 203225.42 | 0 | [7 empty] | 203225.42 | 0 | 203225.42 | 0 | [6 empty] | 203225 | 0 | 203225 |  | 203225
6 | T15.01 | INFRACO (PUK) | PM Other | 261851.55 | 0 | 261851.55 | 261851.55 | 0 | [6 empty] | Project Management | 261851.55 | 0 | 261851.55 | 0 | [6 empty] | 261852 | 0 | 261852 | Other Resources | 261852
| T15 | Total PUK |  | 261851.55 | 0 | 261851.55 | 261851.55 | 0 | [7 empty] | 261851.55 | 0 | 261851.55 | 0 | [6 empty] | 261852 | 0 | 261852 |  | 261852
6 | T16.01 | Financial advisor 05/06 | PM Other | 285286 | 0 | 285286 | 285286 | 0 | [6 empty] | Project Management | 285286 | 0 | 285286 | 0 | [6 empty] | 285286 | 0 | 285286 | Other Resources | 285286
6 | T16.02 | Commercial advice | PM Other | 11864 | 0 | 11864 | 11864 | 0 | [6 empty] | Project Management | 11864 | 0 | 11864 | 0 | [6 empty] | 11864 | 0 | 11864 | Other Resources | 11864
| T16 | Total FINANCIAL ADVISOR |  | 297150 | 0 | 297150 | 297150 | 0 | [7 empty] | 297150 | 0 | 297150 | 0 | [6 empty] | 297150 | 0 | 297150 |  | 297150
6 | T17.01 | Insurance consultancy | PM Support | 318302 | 0 | 318302 | 318302 | 0 | [6 empty] | Project Management | 294670 | 23632 | 318302 | 0 | [6 empty] | 236767 | 659 | 237426 | Project Management | 235036
6 | T17.02 | OCIP | PM Support | 5241434 | -896020.88 | 4345413.12 | 4345413.12 | 0 | [6 empty] | Project Management | 4308078.9167 | 37334.2033 | 4345413.12 | 0 | [6 empty] | 3344531 | 97333 | 3441864 | Project Management | 3565835
6 | T17.03 | Claims below deductible | PM Support | 6111 | 0 | 6111 | 6111 | 0 | [6 empty] | Project Management | 6111 | 0 | 6111 | 0 | [6 empty] | 1012 | 0 | 1012 | Project Management | 1012
6 | T17.04 | Insurance Claims professional fees | PM Support | 69059 | 3297.3 | 72356.3 | 72356.3 | 0 | [6 empty] | Project Management | 68002.3 | 4354 | 72356.3 | 0 | [6 empty] | 25893 | 0 | 25893 | Project Management | 33764
6 | T17.05 | Recoverable insurance claims - MUDFA | PM Support | 219791 | 0 | 219791 | 219791 | 0 | [6 empty] | Project Management | 219791 | 0 | 219791 | 0 | [6 empty] | 214281 | 0 | 214281 | Project Management | 214281
6 | T17.06 | Non-recoverable insurance claims - MUDFA | PM Support | 510 | 0 | 510 | 510 | 0 | [6 empty] | Project Management | 510 | 0 | 510 | 0 | [6 empty] | 510 | 0 | 510 | Project Management | 510
6 | T17.07 | Recoverable insurance claims - Infraco | PM Support | 0 | 0 | 0 | 0 | 0 | [6 empty] | Project Management | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | Project Management | 0
6 | T17.08 | Non-recoverable insurance claims - Infraco | PM Support | 0 | 0 | 0 | 0 | 0 | [6 empty] | Project Management | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | Project Management | 0
| T17 | Total INSURANCE |  | 5855207 | -892723.58 | 4962483.42 | 4962483.42 | 0 | [7 empty] | 4897163.2167 | 65320.2033 | 4962483.42 | 0 | [6 empty] | 3822994 | 97992 | 3920986 |  | 4050438
4 | T01.12 | MUDFA Site Overheads | Utilities | 27720 | 0 | 27720 | 27720 | 0 | [6 empty] | Project Management | 27720 | 0 | 27720 | 0 | [6 empty] | 27720 | 0 | 27720 | Project Management | 27720
| T01.12 | MUDFA Site Overheads |  | 27720 | 0 | 27720 | 27720 | 0 | [7 empty] | 27720 | 0 | 27720 | 0 | [6 empty] | 27720 | 0 | 27720 |  | 27720
4 | T18.01.01 | Pre-construction Services | Utilities | 0 | 8743 | 8743 | 8743 | 0 | [6 empty] | Project Management | 8743 | 0 | 8743 | 0 | [6 empty] | 0 | 8743 | 8743 | Utillties | 8743
4 | T18.01.02 | Contract prelims | Utilities | 0 | 7765360 | 7765360 | 7765360 | 0 | [6 empty] | Project Management | 7765360 | 0 | 7765360 | 0 | [6 empty] | 0 | 7765360 | 7765360 | Utillties | 7765360
4 | T18.01.03 | Section 1a | Utilities | 0 | 4932189 | 4932189 | 4932189 | 0 | [6 empty] | Project Management | 4932189 | 0 | 4932189 | 0 | [6 empty] | 0 | 4932189 | 4932189 | Utillties | 4932189
4 | T18.01.04 | Section 1b | Utilities | 0 | 1532632 | 1532632 | 1532632 | 0 | [6 empty] | Project Management | 1532632 | 0 | 1532632 | 0 | [6 empty] | 0 | 1532632 | 1532632 | Utillties | 1532632
4 | T18.01.05 | Section 1c | Utilities | 0 | 5316033 | 5316033 | 5316033 | 0 | [6 empty] | Project Management | 5316033 | 0 | 5316033 | 0 | [6 empty] | 0 | 5316033 | 5316033 | Utillties | 5316033
4 | T18.01.06 | Section 1d | Utilities | 0 | 3171887 | 3171887 | 3171887 | 0 | [6 empty] | Project Management | 3171887 | 0 | 3171887 | 0 | [6 empty] | 0 | 3171887 | 3171887 | Utillties | 3171887
4 | T18.01.07 | Section 2 | Utilities | 0 | 2209689 | 2209689 | 2209689 | 0 | [6 empty] | Project Management | 2209689 | 0 | 2209689 | 0 | [6 empty] | 0 | 2209689 | 2209689 | Utillties | 2209689
4 | T18.01.13 | Section 5a | Utilities | 0 | 158424 | 158424 | 158424 | 0 | [6 empty] | Project Management | 158424 | 0 | 158424 | 0 | [6 empty] | 0 | 158424 | 158424 | Utillties | 158424
4 | T18.01.14 | Section 5b | Utilities | 0 | 601934 | 601934 | 601934 | 0 | [6 empty] | Project Management | 601934 | 0 | 601934 | 0 | [6 empty] | 0 | 601934 | 601934 | Utillties | 601934
4 | T18.01.16 | Section 6 | Utilities | 0 | 2015512 | 2015512 | 2015512 | 0 | [6 empty] | Project Management | 2015512 | 0 | 2015512 | 0 | [6 empty] | 0 | 2015512 | 2015512 | Utillties | 2015512
4 | T18.01.17 | Section 7 | Utilities | 0 | 2966791 | 2966791 | 2966791 | 0 | [6 empty] | Project Management | 2966791 | 0 | 2966791 | 0 | [6 empty] | 0 | 2966791 | 2966791 | Utillties | 2966791
4 | T18.01.18 | Unallocated to section | Utilities | 57252110 | -34944736 | 22307374 | 22307374 | 0 | [6 empty] | Project Management | 22307374 | 0 | 22307374 | 0 | [6 empty] | 57252110 | -34944736 | 22307374 | Utillties | 22307374
4 | T18.01.19 | Variations | Utilities | 0 | 3740542 | 3740542 | 3740542 | 0 | [6 empty] | Project Management | 3740542 | 0 | 3740542 | 0 | [6 empty] | 0 | 3740542 | 3740542 | Utillties | 3740542
4 | T18.01.21 | Claim(s) | Utilities | 0 | 525000 | 525000 | 525000 | 0 | [6 empty] | Project Management | 525000 | 0 | 525000 | 0 | [6 empty] | 0 | 525000 | 525000 | Utillties | 525000
| T18.01 | Subtotal MUDFA |  | 57252110 | 0 | 57252110 | 57252110 | 0 | [7 empty] | 57252110 | 0 | 57252110 | 0 | [6 empty] | 57252110 | 0 | 57252110 |  | 57252110
4 | T18.02.18 | SUC Costs | Utilities | 12223127.2 | 1323908.8 | 13547036 | 13547036 | 0 | [6 empty] | Project Management | 13547036 | 0 | 13547036 | 0 | [6 empty] | 11617196.25 | 4300513 | 15917709.25 | Utillties | 15917709.25
4 | T18.02.19 | MUDFA related Non SUC costs | Utilities | 3530240 | 33000 | 3563240 | 3563240 | 0 | [6 empty] | Project Management | 3563240 | 0 | 3563240 | 0 | [6 empty] | 3381724.75 | 10000 | 3391724.75 | Utillties | 3391724.75
4 | T18.02.22 | Betterment | Utilities | -3823624.05 | -910414 | -4734038.05 | -4734038.05 | 0 | [6 empty] | Project Management | -4734038.05 | 0 | -4734038.05 | 0 | [6 empty] | -3823624.05 | -2312192 | -6135816.05 | Utillties | -6135816.05
| T18.02 | Subtotal utilities |  | 11929743.15 | 446494.8 | 12376237.95 | 12376237.95 | 0 | [7 empty] | 12376237.95 | 0 | 12376237.95 | 0 | [6 empty] | 11175296.95 | 1998321 | 13173617.95 |  | 13173617.95
| T18 | Total MUDFA / Utilities |  | 69209573.15 | 446494.8 | 69656067.95 | 69656067.95 | 0 | [7 empty] | 69656067.95 | 0 | 69656067.95 | 0 | [6 empty] | 68455126.95 | 1998321 | 70453447.95 |  | 70453447.95
| T19.01.01 | Prelims | Infraco | 35312534 | 0 | 35312534 | 35312534 | 0 | [6 empty] | Infraco - Off Street | 35312534 | 0 | 35312534 | 0 | [6 empty] | 35312534 | 44777745.1277 | 80090279.1277 | Infrastructure | 80090279.1277
| T19.01.02 | Infraco early mobilisation | Infraco | 8537745 | 0 | 8537745 | 8537745 | 0 | [6 empty] | Infraco - Off Street | 8537745 | 0 | 8537745 | 0 | [6 empty] | 8537745 | -8537744.9998 | 0.00017 | Infrastructure | 0.00019
| T19.01.03 | Advanced purchases | Infraco | 18000000 | 0 | 18000000 | 18000000 | 0 | [6 empty] | Infraco - Off Street | 18000000 | 0 | 18000000 | 0 | [6 empty] | 18000000 | -17999999.9998 | 0.00017 | Infrastructure | 0.00019
| T19.01.05 | Section 1a | Infraco | 1748177 | 0 | 1748177 | 1748177 | 0 | [6 empty] | Infraco - Off Street | 1748177 | 0 | 1748177 | 0 | [6 empty] | 1748177 | -194661.21 | 1553515.79 | Infrastructure | 1553515.79
| T19.01.06 | Section 1b | Infraco | 89899 | 0 | 89899 | 89899 | 0 | [6 empty] | Infraco - Off Street | 89899 | 0 | 89899 | 0 | [6 empty] | 89899 | 17979.3804 | 107878.3804 | Infrastructure | 107878.3804
| T19.01.07 | Section 1c | Infraco | 150909 | 0 | 150909 | 150909 | 0 | [6 empty] | Infraco - Off Street | 150909 | 0 | 150909 | 0 | [6 empty] | 150909 | -0.33 | 150908.67 | Infrastructure | 150908.67
| T19.01.08 | Section 1d | Infraco | 2175744 | 0 | 2175744 | 2175744 | 0 | [6 empty] | Infraco - Off Street | 2175744 | 0 | 2175744 | 0 | [6 empty] | 2175744 | 31778.6153 | 2207522.6153 | Infrastructure | 2207522.6153
| T19.01.09 | Section 2 | Infraco | 853899 | 0 | 853899 | 853899 | 0 | [6 empty] | Infraco - Off Street | 853899 | 0 | 853899 | 0 | [6 empty] | 853899 | -0.784 | 853898.216 | Infrastructure | 853898.216
| T19.01.15 | Section 5a | Infraco | 209534 | 0 | 209534 | 209534 | 0 | [6 empty] | Infraco - Off Street | 209534 | 0 | 209534 | 0 | [6 empty] | 209534 | 48336.1217 | 257870.1217 | Infrastructure | 257870.1217
| T19.01.16 | Section 5b | Infraco | 5092985 | 0 | 5092985 | 5092985 | 0 | [6 empty] | Infraco - Off Street | 5092985 | 0 | 5092985 | 0 | [6 empty] | 5092985 | 462128.0272 | 5555113.0272 | Infrastructure | 5555113.0272
| T19.01.17 | Section 5c | Infraco | 1678137 | 0 | 1678137 | 1678137 | 0 | [6 empty] | Infraco - Off Street | 1678137 | 0 | 1678137 | 0 | [6 empty] | 1678137 | 65596.1101 | 1743733.1101 | Infrastructure | 1743733.1101
| T19.01.18 | Section 6 | Infraco | 7318571 | 0 | 7318571 | 7318571 | 0 | [6 empty] | Infraco - Off Street | 7318571 | 0 | 7318571 | 0 | [6 empty] | 7318571 | -323348.3007 | 6995222.6993 | Infrastructure | 6995222.6993
| T19.01.19 | Section 7 | Infraco | 1281425 | 0 | 1281425 | 1281425 | 0 | [6 empty] | Infraco - Off Street | 1281425 | 0 | 1281425 | 0 | [6 empty] | 1281425 | 8480.3505 | 1289905.3505 | Infrastructure | 1289905.3505
| T19.01.20 | Unallocated to section | Infraco | 18240000 | 6031705 | 24271705 | 24271705 | 0 | [6 empty] | Infraco - Off Street | 24271705 | 0 | 24271705 | 0 | [6 empty] | 18240000 | -18240000 | 0 | Infrastructure | 0
| T19.01.21 | NR Immunisation | Infraco | 476943 | 0 | 476943 | 476943 | 0 | [6 empty] | Infraco - Off Street | 476943 | 0 | 476943 | 0 | [6 empty] | 476943 | 258975.1026 | 735918.1026 | Infrastructure | 735918.1026
| T19.01.22 | Post mediation - Infraco - Off Street | Infraco | 157865628.1 | 20849822.9 | 178715451 | 199104596.67 | 0 | [6 empty] | Infraco - Off Street | 190473111.39 | -11757660.39 | 199104596.67 | 0 | [6 empty] | 27000000 | 9000000 | 36000000 | Infrastructure | 51339000
| T19.01.22b | Post mediation - Infraco - On Street | Infraco | 13325540.59 | 5666605.41 | 18992146 | 199104596.67 | 0 | [6 empty] | Infraco - On Street |  | 18992146 | 199104596.67 | 0 | [9 empty] | Infrastructure
3 | T19.01.22c | Post mediation - Infraco - Other | Other Infraco | 1397000 | 0 | 1397000 | 199104596.67 | 0 | [6 empty] | Infraco - Other |  | 1397000 | 199104596.67 | 0 | [9 empty] | Infrastructure
| T19.01.24 | Report adjustment | Infraco | 0 | 165540 | 165540 | 165540 | 0 | [6 empty] | Infraco - Off Street | 165540 | 0 | 165540 | 0 | [6 empty] | 0 | 0 | 0 | Infrastructure | 0
| T19.01.05-24 | Subtotal Construction |  | 273754670.36 | 32713673.31 | 306468343.67 | 306468343.67 | 0 | [7 empty] | 297836858.39 | 8631485.61 | 306468343.67 | 0 | [6 empty] | 128166502 | 9375263.2111 | 137541765.2111 |  | 152880765.2111
| T19.01.35 | Variations - Prelims | Infraco | 203845 | 0 | 203845 | 203845 | 0 | [6 empty] | Infraco - Off Street | 203845 | 0 | 203845 | 0 | [6 empty] | 203845 | 10887 | 214732 | Infrastructure | 214732
| T19.01.36 | Variations - Section 1a | Infraco | 228259 | 0 | 228259 | 228259 | 0 | [6 empty] | Infraco - Off Street | 228259 | 0 | 228259 | 0 | [6 empty] | 228259 | 9799.51 | 238058.51 | Infrastructure | 227239.51
| T19.01.37 | Variations - Section 1b | Infraco | 190199 | 0 | 190199 | 190199 | 0 | [6 empty] | Infraco - Off Street | 190199 | 0 | 190199 | 0 | [6 empty] | 238339 | 139062 | 377401 | Infrastructure | 377401
| T19.01.38 | Variations - Section 1c | Infraco | 134688 | 0 | 134688 | 134688 | 0 | [6 empty] | Infraco - Off Street | 134688 | 0 | 134688 | 0 | [6 empty] | 134688 | 283563 | 418251 | Infrastructure | 418251
| T19.01.39 | Variations - Section 1d | Infraco | 10360577.75 | 0 | 10360577.75 | 10360577.75 | 0 | [6 empty] | Infraco - Off Street | 10360577.75 | 0 | 10360577.75 | 0 | [6 empty] | 10360577.75 | -202075.75 | 10158502 | Infrastructure | 10158502
| T19.01.40 | Variations - Section 2 | Infraco | 342609 | 0 | 342609 | 342609 | 0 | [6 empty] | Infraco - Off Street | 342609 | 0 | 342609 | 0 | [6 empty] | 342609 | 57201 | 399810 | Infrastructure | 420185
| T19.01.46 | Variations - Section 5a | Infraco | 1131441 | 0 | 1131441 | 1131441 | 0 | [6 empty] | Infraco - Off Street | 1131441 | 0 | 1131441 | 0 | [6 empty] | 1131441 | 245477 | 1376918 | Infrastructure | 1376918
| T19.01.47 | Variations - Section 5b | Infraco | 1677856 | 0 | 1677856 | 1677856 | 0 | [6 empty] | Infraco - Off Street | 1677856 | 0 | 1677856 | 0 | [6 empty] | 1677856 | 196527 | 1874383 | Infrastructure | 1874383
| T19.01.48 | Variations - Section 5c | Infraco | 1471584 | 0 | 1471584 | 1471584 | 0 | [6 empty] | Infraco - Off Street | 1471584 | 0 | 1471584 | 0 | [6 empty] | 1471584 | 394724.42 | 1866308.42 | Infrastructure | 1866308.42
| T19.01.49 | Variations - Section 6 | Infraco | 2239808 | 0 | 2239808 | 2239808 | 0 | [6 empty] | Infraco - Off Street | 2239808 | 0 | 2239808 | 0 | [6 empty] | 2239808 | 314155 | 2553963 | Infrastructure | 2553963
| T19.01.50 | Variations - Section 7 | Infraco | 3075419 | 0 | 3075419 | 3075419 | 0 | [6 empty] | Infraco - Off Street | 3075419 | 0 | 3075419 | 0 | [6 empty] | 3075419 | 1046475.55 | 4121894.55 | Infrastructure | 4121894.55
| T19.01.27 | Variations - Unallocated to section | Infraco | 1542914 | 0 | 1542914 | 1542914 | 0 | [6 empty] | Infraco - Off Street | 1542914 | 0 | 1542914 | 0 | [6 empty] | 1403111 | 1238864 | 2641975 | Infrastructure | 2641975
| T19.01.52 | Variations - Princes Street | Infraco | 338806 | -338806 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | [6 empty] | 313806 | 0 | 313806 | Infrastructure | 313806
| T19.01.53 | Variations - Line 1b Costs | Infraco | 3200000 | -3200000 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | [6 empty] | 3200000 | 0 | 3200000 | Infrastructure | 3200000
| T19.01.27, 35-54 | Subtotal Variations / Changes |  | 26138005.75 | -3538806 | 22599199.75 | 22599199.75 | 0 | [7 empty] | 22599199.75 | 0 | 22599199.75 | 0 | [6 empty] | 26021342.75 | 3734659.73 | 29756002.48 |  | 29765558.48
| T19.01.28 | Infraco contingency | Infraco | 472101 | -472101 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | [6 empty] | 415418 | -450.4583 | 414967.5417 | Infrastructure | 419967.5417
| T19.01.56 | Accommodation Works | Infraco | 203680 | 0 | 203680 | 203680 | 0 | [6 empty] | Infraco - Off Street | 203680 | 0 | 203680 | 0 | [6 empty] | 203680 | 286320 | 490000 | Infrastructure | 490000
| T19.01.57 | PICOPS / COSS / Possession Protection Staff support when undertaking works adjacent or over the railway | Infraco | 55000 | 0 | 55000 | 55000 | 0 | [6 empty] | Infraco - Off Street | 55000 | 0 | 55000 | 0 | [6 empty] | 55000 | 25000 | 80000 | Infrastructure | 80000
| T19.01.60 | Pumped surface water outfall at A8 underpass (by depot) | Infraco | 0 | 0 | 0 | [8 empty] | Infraco - Off Street | 0 | 0 | [8 empty] | 0 | 50000 | 50000 | Infrastructure | 50000
| T19.01.64 | Extra over for shell grip at junctions | Infraco | 74311.23 | 0 | 74311.23 | 74311.23 | 0 | [6 empty] | Infraco - Off Street | 74311.23 | 0 | 74311.23 | 0 | [6 empty] | 74311.23 | 18246.77 | 92558 | Infrastructure | 92558
| T19.01.65 | Allowance for SP connections to new street lights and new traffic signals | Infraco | [11 empty] | Infraco - Off Street | 0 | 0 | [8 empty] | 0 | 15287 | 15287 | Infrastructure | 15287
| T19.01.66 | UTC associated with the delivery of the alignment | Infraco | 533640 | 0 | 533640 | 533640 | 0 | [6 empty] | Infraco - Off Street | 533640 | 0 | 533640 | 0 | [6 empty] | 533640 | 0 | 533640 | Infrastructure | 533640
| T19.01.69 | Allowance for minor utility diversions | Infraco | 294248 | 0 | 294248 | 294248 | 0 | [6 empty] | Infraco - Off Street | 294248 | 0 | 294248 | 0 | [6 empty] | 236152.5 | 9999.5 | 246152 | Infrastructure | 246152
| T19.01.70 | Archaeological Officer – impact on productivity | Infraco | [11 empty] | Infraco - Off Street | 0 | 0 | [8 empty] | 0 | 120000 | 120000 | Infrastructure | 120000
| T19.01.75 | SP connections to the depot and IPR | Infraco | 580652 | 0 | 580652 | 580652 | 0 | [6 empty] | Infraco - Off Street | 580652 | 0 | 580652 | 0 | [6 empty] | 580652 | 143073 | 723725 | Infrastructure | 723725
| T19.01.76 | SP connections to Phase 1a sub-stations | Infraco | [12 empty] | 0 | 0 | [8 empty] | 0 | 400000 | 400000 | Infrastructure | 400000
| T19.01.55-90 | Subtotal Provisional sums |  | 2213632.23 | -472101 | 1741531.23 | 1741531.23 | 0 | [7 empty] | 1741531.23 | 0 | 1741531.23 | 0 | [6 empty] | 2098853.73 | 1067475.8117 | 3166329.5417 |  | 3171329.5417
| T19.01 | Subtotal Infraco main works |  | 302106308.34 | 28702766.31 | 330809074.65 | 330809074.65 | 0 | [7 empty] | 322177589.37 | 8631485.61 | 330809074.65 | 0 | [6 empty] | 156286698.48 | 14177398.7528 | 170464097.2328 |  | 185817653.2328
1 | T19.02.03 | Environ. impacts - badgers | Off Road Other | 26576 | 0 | 26576 | 26576 | 0 | [6 empty] | Project Management | 26576 | 0 | 26576 | 0 | [6 empty] | 26576 | 0 | 26576 | Infrastructure | 26576
1 | T19.02.04 | Invasive species | Off Road Other | 254950 | 0 | 254950 | 254950 | 0 | [6 empty] | Project Management | 254950 | 0 | 254950 | 0 | [6 empty] | 253500 | 0 | 253500 | Infrastructure | 253500
| T19.02 | Subtotal advance works |  | 281526 | 0 | 281526 | 281526 | 0 | [7 empty] | 281526 | 0 | 281526 | 0 | [6 empty] | 280076 | 0 | 280076 |  | 280076
1 | T19.03.01 | Unallocated | Off Road Other | 134574 | 0 | 134574 | 134574 | 0 | [6 empty] | Project Management | 134574 | 0 | 134574 | 0 | [6 empty] | 134574 | 0 | 134574 | Infrastructure | 134574
1 | T19.03.02 | Set up / mobilisation | Off Road Other | 179741 | 0 | 179741 | 179741 | 0 | [6 empty] | Project Management | 179741 | 0 | 179741 | 0 | [6 empty] | 179741 | 0 | 179741 | Infrastructure | 179741
1 | T19.03.03 | Phase 1 (150,000m3) | Off Road Other | 2914685 | 0 | 2914685 | 2914685 | 0 | [6 empty] | Project Management | 2914685 | 0 | 2914685 | 0 | [6 empty] | 2914685 | 0 | 2914685 | Infrastructure | 2914685
1 | T19.03.04 | Phase 2 (100,000m3) | Off Road Other | 2209378 | 0 | 2209378 | 2209378 | 0 | [6 empty] | Project Management | 2209378 | 0 | 2209378 | 0 | [6 empty] | 2209378 | 0 | 2209378 | Infrastructure | 2209378
| T19.03 | Subtotal depot advance works |  | 5438378 | 0 | 5438378 | 5438378 | 0 | [7 empty] | 5438378 | 0 | 5438378 | 0 | [6 empty] | 5438378 | 0 | 5438378 |  | 5438378
1 | T19.07.04 | Power - Network reinforcement | Off Road Other | [11 empty] | Project Management | 0 | 0 | [8 empty] | 0 | 216674 | 216674 | Infrastructure | 216674
1 | T19.07.06 | IPR2 contingency | Off Road Other | 259534 | 0 | 259534 | 259534 | 0 | [6 empty] | Project Management | 259534 | 0 | 259534 | 0 | [6 empty] | 259534 | 40466 | 300000 | Infrastructure | 300000
1 | T19.07.08 | Murrayfield modifications | Off Road Other | 1154856 | -93289 | 1061567 | 1061567 | 0 | [6 empty] | Project Management | 1061567 | 0 | 1061567 | 0 | [6 empty] | 1202961 | -17118 | 1185843 | Infrastructure | 1185843
1 | T19.07.10 | Office land rental | Off Road Other | 333267 | -1788.4615 | 331478.5385 | 331478.5385 | 0 | [6 empty] | Project Management | 324401.6154 | 7076.9231 | 331478.5385 | 0 | [6 empty] | 207124 | 8105.88 | 215229.88 | Infrastructure | 226743.88
1 | T19.07.11 | Leith goods yard | Off Road Other | 87296 | 85169.5385 | 172465.5385 | 172465.5385 | 0 | [6 empty] | Project Management | 168450.1538 | 4015.3846 | 172465.5385 | 0 | [6 empty] | 80288 | 4253.0223 | 84541.0223 | Infrastructure | 89541.0223
1 | T19.07.12 | Traffic management design | Off Road Other | 87558 | 11108.6667 | 98666.6667 | 98666.6667 | 0 | [6 empty] | Project Management | 94000 | 4666.6667 | 98666.6667 | 0 | [6 empty] | 196307 | -154185 | 42122 | Infrastructure | 42122
1 | T19.07.17 | Burnside Road - Construction Costs | Off Road Other | 1548494 | -25412.01 | 1523081.99 | 1523081.99 | 0 | [6 empty] | Project Management | 1523081.99 | 0 | 1523081.99 | 0 | [6 empty] | 1485212 | 37869.99 | 1523081.99 | Infrastructure | 1523081.99
1 | T19.07.18 | Burnside Road - BAA Costs | Off Road Other | 410792.19 | 3851.27 | 414643.46 | 414643.46 | 0 | [6 empty] | Project Management | 414643.46 | 0 | 414643.46 | 0 | [6 empty] | 410792.19 | 3851.27 | 414643.46 | Infrastructure | 414643.46
1 | T19.07.19 | Burnside Road - Consultancy Costs | Off Road Other | 200218 | 2228.76 | 202446.76 | 202446.76 | 0 | [6 empty] | Project Management | 202446.76 | 0 | 202446.76 | 0 | [6 empty] | 198867.83 | 3578.93 | 202446.76 | Infrastructure | 202446.76
1 | T19.07.20 | Burnside Road - Other Costs | Off Road Other | 40246 | 85413.9 | 125659.9 | 125659.9 | 0 | [6 empty] | Project Management | 125659.9 | 0 | 125659.9 | 0 | [6 empty] | 16736 | 58524.9 | 75260.9 | Infrastructure | 75260.9
4 | T19.07.21 | BAA MUDFA - Construction Costs | Utilities | 428653 | 10991.44 | 439644.44 | 439644.44 | 0 | [6 empty] | Project Management | 439644.44 | 0 | 439644.44 | 0 | [6 empty] | 428653 | 10990.44 | 439643.44 | Infrastructure | 439643.44
4 | T19.07.22 | BAA MUDFA - BAA Costs | Utilities | 201977 | 3023.07 | 205000.07 | 205000.07 | 0 | [6 empty] | Project Management | 205000.07 | 0 | 205000.07 | 0 | [6 empty] | 201977 | 10525.07 | 212502.07 | Infrastructure | 212502.07
4 | T19.07.23 | BAA MUDFA - Consultancy Costs | Utilities | 186486 | -0.29 | 186485.71 | 186485.71 | 0 | [6 empty] | Project Management | 186485.71 | 0 | 186485.71 | 0 | [6 empty] | 186486 | -0.29 | 186485.71 | Infrastructure | 186485.71
1 | T19.07.25 | Forth Ports Section 1a | Off Road Other | 1431497 | -45064 | 1386433 | 1386433 | 0 | [6 empty] | Project Management | 1386433 | 0 | 1386433 | 0 | [6 empty] | 1256337.18 | 183794.82 | 1440132 | Infrastructure | 1440132
| T19.01-08, 10-12,17-20 | Subtotal non Infraco works |  | 6370874.19 | 36232.8836 | 6407107.0736 | 6407107.0736 | 0 | [7 empty] | 6391348.0992 | 15758.9744 | 6407107.0736 | 0 | [6 empty] | 6131275.2 | 407331.0323 | 6538606.2323 |  | 6555120.2323
1 | T19.07.26 | SW Global Resourcing | Off Road Other | 435929 | 0 | 435929 | 435929 | 0 | [6 empty] | Project Management | 435929 | 0 | 435929 | 0 | [6 empty] | 435899 | 4554 | 440453 | Infrastructure | 440453
1 | T19.07.27 | Stray Current Monitoring | Off Road Other | 102629.99 | 0 | 102629.99 | 102629.99 | 0 | [6 empty] | Project Management | 102629.99 | 0 | 102629.99 | 0 | [6 empty] | 101205 | 45018 | 146223 | Infrastructure | 146223
4 | T19.07.28 | Manhole at Balbirnie Place (Frontline cost) | Utilities | 274133 | 5540 | 279673 | 279673 | 0 | [6 empty] | Project Management | 279673 | 0 | 279673 | 0 | [6 empty] | 215407.31 | -115274.31 | 100133 | Infrastructure | 100133
4 | T19.07.29 | SGN Gas main haymarket | Utilities | 43565 | -43565 | 0 | 0 | 0 | [6 empty] | Project Management | 0 | 0 | 0 | 0 | [6 empty] | 43565.11 | -43565.11 | 0 | Infrastructure | 0
1 | T19.07.30 | Crash Gate 10 | Off Road Other | 125293.79 | 13254.9333 | 138548.7233 | 138548.7233 | 0 | [6 empty] | Project Management | 135234.99 | 3313.7333 | 138548.7233 | 0 | [6 empty] | 125293.79 | 0.21 | 125294 | Infrastructure | 125294
1 | T19.07.31 | Constitution Street – Mock-up | Off Road Other | 38351 | 0 | 38351 | 38351 | 0 | [6 empty] | Project Management | 38351 | 0 | 38351 | 0 | [6 empty] | 38351 | 0.40333 | 38351.4033 | Infrastructure | 38351.4033
4 | T19.07.32 | SGN Gas diversion | Utilities | 544192 | 112826 | 657018 | 657018 | 0 | [6 empty] | Project Management | 322018 | 335000 | 657018 | 0 | [6 empty] | 180750 | 199622 | 380372 | Infrastructure | 385372
4 | T19.07.33 | MUDFA scoped side entry manholes | Utilities | 550302.71 | 22276.29 | 572579 | 572579 | 0 | [6 empty] | Project Management | 572579 | 0 | 572579 | 0 | [6 empty] | 550302.71 | 44720.29 | 595023 | Infrastructure | 595023
4 | T19.07.35 | Section 1a Utilities | Utilities | 3070008 | 37472.0585 | 3107480.0585 | 3107480.0585 | 0 | [6 empty] | Project Management | 3107480.0585 | 0 | 3107480.0585 | 0 | [6 empty] | 3057832 | 423854.0585 | 3481686.0585 | Infrastructure | 3481686.0585
4 | T19.07.36 | Clancy Docwra Utilities Works | Utilities | 5264981.42 | 439136.58 | 5704118 | 5704118 | 0 | [6 empty] | Project Management | 5704118 | 0 | 5704118 | 0 | [6 empty] | 5724249 | 427770 | 6152019 | Infrastructure | 6152019
4 | T19.07.37 | Section 5C Edinburgh Park Clancy | Utilities | 243359 | 5344 | 248703 | 248703 | 0 | [6 empty] | Project Management | 248703 | 0 | 248703 | 0 | [6 empty] | 243359 | 13238 | 256597 | Infrastructure | 256597
1 | T19.07.38 | Mass Barier Costs | Off Road Other | [11 empty] | Project Management | 0 | 0 | [8 empty] | 0 | 221687 | 221687 | Infrastructure | 221687
4 | T19.07.40 | South Gyle - Sewer Diversion | Utilities | 836000 | 37240 | 873240 | 873240 | 0 | [6 empty] | Project Management | 873240 | 0 | 873240 | 0 | [6 empty] | 809513 | -11305 | 798208 | Infrastructure | 798208
1 | T19.07.41 | Visirail / Rubber Kerbs | Off Road Other | 879759.57 | 46907.0967 | 926666.6667 | 926666.6667 | 0 | [6 empty] | Project Management | 920000 | 6666.6667 | 926666.6667 | 0 | [6 empty] | 887732 | 14685 | 902417 | Infrastructure | 906782
4 | T19.07.42 | SUC Costs - from MUDFA | Utilities | 38532 | 0 | 38532 | 38532 | 0 | [6 empty] | Project Management | 38532 | 0 | 38532 | 0 | [6 empty] | 13648 | -13648 | 0 | Infrastructure | 0
1 | T19.07.46 | Bus Tracker Work | Off Road Other | 40260 | 0 | 40260 | 40260 | 0 | [6 empty] | Project Management | 40260 | 0 | 40260 | 0 | [6 empty] | 40260 | 4740 | 45000 | Infrastructure | 45000
1 | T19.07.47 | POL HA Temp Retention Works | Off Road Other | 113632 | 0 | 113632 | 113632 | 0 | [6 empty] | Project Management | 113632 | 0 | 113632 | 0 | [6 empty] | 100000 | 0 | 100000 | Infrastructure | 100000
4 | T19.07.48 | Cabling at Tower Place Bridge Diversion Works | Utilities | 6309 | 19558 | 25867 | 25867 | 0 | [6 empty] | Project Management | 25867 | 0 | 25867 | 0 | [6 empty] | 7561 | 13747 | 21308 | Infrastructure | 21308
| T19.07.26-48 | Subtotal non Infraco changes |  | 12607237.48 | 695989.9585 | 13303227.4385 | 13303227.4385 | 0 | [7 empty] | 12958247.0385 | 344980.4 | 13303227.4385 | 0 | [6 empty] | 12574927.92 | 1229843.5418 | 13804771.4618 |  | 13814136.4618
1 | T19.07.09 | Fastlink alternative | Off Road Other | 516214 | 32786 | 549000 | 549000 | 0 | [6 empty] | Project Management | 549000 | 0 | 549000 | 0 | [6 empty] | 546558 | 2442 | 549000 | Infrastructure | 549000
1 | T19.07.13 | Ancient monuments | Off Road Other | 70226 | 34440.6667 | 104666.6667 | 104666.6667 | 0 | [6 empty] | Project Management | 96000 | 8666.6667 | 104666.6667 | 0 | [6 empty] | 51460 | 10548 | 62008 | Infrastructure | 62008
1 | T19.07.14 | TMi cycle integration study | Off Road Other | 19656.9 | 0 | 19656.9 | 19656.9 | 0 | [6 empty] | Project Management | 19656.9 | 0 | 19656.9 | 0 | [6 empty] | 19656.9 | 0.1 | 19657 | Infrastructure | 19657
1 | T19.07.15 | Siemens out of hours monitoring | Off Road Other | 66716 | 0 | 66716 | 66716 | 0 | [6 empty] | Project Management | 66716 | 0 | 66716 | 0 | [6 empty] | 66716 | 0 | 66716 | Infrastructure | 66716
4 | T19.07.49 | Gogar 250 Water Main - Clancy | Utilities | 295207 | 11477 | 306684 | 306684 | 0 | [6 empty] | Project Management | 306684 | 0 | 306684 | 0 | [6 empty] | 55 | 80118 | 80173 | Infrastructure | 190430
4 | T19.07.50 | Remedial Works to SW Manholes - Crummock | Utilities | 27193.01 | 1415.99 | 28609 | 28609 | 0 | [6 empty] | Project Management | 28609 | 0 | 28609 | 0 | [6 empty] | 0 | 0 | 0 | Infrastructure | 15000
4 | T19.07.51 | SW Abandonments | Utilities | 310959 | 32127 | 343086 | 343086 | 0 | [6 empty] | Project Management | 343086 | 0 | 343086 | 0 | [6 empty] | 0 | 0 | 0 | Infrastructure | 80000
4 | T19.07.52 | Assembly St Temp SW 300mm Diversion | Utilities | 91786 | 5241 | 97027 | 97027 | 0 | [6 empty] | Project Management | 97027 | 0 | 97027 | 0 | [6 empty] | 110 | -110 | 0 | Infrastructure | 30000
1 | T19.07.53 | Traffic Management Costs | Off Road Other | 657635 | 13735.7333 | 671370.7333 | 671370.7333 | 0 | [6 empty] | Project Management | 667936.8 | 3433.9333 | 671370.7333 | 0 | [6 empty] | 0 | 588411 | 588411 | Infrastructure | 622457
4 | T19.07.54 | Remedial works for Scottish Water | Utilities | 8430.19 | -0.19 | 8430 | 8430 | 0 | [6 empty] | Project Management | 8430 | 0 | 8430 | 0 | [9 empty] | Infrastructure | 0
4 | T19.07.55 | McNicholas Utilities Works | Utilities | 10556109 | 3021891 | 13578000 | 13578000 | 0 | [6 empty] | Utilities (Post Mediation & Legacy) | 11337000 | 2241000 | 13578000 | 0 | [9 empty] | Infrastructure | 0
1 | T19.07.60 | Reporting adjustments from T19.01 | Off Road Other | 41290 | 4058594 | 4099884 | 4099884 | 0 | [6 empty] | Project Management | 4099884 | 0 | 4099884 | 0 | [6 empty] | 0 | 0 | 0 | Infrastructure | 0
2 | T19.07.61 | York Place Direct Works | On Road Other | 178000 | 0 | 178000 | 178000 | 0 | [6 empty] | Project Management | 0 | 178000 | 178000 | 0 | [6 empty] | 0 | 0 | 0 | Infrastructure | 0
| T19.07.09,13-15,49-67 | Subtotal non Infraco Provisional Sums |  | 12839422.1 | 7211708.2 | 20051130.3 | 20051130.3 | 0 | [7 empty] | 17620029.7 | 2431100.6 | 20051130.3 | 0 | [6 empty] | 684555.9 | 681409.1 | 1365965 |  | 1635268
| T19.07 | Subtotal Non Infraco works |  | 31817533.77 | 7943931.0421 | 39761464.8121 | 39761464.8121 | 0 | [7 empty] | 36969624.8377 | 2791839.9744 | 39761464.8121 | 0 | [6 empty] | 19390759.02 | 2318583.6741 | 21709342.6941 |  | 22004524.6941
| T19 | Total Infraco |  | 339643746.11 | 36646697.3521 | 376290443.4621 | 376290443.4621 | 0 | [7 empty] | 364867118.2077 | 11423325.5844 | 376290443.4621 | 0 | [6 empty] | 181395911.5 | 16495982.4269 | 197891893.9269 |  | 213540631.9269
5 | T20.01.01 | Prelims | Vehicles | 6215 | 0 | 6215 | 6215 | 0 | [6 empty] | Tram vehicles | 6215 | 0 | 6215 | 0 | [6 empty] | 6215 | 0 | 6215 | Tram vehicles | 6215
5 | T20.01.03 | Approval of preliminary design | Vehicles | 1100833 | 0 | 1100833 | 1100833 | 0 | [6 empty] | Tram vehicles | 1100833 | 0 | 1100833 | 0 | [6 empty] | 1100833 | 0 | 1100833 | Tram vehicles | 1100833
5 | T20.01.05 | Approval of final design / mock up | Vehicles | 1651249 | 0 | 1651249 | 1651249 | 0 | [6 empty] | Tram vehicles | 1651249 | 0 | 1651249 | 0 | [6 empty] | 1651249 | 0 | 1651249 | Tram vehicles | 1651249
5 | T20.01.07 | Commencenent of tram works | Vehicles | 9687326 | 0 | 9687326 | 9687326 | 0 | [6 empty] | Tram vehicles | 9687326 | 0 | 9687326 | 0 | [6 empty] | 9687326 | 0 | 9687326 | Tram vehicles | 9687326
5 | T20.01.08 | Completion 1st set bodyshells | Vehicles | 3302497 | 0 | 3302497 | 3302497 | 0 | [6 empty] | Tram vehicles | 3302497 | 0 | 3302497 | 0 | [6 empty] | 3302497 | 0 | 3302497 | Tram vehicles | 3302497
5 | T20.01.09 | Completion 1st set bogies | Vehicles | 3302497 | 0 | 3302497 | 3302497 | 0 | [6 empty] | Tram vehicles | 3302497 | 0 | 3302497 | 0 | [6 empty] | 3302497 | 0 | 3302497 | Tram vehicles | 3302497
5 | T20.01.10 | Completion 1st tram assembly | Vehicles | 3302497 | 0 | 3302497 | 3302497 | 0 | [6 empty] | Tram vehicles | 3302497 | 0 | 3302497 | 0 | [6 empty] | 3302497 | 0 | 3302497 | Tram vehicles | 3302497
5 | T20.01.11 | Completion factory based type testing | Vehicles | 3852914 | 0 | 3852914 | 3852914 | 0 | [6 empty] | Tram vehicles | 3852914 | 0 | 3852914 | 0 | [6 empty] | 3852914 | 0 | 3852914 | Tram vehicles | 3852914
5 | T20.01.12 | Delivery of preliminary tram maintenance manuals | Vehicles | 3302497 | 0 | 3302497 | 3302497 | 0 | [6 empty] | Tram vehicles | 3302497 | 0 | 3302497 | 0 | [6 empty] | 3302497 | 0 | 3302497 | Tram vehicles | 3302497
5 | T20.01.13 | Delivery of spares | Vehicles | 1100832.5 | 0 | 1100832.5 | 1100832.5 | 0 | [6 empty] | Tram vehicles | 1100832.5 | 0 | 1100832.5 | 0 | [6 empty] | 1100832.5 | 0 | 1100832.5 | Tram vehicles | 1100832.5
5 | T20.01.14 | Delivery of final documentation | Vehicles | 0 | 1100832.5 | 1100832.5 | 1100832.5 | 0 | [6 empty] | Tram vehicles | 1100832.5 | 0 | 1100832.5 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.15 | Delivery of special tools | Vehicles | 550416.25 | 0 | 550416.25 | 550416.25 | 0 | [6 empty] | Tram vehicles | 550416.25 | 0 | 550416.25 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.16 | Completion of driver training | Vehicles | 550416 | 0 | 550416 | 550416 | 0 | [6 empty] | Tram vehicles | 550416 | 0 | 550416 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.17 | Completion of maintainer training | Vehicles | 0 | 550416.25 | 550416.25 | 550416.25 | 0 | [6 empty] | Tram vehicles | 550416.25 | 0 | 550416.25 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.21 | Supply chain mobilisation | Vehicles | 11075131 | 0 | 11075131 | 11075131 | 0 | [6 empty] | Tram vehicles | 11075131 | 0 | 11075131 | 0 | [6 empty] | 11075131 | 0 | 11075131 | Tram vehicles | 11075131
5 | T20.01.22 | Adjustment | Vehicles | 0 | 0 | 0 | 0 | 0 | [6 empty] | Tram vehicles | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.23 | Delivery of trams | Vehicles | 4513413.26 | 0 | 4513413.26 | 4513413.26 | 0 | [6 empty] | Tram vehicles | 4513413.26 | 0 | 4513413.26 | 0 | [6 empty] | 4073080 | 440362 | 4513442 | Tram vehicles | 4513442
5 | T20.01.24 | Testing and commissioning | Vehicles | 2752081 | 660499.5 | 3412580.5 | 3412580.5 | 0 | [6 empty] | Tram vehicles | 3192414 | 220166.5 | 3412580.5 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
5 | T20.01.25 | Advance maintenance mobilisation | Vehicles | 1799024.98 | 317475 | 2116499.98 | 2116499.98 | 0 | [6 empty] | Tram vehicles | 2116499.98 | 0 | 2116499.98 | 0 | [6 empty] | 846600 | 0 | 846600 | Tram vehicles | 846600
5 | T20.01.26 | Depot equipment | Vehicles | 703036.02 | 0 | 703036.02 | 703036.02 | 0 | [6 empty] | Tram vehicles | 703036.02 | 0 | 703036.02 | 0 | [6 empty] | 465477 | 0 | 465477 | Tram vehicles | 465477
5 | T20.01.27 | Variations / changes | Vehicles | 481478 | 37500 | 518978 | 518978 | 0 | [6 empty] | Tram vehicles | 506478 | 12500 | 518978 | 0 | [6 empty] | 378333 | 0 | 378333 | Tram vehicles | 378333
5 | T20.01.28 | Contingency | Vehicles | 13713.97 | 0 | 13713.97 | 13713.97 | 0 | [6 empty] | Tram vehicles | 13713.97 | 0 | 13713.97 | 0 | [6 empty] | 11464 | 0 | 11464 | Tram vehicles | 11464
5 | T20.01.29 | Claims | Vehicles | 5112306 | 0 | 5112306 | 5112306 | 0 | [6 empty] | Tram vehicles | 5112306 | 0 | 5112306 | 0 | [6 empty] | 0 | 0 | 0 | Tram vehicles | 0
| T20.01 | Subtotal Tramco main works |  | 58160373.98 | 2666723.25 | 60827097.23 | 60827097.23 | 0 | [7 empty] | 60594430.73 | 232666.5 | 60827097.23 | 0 | [6 empty] | 47459442.5 | 440362 | 47899804.5 |  | 47899804.5
6 | T99.01 | Miscellaneous | PM Other | 168727.64 | 0 | 168727.64 | 168727.64 | 0 | [6 empty] | Project Management | 168727.64 | 0 | 168727.64 | 0 | [6 empty] | 168727.64 | 0 | 168727.64 | Project Management | 168727.64
6 | T99.02 | Previous years | PM Other | 3093000 | 0 | 3093000 | 3093000 | 0 | [6 empty] | Project Management | 3093000 | 0 | 3093000 | 0 | [6 empty] | 3093000 | 0 | 3093000 | Project Management | 3093000
| T99 | Total Miscellaneous |  | 3261727.64 | 0 | 3261727.64 | 3261727.64 | 0 | [7 empty] | 3261727.64 | 0 | 3261727.64 | 0 | [6 empty] | 3261727.64 | 0 | 3261727.64 |  | 3261727.64
| T999 | Total |  | 626725361.29 | 42365508.9825 | 669090870.2725 | 669090870.2725 | 0 | [7 empty] | 656362184.4606 | 12728686.0519 | 669090870.2725 | 0 | [6 empty] | 423646040.52 | 37788942.8069 | 461434983.3269 |  | 478273186.2969
[6 empty] | 669090870.2725 | [10 empty] | 12728685.8119
-0.24
[6 empty] | 7710515.51 | [9 empty] | 7683305.51 | 27204 | [10 empty] | 6357646.57 |  | 6366954.57