## Profile
Costs to Go | 231.75 | 2011/12 |  |  |  | 2012/13 |  |  |  | 2013/14 |  |  |  | 2014/15
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Infraco* | 184.19 |  |  | 54.2318 | 33.7632 | 23.4342 | 17.3396 | 17.2058 | 14.7938 | 8.2921 | 5.5505 | 4.412 | 3.8374 | 1.3297
Utilities | 2.912 | 2011/12 Q4: 2.912
CAF | 14.4 | 2011/12 Q4: 14.4
PM and Other** | 30.25 |  |  | 8.9066 | 5.545 | 3.8487 | 2.8477 | 2.8258 | 2.4296 | 1.3618 | 0.91157 | 0.7246 | 0.63022 | 0.21838
| 231.752 | 2011/12 Q4: 119.7586; 2012/13 Q4: 84.725; 2013/14 Q4: 25.7202; 2014/15 Q4: 1.5481
*On and Off Street to go apportioned as a percentage of quantifed off street milestones
** Assumes PM matches construction phasing

## Summary
Edinburgh Tram Budget
Post Settlement Agreement Budget
Budget Development - August 2011
£m
Off-Street Lump Sum Price | 360060000
Airport to Haymarket (Infraco) (A) | 360060000
On Street Budget;
On-street contract price - Bilfinger Berger | 27818000
On-street contract price - Siemens | 11000000
Haymarket to York Place (B) | 38818000
Infrastructure (A+B) | 398878000
Utilities (C) | 1812000
Leith Walk Utilities | 1100000
CAF (D) | 62400000
Total - Infrastructure/Utilities/CAF (A+B+C+D) | 464190000
Non BSC Costs to date (E) | 248500000
Non BSC Costs to go;
Project Management | 24200000
Third Party Related Items | 5300000
Public Art Reinstatement | 300000
Total Non BSC Costs to go (F) | 29800000
Contingency & Specified Risk (G) | 34507000
Total Budget | 776997000

## High Level Budget
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Risk Model Data
|  |  | £M | £M | £M |  | Probability | Optimistic Cost | Most Likely | Pessimistic
Off Street Works | [6 empty] | % | Assume only 5% chance it will be lower than this |  | Assume only 5% chance it will be higher than this
Airport to Haymarket | Base Cost
(Infraco) | Payments to App 43 + Hg Certs 1, 2 & 3a |  | 178.93 |  |  |  | 100% | 178930000 | 178930000 | 178930000
| Apps 44 & 45 + Hg Certs 3b & 3c |  | 16.06 |  |  |  | 100% | 16060000 | 16060000 | 16060000
| Prioritised Works |  | 19.68 |  |  |  | 100% | 19680000 | 19680000 | 19680000
| Costs 'to go' to BBS |  |  | 147.83 |  |  | 100% | 147830000 | 147830000 | 147830000
| Deduction for Forth Ports |  |  | -2.44 |  | Colin Smith | 100% | -4000000 | -2440000 | -1000000
|  | Base Cost Total | 214.67 | 145.39 | 360.06
Risks
| R041 | Approval of plans for Gogar interchange |  |  |  |  | 50% | 150000 | 350000 | 500000
| FG Risk35 | Retaining wall (treatment of unstable wall or special construction measures) |  |  |  | Price given at Workshop | 60% | 50000 | 100000 | 200000
| FG Risk 36 | Edinburgh Gateway - Power Cable |  |  |  | AC confirmed estimate from previous meeting | 90% | 350000 | 400000 | 400000
| FG Risk 47 | Scottish Rugby Union appeasement costs |  |  |  | now in R041
| FG Risk 49 | Blockades and possessions not included in Lump sum |  |  |  | Allowance | 50% | 125000 | 250000 | 250000
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 214.67 | 145.39 | 360.06
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
On Street Works
Haymarket to York Place | Base Cost
(Infraco) | On-street contract price - Bilfinger Berger |  |  | 33.3 |  | Discussion on Pricing ; CS to go back to Contractor; view to be taken on holding contingency | 100% | 28000000 | 31300000 | 33300000
| On-street contract price - Siemens |  |  | 12.5 |  | As above | 100% | 11875000 | 12500000 | 12500000
| Value Engineering Opportunity |  |  | -7 |  | Traffic Mgt, Average to Low Tenders and Siemens reduction | 100% | -15000000 | -7000000 | -7000000
|  | Base Cost Total | 0 | 38.8 | 38.8
Risks
Pricing Assumptions
|  | 6.4.2.1 Floating Track Slab |  |  |  | Priced at £597k included in Siemens tender for On Street | 100% | 477600 | 597000 | 716400
|  | 6.4.2.3 York Place Terminal Point |  |  |  |  | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.4 Cathedral Lane Substation |  |  |  | Colin Smith | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.5 Elder Street |  |  |  | Advised at Zero Cost Andy Conway 09-08-11 | 100% | 0 | 0 | 0
|  | 6.4.2.6 Dublin Street |  |  |  | Steps - Advised at £75k Cost Andy Conway 09-08-11 | 100% | 60000 | 75000 | 90000
|  | 6.4.2.7 Cycleway at Mound |  |  |  | Revised Number from Steven Bell | 100% | 80000 | 100000 | 120000
|  | 6.4.2.8 St Andrews Square |  | OUT |  | base costs in budget - street scape uplift separate budget - therefore risk allowance zero
| R049 | Additional land required to allow construction |  |  |  | figure supplied by Third party manager | 90% | 130000 | 150000 | 180000
| R057 | Unknown or abandoned chambers', cellars, voids etc. |  |  |  | NOT a Risk
| FG Risk 8 | Sub-suppliers warranties expire during the maintenance period and Siemens may have legitimate claim due to delays |  |  |  | Colin Smith - see e-mail 11/8/11, This cost is included in Siemens on Street Price | 50% | 0 | 0 | 0
| FG Risk 15 | Multiple road closures proposed / agreed may not work with traffic despite being acceptable in principle (via the model results) |  |  |  | Shouldn't be our issue | 80% | 180000 | 200000 | 250000
| FG Risk 17 | OLE may not work - design costs to determine a solution and the consequential costs (Design, Construction, Quant's and delay) |  |  |  | discussion with CS | 90% | 850000 | 1000000 | 1500000
| FG Risk 23 | Demolition of building could impact on Infraco |  | OUT |  | This will not happen
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 0 | 38.8 | 38.8
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Utilities
Base Cost
| Identifiable items on Register |  |  | 1.812 |  | Master schedule showing £1.253M; See Contingency and Specified risks. Steven Bell to confirm; 700nr now the figure of conflicts £1.25M was on 550nr; say ave. cost of £20k ea x 200nr problems | 100% | 400000 | 1812000 | 2000000
| Trial Holes (140nr x £3k) |  |  | 0 |  | Included in Siemens Priority Works Price | 100% | 0 | 0 | 0
| Leith Walk Utilities |  |  | 1.1 |  |  | 100% | 1045000 | 1100000 | 1155000
|  | Base Cost Total | 0 | 2.912 | 2.912
Risks
| R004 | Damage to Utility Apparatus |  | OUT
| R032 | Utilities works, failure of MUDFA to deliver against programme |  | OUT
| R038 | Utility Consents |  | OUT
| FG Risk 1 | Utilities Risk - Utility diversions, clashes, design solutions, delay, construction |  |  |  | Discussion with CS; designer cost £5k; delay 1 on programme£5 days £10/ec all in £110k/ea x 200nr | 90% | 250000 | 1800000 | 2200000
| FG Risk 5 | Mitigation costs to avoid known and onerous utility clashes in the track formation - derogation for track formation levels to avoid utilities |  | OUT |  | Opex cost for council
| FG Risk 29 | Drainage connections (20% of above FG Risk 28) |  |  |  | Allowance OK | 80% | 100000 | 200000 | 300000
| FG Risk 31 | Road level lowering and utility issues as a result |  |  |  | Relates to South St Andews Sq; York Place; Shandwick Place; Michael Blake - CS pursue this; | 90% | 2000000 | 3000000 | 5000000
| FG Risk 59 | Delay to delivery of items on the Identified Utilities Register |  | OUT |  | Delay included in overall delay costs |  | 0 | 0 | 0
| FG Risk 60 | Loss and Expense Claims as a result of any delay |  | OUT |  | Included in £300k/week |  | 0 | 0 | 0
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 0 | 2.912 | 2.912
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
CAF
Base Cost
|  |  | 48 |  |  |  | 100% | 48000000 | 48000000 | 48000000
|  |  |  | 14.4 |  |  | 100% | 14400000 | 14400000 | 14400000
|  | Base Cost Total | 48 | 14.4 | 62.4
Risks
| R024 | Power not available to re-commission first tram |  | OUT
| FG Risk 39 | Test track - single or 2 lines? |  | OUT |  | Discussed at meeting 11-08-11; considered not a risk
| FG Risk 50 | £62.4m is up to Sept 2013 - €170k per month. Delay to Jan 14 anticipated - Risk that it could be beyond Jan 14 |  |  |  | From Sept 2013 9months | 95% | 900000 | 1350000 | 1800000
| FG Risk 51 | Breaking the CAF away from consortium could give unexpected results £250k |  | OUT |  | Allowance only £1000/per tram SHOW stopper can not be quantified; It is a contractual issue
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 48 | 14.4 | 62.4
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Project Management
Base Cost
| To Date |  | 248.5 |  |  |  | 100% | 248500000 | 248500000 | 248500000
| Project Management Costs |  |  | 20.5 |  |  | 100% | 18450000 | 20500000 | 22550000
| Third Party | CAAD - CALA |  | 1.3 |  |  | 100% | 1235000 | 1300000 | 1365000
|  | CAAD - Tesco |  | 0.1 |  |  | 100% | 95000 | 100000 | 105000
|  | Network Rail - APA |  | 1.7 |  | Pessimistic view | 100% | 1000000 | 1250000 | 1700000
|  | Network Rail - Bridge & Operating Agreements |  | 0.1 |  |  | 100% | 95000 | 100000 | 105000
|  | Edinburgh Airport Ltd |  | 0.8 |  |  | 100% | 760000 | 800000 | 840000
|  | New Inglston Ltd |  | 0.75 |  |  | 100% | 712500 | 750000 | 787500
|  | Forth ports |  | 1 |  | Reinstatement view | 100% | 950000 | 1000000 | 1050000
| Accommodation |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Preparing for Operations |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Insurance & Extensions |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Warranty Extensions |  |  | OUT |  | included in Risk 8 | 100% | 0 | 0 | 0
| Legal |  |  | 1.3 |  | Provided by McGrigors | 100% | 1235000 | 1300000 | 1560000
| Land & property |  |  | OUT |  | included in Risk R049 | 100% | 0 | 0 | 0
| Traffic Modelling Costs |  |  | 0.1 |  | provided by AC | 100% | 95000 | 100000 | 105000
| Comms and Marketing |  |  | 1.1 |  |  | 100% | 1045000 | 1100000 | 1155000
| Comms Link to CEC |  |  | OUT |  | Covered by ER | 100% | 0 | 0 | 0
| Reinstatement of Public Art |  |  | 0.3 |  |  | 100% | 285000 | 300000 | 315000
| Materials Storage Cost |  |  | 1.2 |  | £300k included in Siemens Prices | 100% | 1140000 | 1200000 | 1260000
| Design Completion | Register of Design Disputes |  | OUT |  | Balance of Design issues to be included in General Design Risk Item at end | 100% | 0 | 0 | 0
|  | Base Cost Total | 248.5 | 30.25 | 278.75
Risks
| Event Delay Risk |  |  |  |  | Moved from Base to Risk | 100% | 1000000 | 1600000 | 2000000
| FG Risk 11 | Compensation budget - Extension to programme may incur additional compensation |  |  |  | Figure derived from 'Open for Business yearly cost of £210k/yr | 90% | 105000 | 160000 | 210000
| FG Risk 53 | Early Rate liabilities |  | OUT |  | Inc. in Pm costs above |  | 0 | 0 | 0
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 248.5 | 30.25 | 278.75
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Discrete Risks
|  | Base Cost Total | 0 | 0 | 0
Risks
Settlement Agreement
Colin Smiths Key areas
|  | Impact on tram Supply Agreement |  | OUT |  | All these are to do with legal's and are musts ; if wrong these are black flags
|  | Impact on Interface Agreement |  | OUT
|  | Impact on maintenance Agreement |  | OUT
|  | Warranties |  | OUT |  | As previous |  | 0 | 0 | 0
|  | tram inspection Agreement |  | OUT |  | tied into interface items |  | 0 | 0 | 0
|  | Traffic Modelling |  | OUT |  | OUT in PM above |  | 0 | 0 | 0
|  | milestone payments |  | OUT |  | OUT |  | 0 | 0 | 0
|  | LD's Capped |  | OUT |  | not a risk |  | 0 | 0 | 0
|  | Delay to Off Street Works caused by On Street Works delay |  | OUT |  | in FG Risk 12 |  | 0 | 0 | 0
|  | Running Off Street Works only; maintenance liabilities |  | OUT |  | This is now not an option |  | 0 | 0 | 0
|  | 21 day notification - Major Risk - contract move to cost reimbursable |  |  |  | only effects Civils; Rates are to be ; probability is 20% of the £33M worst case | 90% | 2200000 | 3300000 | 6600000
Pricing Assumptions
| FG Risk 40a | 6.4.1 - Approval body |  | OUT |  | No Value
| FG Risk 40b | 6.4.2 - Design Approvals 8nr |  | OUT |  | see On Street Pricing Assumptions |  | 0 | 0 | 0
| FG Risk 40c | 6.4.3 - Urban Traffic Controls |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40d | 6.4.4 - Excavation limits |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40e | Temporary works by tie |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40f | 6.4.5 - Utility free construction |  | OUT |  | Covered by Utility Items |  | 0 | 0 | 0
| FG Risk 40g | 6.4.6 - Unexploded ordinance |  | OUT |  | OUT in PM above |  | 0 | 0 | 0
| FG Risk 40h | Contaminated material |  | OUT |  | Covered by Utility Items |  | 0 | 0 | 0
| FG Risk 40j | 6.4.7 - Routine maintenance |  |  |  |  | 50% | 100000 | 500000 | 600000
| FG Risk 40k | 6.4.8 - Relaxation of time constraints |  |  |  |  | 50% | 100000 | 300000 | 400000
| FG Risk 40m | 6.4.9 - Protection of trees |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40n | 6.4.10 - Archaeological Finds |  |  |  |  | 50% | 10000 | 250000 | 500000
| FG Risk 40p | 6.4.11 - Programme Narrative |  | OUT |  | Covered by other risks |  | 0 | 0 | 0
| FG Risk 40q | 6.4.12 - 20 Non controversial issues no risk |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40r | 6.4.21 - Vandalism |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40s | 6.2.22 - Material Free Issue |  |  |  | Ticket machines - AC to confirm item | 50% | 225000 | 250000 | 275000
| FG Risk 40t | 6.4.24 - Clause too broad |  | OUT |  | No value |  | 0 | 0 | 0
Other Risks
| R002 | Death, injury or damage to third parties (people or property) during construction |  | OUT |  | Covered by Insurance Costs / Contractors Insurance
| R011 | Failure of Contractors / Sub-Contractors to self-certify completion, close out of NCRs and deliver construction quality |  |  |  |  | 15% | 20000 | 40000 | 60000
| R018 | Security Incident |  |  |  |  | 5% | 10000 | 50000 | 100000
| R019 | Archaeological or Human Remains |  | OUT |  | Covered in PM costs
| R020 | Exceptional adverse weather |  |  |  |  | 5% | 120000 | 300000 | 420000
| FG Risk 3 | Road Maintenance adoption costs burden on project due to on-going works and delay of hand-back |  | OUT |  | Considered to be in FG Risk 040j
| FG Risk 12 | OVERALL time delay impact (assessment of cumulative effect of identified risks on this register) |  |  |  | Delay considered to be £300k/week; | 90% | 7800000 | 11610000 | 15600000
| General Design Risk |  |  |  |  | This will be the balance figure of £10M on design items above | 100% | 4443750 | 5925000 | 6221250
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 0 | 0 | 0
|  | GRAND TOTAL |  | 231.752 | 742.922 | M |  | Risk | 34.507

## High Level Budget (2)
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Risk Model Data
|  |  | £M | £M | £M |  | Probability | Optimistic Cost | Most Likely | Pessimistic
Off Street Works | [6 empty] | % | Assume only 5% chance it will be lower than this |  | Assume only 5% chance it will be higher than this
Airport to Haymarket | Base Cost
(Infraco) | Payments to App 43 + Hg Certs 1, 2 & 3a |  | 178.93 |  |  |  | 100% | 178930000 | 178930000 | 178930000
| Apps 44 & 45 + Hg Certs 3b & 3c |  | 16.06 |  |  |  | 100% | 16060000 | 16060000 | 16060000
| Prioritised Works |  | 19.68 |  |  |  | 100% | 19680000 | 19680000 | 19680000
| Costs 'to go' to BBS |  |  | 147.83 |  |  | 100% | 147830000 | 147830000 | 147830000
| Deduction for Forth Ports |  |  | -2 |  | Colin Smith | 100% | -4000000 | -2000000 | -1000000
|  | Base Cost Total | 214.67 | 145.83 | 360.5
|  | Sub Total | 214.67 | 145.83 | 360.5
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
On Street Works
Haymarket to York Place | Base Cost
(Infraco) | On-street contract price - Bilfinger Berger |  |  | 33.3 |  | Discussion on Pricing ; CS to go back to Contractor; view to be taken on holding contingency | 100% | 28000000 | 31300000 | 33300000
| On-street contract price - Siemens |  |  | 12.5 |  | As above | 100% | 11875000 | 12500000 | 12500000
|  | Base Cost Total | 0 | 45.8 | 45.8
|  | Sub Total | 0 | 45.8 | 45.8
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Utilities
Base Cost
| Identifiable items on Register |  |  | 1.25 |  | Master schedule showing £1.253M; See Contingency and Specified risks. Steven Bell to confirm; 700nr now the figure of conflicts £1.25M was on 550nr; say ave. cost of £20k ea x 200nr problems | 100% | 400000 | 1250000 | 2000000
| Trial Holes (140nr x £3k) |  |  | 0.42 |  |  | 100% | 399000 | 420000 | 504000
| Leith Walk Utilities |  |  | 1.1 |  |  | 100% | 1045000 | 1100000 | 1155000
|  | Base Cost Total | 0 | 2.77 | 2.77
|  | Sub Total | 0 | 2.77 | 2.77
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
CAF
Base Cost
|  |  | 48 |  |  |  | 100% | 48000000 | 48000000 | 48000000
|  |  |  | 14.4 |  |  | 100% | 14400000 | 14400000 | 14400000
|  | Base Cost Total | 48 | 14.4 | 62.4
|  | Sub Total | 48 | 14.4 | 62.4
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Project Management
Base Cost
| To Date |  | 248.5 |  |  |  | 100% | 248500000 | 248500000 | 248500000
| Project Management Costs |  |  | 20.5 |  |  | 100% | 18450000 | 20500000 | 22550000
| Third Party | CAAD - CALA |  | 1.3 |  |  | 100% | 1235000 | 1300000 | 1365000
|  | CAAD - Tesco |  | 0.1 |  |  | 100% | 95000 | 100000 | 105000
|  | Network Rail - APA |  | 1.7 |  | Pessimistic view | 100% | 1000000 | 1250000 | 1700000
|  | Network Rail - Bridge & Operating Agreements |  | 0.1 |  |  | 100% | 95000 | 100000 | 105000
|  | Edinburgh Airport Ltd |  | 0.8 |  |  | 100% | 760000 | 800000 | 840000
|  | New Inglston Ltd |  | 0.75 |  |  | 100% | 712500 | 750000 | 787500
|  | Forth ports |  | 1 |  | Reinstatement view | 100% | 950000 | 1000000 | 1050000
| Accommodation |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Preparing for Operations |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Insurance & Extensions |  |  | OUT |  | Covered by PM Costs Line | 100% | 0 | 0 | 0
| Warranty Extensions |  |  | OUT |  | included in Risk 8 | 100% | 0 | 0 | 0
| Legal |  |  | 1.3 |  | Provided by McGrigors | 100% | 1235000 | 1300000 | 1560000
| Land & property |  |  | OUT |  | included in Risk R049 | 100% | 0 | 0 | 0
| Traffic Modelling Costs |  |  | 0.1 |  | provided by AC | 100% | 95000 | 100000 | 105000
| Comms and Marketing |  |  | 1.1 |  |  | 100% | 1045000 | 1100000 | 1155000
| Comms Link to CEC |  |  | OUT |  | Covered by ER | 100% | 0 | 0 | 0
| Reinstatement of Public Art |  |  | 0.3 |  |  | 100% | 285000 | 300000 | 315000
| Materials Storage Cost |  |  | 1.5 |  |  | 100% | 1425000 | 1500000 | 1575000
| Design Completion | Register of Design Disputes |  | OUT |  | Balance of Design issues to be included in General Design Risk Item at end | 100% | 0 | 0 | 0
|  | Base Cost Total | 248.5 | 30.55 | 279.05
|  | Sub Total | 248.5 | 30.55 | 279.05
|  | Total Base Budget |  |  | 750.52
Level 1 | Level 2 |  | COWD | TO GO | BUDGET | Notes | Probability | Optimistic Cost | Most Likely | Pessimistic
|  |  | £M | £M | £M
Discrete Risks
|  | Base Cost Total | 0 | 0 | 0
Risks
Settlement Agreement
Colin Smiths Key areas
|  | Impact on tram Supply Agreement |  | OUT |  | All these are to do with legal's and are musts ; if wrong these are black flags
|  | Impact on Interface Agreement |  | OUT
|  | Impact on maintenance Agreement |  | OUT
|  | Warranties |  | OUT |  | As previous |  | 0 | 0 | 0
|  | tram inspection Agreement |  | OUT |  | tied into interface items |  | 0 | 0 | 0
|  | Traffic Modelling |  | OUT |  | OUT in PM above |  | 0 | 0 | 0
|  | milestone payments |  | OUT |  | OUT |  | 0 | 0 | 0
|  | LD's Capped |  | OUT |  | not a risk |  | 0 | 0 | 0
|  | Delay to Off Street Works caused by On Street Works delay |  | OUT |  | in FG Risk 12 |  | 0 | 0 | 0
|  | Running Off Street Works only; maintenance liabilities |  | OUT |  | This is now not an option |  | 0 | 0 | 0
|  | 21 day notification - Major Risk - contract move to cost reimbursable |  |  |  | only effects Civils; Rates are to be ; probability is 20% of the £33M worst case | 90% | 2200000 | 3300000 | 6600000
Pricing Assumptions
| FG Risk 40a | 6.4.1 - Approval body |  | OUT |  | No Value
| FG Risk 40b | 6.4.2 - Design Approvals 8nr |  | OUT |  | see On Street Pricing Assumptions |  | 0 | 0 | 0
| FG Risk 40c | 6.4.3 - Urban Traffic Controls |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40d | 6.4.4 - Excavation limits |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40e | Temporary works by tie |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40f | 6.4.5 - Utility free construction |  | OUT |  | Covered by Utility Items |  | 0 | 0 | 0
| FG Risk 40g | 6.4.6 - Unexploded ordinance |  | OUT |  | OUT in PM above |  | 0 | 0 | 0
| FG Risk 40h | Contaminated material |  | OUT |  | Covered by Utility Items |  | 0 | 0 | 0
| FG Risk 40j | 6.4.7 - Routine maintenance |  |  |  |  | 50% | 100000 | 500000 | 600000
| FG Risk 40k | 6.4.8 - Relaxation of time constraints |  |  |  |  | 50% | 100000 | 300000 | 400000
| FG Risk 40m | 6.4.9 - Protection of trees |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40n | 6.4.10 - Archaeological Finds |  |  |  |  | 50% | 10000 | 250000 | 500000
| FG Risk 40p | 6.4.11 - Programme Narrative |  | OUT |  | Covered by other risks |  | 0 | 0 | 0
| FG Risk 40q | 6.4.12 - 20 Non controversial issues no risk |  | OUT |  | No Value |  | 0 | 0 | 0
| FG Risk 40r | 6.4.21 - Vandalism |  | OUT |  | Contractors Risk |  | 0 | 0 | 0
| FG Risk 40s | 6.2.22 - Material Free Issue |  |  |  | Ticket machines - AC to confirm item | 50% | 225000 | 250000 | 275000
| FG Risk 40t | 6.4.24 - Clause too broad |  | OUT |  | No value |  | 0 | 0 | 0
Other Risks
| R002 | Death, injury or damage to third parties (people or property) during construction |  | OUT |  | Covered by Insurance Costs / Contractors Insurance
| R011 | Failure of Contractors / Sub-Contractors to self-certify completion, close out of NCRs and deliver construction quality |  |  |  |  | 15% | 20000 | 40000 | 60000
| R018 | Security Incident |  |  |  |  | 5% | 10000 | 50000 | 100000
| R019 | Archaeological or Human Remains |  | OUT |  | Covered in PM costs
| R020 | Exceptional adverse weather |  |  |  |  | 5% | 120000 | 300000 | 420000
| FG Risk 3 | Road Maintenance adoption costs burden on project due to on-going works and delay of hand-back |  | OUT |  | Considered to be in FG Risk 040j
| FG Risk 12 | OVERALL time delay impact (assessment of cumulative effect of identified risks on this register) |  |  |  | Delay considered to be £300k/week; | 90% | 7800000 | 11610000 | 15600000
| General Design Risk |  |  |  |  | This will be the balance figure of £10M on design items above | 100% | 4443750 | 5925000 | 6221250
|  | Risk Cost Total | 0 | 0 | 0
Risks
| R041 | Approval of plans for Gogar interchange |  |  |  |  | 50% | 150000 | 350000 | 500000
| FG Risk35 | Retaining wall (treatment of unstable wall or special construction measures) |  |  |  | Price given at Workshop | 60% | 50000 | 100000 | 200000
| FG Risk 36 | Edinburgh Gateway - Power Cable |  |  |  | AC confirmed estimate from previous meeting | 90% | 350000 | 400000 | 400000
| FG Risk 47 | Scottish Rugby Union appeasement costs |  |  |  | now in R041
| FG Risk 49 | Blockades and possessions not included in Lump sum |  |  |  | Allowance | 50% | 125000 | 250000 | 250000
|  | Risk Cost Total | 0 | 0 | 0
Risks
| R004 | Damage to Utility Apparatus |  | OUT
| R032 | Utilities works, failure of MUDFA to deliver against programme |  | OUT
| R038 | Utility Consents |  | OUT
| FG Risk 1 | Utilities Risk - Utility diversions, clashes, design solutions, delay, construction |  |  |  | Discussion with CS; designer cost £5k; delay 1 on programme£5 days £10/ec all in £110k/ea x 200nr | 90% | 250000 | 1800000 | 2200000
| FG Risk 5 | Mitigation costs to avoid known and onerous utility clashes in the track formation - derogation for track formation levels to avoid utilities |  | OUT |  | Opex cost for council
| FG Risk 29 | Drainage connections (20% of above FG Risk 28) |  |  |  | Allowance OK | 80% | 100000 | 200000 | 300000
| FG Risk 31 | Road level lowering and utility issues as a result |  |  |  | Relates to South St Andews Sq; York Place; Shandwick Place; Michael Blake - CS pursue this; | 90% | 2000000 | 3000000 | 5000000
| FG Risk 59 | Delay to delivery of items on the Identified Utilities Register |  | OUT |  | Delay included in overall delay costs |  | 0 | 0 | 0
| FG Risk 60 | Loss and Expense Claims as a result of any delay |  | OUT |  | Included in £300k/week |  | 0 | 0 | 0
|  | Risk Cost Total | 0 | 0 | 0
Risks
Pricing Assumptions
|  | 6.4.2.1 Floating Track Slab |  |  |  | Colin Smith | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.3 York Place Terminal Point |  |  |  |  | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.4 Cathedral Lane Substation |  |  |  | Colin Smith | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.5 Elder Street |  |  |  | Advised at Zero Cost Andy Conway 09-08-11 | 100% | 0 | 0 | 0
|  | 6.4.2.6 Dublin Street |  |  |  | Steps - Advised at £75k Cost Andy Conway 09-08-11 | 100% | 60000 | 75000 | 90000
|  | 6.4.2.7 Cycleway at Mound |  |  |  | Colin Smith | 100% | 800000 | 1000000 | 1200000
|  | 6.4.2.8 St Andrews Square |  | OUT |  | base costs in budget - street scape uplift separate budget - therefore risk allowance zero
| R049 | Additional land required to allow construction |  |  |  | figure supplied by Third party manager | 90% | 130000 | 150000 | 180000
| R057 | Unknown or abandoned chambers', cellars, voids etc. |  |  |  | NOT a Risk
| FG Risk 8 | Sub-suppliers warranties expire during the maintenance period and Siemens may have legitimate claim due to delays |  |  |  | Colin Smith - see e-mail 11/8/11 | 50% | 0 | 250000 | 300000
| FG Risk 15 | Multiple road closures proposed / agreed may not work with traffic despite being acceptable in principle (via the model results) |  |  |  | Shouldn't be our issue | 80% | 180000 | 200000 | 250000
| FG Risk 17 | OLE may not work - design costs to determine a solution and the consequential costs (Design, Construction, Quant's and delay) |  |  |  | discussion with CS | 90% | 850000 | 1000000 | 1500000
| FG Risk 23 | Demolition of building could impact on Infraco |  | OUT |  | This will not happen
|  | Risk Cost Total | 0 | 0 | 0
Risks
| R024 | Power not available to re-commission first tram |  | OUT
| FG Risk 39 | Test track - single or 2 lines? |  | OUT |  | Discussed at meeting 11-08-11; considered not a risk
| FG Risk 50 | £62.4m is up to Sept 2013 - €170k per month. Delay to Jan 14 anticipated - Risk that it could be beyond Jan 14 |  |  |  | From Sept 2013 9months | 95% | 900000 | 1350000 | 1800000
| FG Risk 51 | Breaking the CAF away from consortium could give unexpected results £250k |  | OUT |  | Allowance only £1000/per tram SHOW stopper can not be quantified; It is a contractual issue
|  | Risk Cost Total | 0 | 0 | 0
Risks
| Event Delay Risk |  |  |  |  | Moved from Base to Risk | 100% | 1000000 | 1600000 | 2000000
| FG Risk 11 | Compensation budget - Extension to programme may incur additional compensation |  |  |  | Figure derived from 'Open for Business yearly cost of £210k/yr | 90% | 105000 | 160000 | 210000
| FG Risk 53 | Early Rate liabilities |  | OUT |  | Inc. in Pm costs above |  | 0 | 0 | 0
|  | Risk Cost Total | 0 | 0 | 0
|  | Sub Total | 0 | 0 | 0
|  | GRAND TOTAL |  |  | 750.52 | M

## Project Costs
Pitchfork 2 - Project Costs
PM Costs cashflow | [6 empty] | 11.9752 | 30.0979 | 10.3367 | 12.0595 | 10.3367 | 12.0595 | 8.5173 | 4.6148
[7 empty] | Forecast | [7 empty] | 10142000
|  | CAB P4 - 11/12 | Latest Period | Cum COWD P4 - 11/12 | P4 AFC - 11/12 | Cum COWD P4 - 11/12 | P5 & P6 -2011/12 | P7 to P13 -2011/12 | P1-P6 2012/13 | P7-P13 2012/13 | P1-P6 2013/14 | P7-P13 2013/14 | P1-P6 2014/15 | P7-P13 2014/15 | Forecast | Notes
T01.01 | Project management Staff Costs | 31103863.4561 | 379805 | 32333538 | 35311297.5887 | 32333538 | 1214527.8719 | 3052524.8549 | 1048348.2052 | 1223072.9061 | 1048348.2052 | 1223072.9061 | 863828.8705 | 468030.7088 | 42475292.529 | (1)
T01.02 | Recruitment Fees | 466202.5966 | -3128 | 466593 | 472250 | 466593 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471593 | (2)
T01.03 | Travel & Subsistence / Conference | 356213.7554 | 2124.69 | 359526.69 | 366159.69 | 359526.69 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 409526.69 | (3)
T01.04 | Central Overheads | 5580828.8293 | 22996 | 5212065 | 5595423.8 | 5212065 | 46000 | 199000 | 113000 | 113000 | 119000 | 119000 | 125000 | 125000 | 6171065 | (4)
T01.05 | IT & Software Costs / fitout | 3109074.7792 | 25228.67 | 3409893.67 | 4241492.67 | 3409893.67 | 50000 | 150000 | 120000 | 140000 | 126000 | 147000 | 132300 | 154350 | 4429543.67 | (5)
T01.06 | Citypoint - rent,rates,s/c | 3060112.4655 | 31657.33 | 2995934.33 | 3465481.9214 | 2995934.33 | 0 | 469000 | 0 | 0 | 0 | 0 | 0 | 0 | 3464934.33 | (6)
T01.08 | Short Term Contractors | 196804 | 0 | 196804 | 196804 | 196804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196804 | n/a
T01.09 | City Point Overheads | 25270.8462 | 0 | 25271.09 | 25271.09 | 25271.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25271.09 | n/a
T01.10 | Active Risk Manager | 83665 | 0 | 83666 | 83666 | 83666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83666 | n/a
T01.11 | Archaeological supervisor - Gogar works | 185232.89 | 22115 | 174230 | 226884 | 174230 | 0 | 52654 | 0 | 0 | 0 | 0 | 0 | 0 | 226884 | (7)
T01.13 | Archaeology - Non Gogar | 642742.2423 | 0 | 373580 | 601316 | 373580 | 0 | 227736 | 0 | 0 | 0 | 0 | 0 | 0 | 601316 | (7)
T01.14 | DRP Costs | 6531456 | 9616 | 6152699 | 6531480 | 6152699 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6352699 | (8)
T01.15 | Tax Planning / Governance Costs (Non DLA) | 21960 | 0 | 21960 | 301816 | 21960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21960 | (9)
T01 | Total tie PM costs | 51363426.8606 | 490414.69 | 51805760.78 | 57419342.7601 | 51805760.78 | 1525527.8719 | 4190914.8549 | 1281348.2052 | 1476072.9061 | 1293348.2052 | 1489072.9061 | 1121128.8705 | 747380.7088 | 64930555.309
T02 | Total DPOF | 2770140.25 | 34199.76 | 2834832.76 | 7631160.26 | 2834832.76 | 54000 | 333014.5 | 635388 | 3773925 | 0 | 0 | 0 | 0 | 7631160.26 | (10)
T03.01-19 | DLA | 3254733.82 | 0 | 3501468.49 | 3590967.49 | 3501468.49 | 0 | 89499 | 0 | 0 | 0 | 0 | 0 | 0 | 3590967.49 | (11)
T03.20-35 | Subtotal D&W | 2851602.677 | 2340 | 2865485.77 | 2911513.9821 | 2865485.77 | 0 | 46028.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 2911513.9821 | (11)
T03 | Total LEGALS | 6106336.497 | 2340 | 6366954.26 | 6502481.4721 | 6366954.26 | 0 | 135527.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 6502481.4721
T06.01-03 | Subtotal TSS | 10736395.7903 | 10820.17 | 10877944.16 | 11322572.72 | 10877944.16 | 20000 | 70000 | 63000 | 73500 | 66150 | 77175 | 69457.5 | 81033.75 | 11398260.41 | (12)
T06.03a | Subtotal CEC | 2288341.49 | 38561 | 2467459 | 2544581 | 2467459 | 70000 | 210000 | 210000 | 245000 | 210000 | 245000 | 210000 | 245000 | 4112459 | (13)
T06 | Total TSS and CEC | 13024737.2803 | 49381.17 | 13345403.16 | 13867153.72 | 13345403.16 | 90000 | 280000 | 273000 | 318500 | 276150 | 322175 | 279457.5 | 326033.75 | 15510719.41
T12.01-12,23-40 | Subtotal Communications | 2220336.0077 | 31941.45 | 2200180.48 | 2542971.48 | 2200180.48 | 20000 | 80000 |  |  |  |  | 200000 |  | 2500180.48 | (14)
T12.13-22 | Subtotal Stakeholder | 741510 | 0 | 755875.3 | 890875.3 | 755875.3 | [8 empty] | 755875.3 | (15)
T12 | Total COMMS / MARKETING | 2961846.0077 | 31941.45 | 2956055.78 | 3433846.78 | 2956055.78 | 20000 | 80000 | 0 | 0 | 0 | 0 | 200000 | 0 | 3256055.78
T13 | Total TEL | 2797233 | 12000 | 2581912 | 3080753 | 2581912 | 30000 | [7 empty] | 2611912 | (16)
T999 | Total | 79023719.8956 | 620277.07 | 79890918.74 | 91934737.9922 | 79890918.74 | 1719527.8719 | 5019456.5671 | 2189736.2052 | 5568497.9061 | 1569498.2052 | 1811247.9061 | 1600586.3705 | 1073414.4588 | 100442884.2311
|  | 79023719.8956 | 620277.07 | 79890918.74 | 91934737.9922
|  | 0 | 0 | 0 | 0 | Forecast Assumptions: | [8 empty] | 102442884.2311 | +£2m contingency
(1) Staff PM forecast assumptions based upon Phased Employee forecast. Includes VR redundancy in 2011/12
(2) No recruitment fees forecast - anticipated that recruitment will be dealt with by CEC HR at no incremetal cost to CEC group companies
(3) Travel & Subsistence - costs to reduce following completion of CAF delivery. Additional £50k allowed for CAF travel & DPOF staff
(4) Overheads reduction due to move from Citypoint. Assumed £50k recharge for CEC internal audit function. See Oheads sheet
(5) IT software costs prudent view of £20k per period from P8 2011/12 going forwards. Opportunity to reduce if upgrades minimised (SH to verify).
(6) No more CP rent and rates, although charge forecast until March 2012, this includes £80k delapidations costs
(7) Archaeological all forecast in 2011/12 for completion, although this is likely to be spread dependent upon timeline (Chris Bartynek - leaves 26/08)
(8) DRP budget will not be required. Forecast cost for legal drafting/ tie handover included in P5/6 for £200k
(9) This is an operational, not CAPEX cost of the build/ budget
(10) DPOF forecast provided per period 4 PD review report. Original budget based upon full Phase 1a. Significant opportunity (AR to justify fcst)
(11) Legals forecast in-line with AFC reported Period 4 - assumed to be completed by the end of the year. CEC legal to cover turnkey legal costs
(12) TSS support costs at £10k per period +5% uplift per annum
(13) CEC assumed rechargs of £35k pcm - flat rate for project. A Coyle to confirm figures
(14) Comms budget to be covered by CEC. Opening costs covered by operating co. £100k costs to end 2011/12 + £200k safety campaign opening
(15) Stakeholder management cost in-line with forecast P4 2011/12
(16) No further TEL recharge costs to be accepted