## Sheet1
Deckchair versus GHP comparison - Phoenix & Separation
Relating to Presentation on 28/02/11 to CEC of numbers & GHP paper sent 25/02/11
Phoenix | tie Phoenix view Presented 28/2/2011 |  |  | Separation | tie Separation view Presented 28/2/2011
Options Considered | tie Phoenix Position £m | BSC Phoenix Offer £m | tie View of BSC Offer £m | Options Considered | tie Phoenix Position £m | tie Separation adj £m | tie Separation Position £m
BB+S Costs to Haymarket | 247.8 | 368.7 | 368.7 | BB+S Costs to Haymarket | 247.8 |  | 247.8
CAF | 62.5 | 65.4 | 65.4 | CAF | 62.5 |  | 62.5
SDS | 10 | 15.1 | 15.1 | SDS | 10 |  | 10
Sub-total BSC Costs | 320.3 | 449.2 | 449.2 | Sub-total BSC Costs | 320.3 | 0 | 320.3
Further Risk 'to Go' with BSC (exclusions to be Priced) | 20 | 20 | 20 | Further Risk 'to Go' with BSC (exclusions to be Priced) | 20 | -20 | 0
Non-BSC Costs (Haymarket to St Andrews Square) | 19.2 | n/a | 19.2 | Non-BSC Costs (Haymarket to St Andrews Square) | 19.2 |  | 19.2
Non-BSC Project Costs | 266.4 | n/a | 266.4 | Non-BSC Project Costs | 266.4 | 5 | 271.4
Mediation & Professional Fees | 3 | n/a | 3 | Mediation & Professional Fees/ New design | 3 | 10 | 13
Reinstatement | 2.5 | n/a | 2.5 | Reinstatement / Interim works/ Site Security | 2.5 | 11.9 | 14.4
Sub-total Non-BSC Costs | 291.1 | 0 | 291.1 | Sub-total Non-BSC Costs | 291.1 | 26.9 | 318
Add Back Differential of Evaluation Vs. Cash | -33.2 | included | included | Add Back Differential of Evaluation Vs. Cash | -33.2 |  | -33.2
Add Back Delay to date allowance (9 months) | 21 | included | included | Add Back Delay to date allowance (9 months) | 21 | -21 | 0
Other Entitlements | 19 | included | included | Other Entitlements | 19 |  | 19
Further EoT Allowances | 0 | 0 | 0 | Further EoT Allowances (allowances to be Priced) | 0 | 0 | 0
Sub-total Settlement | 6.8 | 0 | 0 | Sub-total Settlement | 6.8 | -21 | -14.2
Total (plus £XX.Xm Risk/ Allowances above) | 638.2 | 469.2 | 760.3 | Total (plus £XX.Xm Risk/ Allowances above) | 638.2 | -14.1 | 624.1
Reconciliation to GHP paper of 25/02/11 |  |  | Adjustment /Diff £m | Reconciliation to GHP paper of 25/02/11 |  |  | Adjustment /Diff £m
GHP Paper incorrectly state Infraco Phoenix offer is £410m. Actual offer is £449.2m |  |  | -39.2 | GHP assessment of off-street works 'to go' (£219.2m vs tie £123.8m) |  |  | 95.4
GHP Analysis deducts On-street works value (£40.0m). These are all relevant costs |  |  | -40 | GHP starting position is that Certificate Add Back Differential of Evaluation Vs. Cash |  |  | 33.2
GHP have assumed that the offer is a GMP, so have included no 'risk' for exclusions |  |  | -20 | GHP Provisional sums/ Contingencies less additional tie risk (£21m - tie £nilm) |  |  | 21
Negotiation' VE/ Purchasing / Contamination adjustments included in GHP view |  |  | -10 | GHP allowance for date mid-2014 (escalation allowance) |  |  | 18
Additional Cost in GHP Paper to St Andrews Square (£24m-19.2m) |  |  | 4.8 | GHP assume that there is a further £15m full procurement cost to go vs. (£15m-£10m) tie view |  |  | 5
Difference BSC assessment of tie costs (£277.1m-271.9m) |  |  | 5.2 | Additional Cost in GHP Paper to St Andrews Square (£22.9m-19.2m) |  |  | 3.7
|  |  |  | Difference BSC assessment of tie costs (£277.1m-276.9m) |  |  | 0.2
|  |  |  | Less tie Interim works (£9.9m) and Site Security (£2.0m) & Costs |  |  | -11.9
Sub-total Differences in GHP figure to tie assessment of BSC Phoenix |  |  | -99.2 | Less tie Other Entitlements |  |  | -19
GHP paper figure 25/02/11 |  |  | 661.1 | Sub-total Differences in GHP figure to tie assessment of BSC Separation |  |  | 145.6
|  | GHP Check total | 661.1 | GHP paper figure 25/02/11 |  |  | 769.7
|  | diff unreconciled | 0 |  |  | GHP Check total | 765.27
[6 empty] | diff unreconciled | 4.43