## Sheet1
Phoenix Risk Review
| Issue | Scope | Price | Programme | Risk | Resist? | tie Position | Risk Provision
[8 empty] | Low | High
[8 empty] | £k | £k
General Scope
1 | Haymarket - SAS | × | × | × | tie to make provision |  | Contained in deckchair numbers | 18000 | 20000
2 | Drawing changes | × | × | × | No provision - NOT ABLE TO QUANTIFY | R | Resist unless all drawings have warrant to meet ER’s - errors, omissions are an Infraco cost | 0 | 0
3 | Approvals and consents | × | × | × | No tie provision. tie retained risks as per existing contract identified elsewhere. NOT ABLE TO QUANTIFY | R | Resist - Original contract position on approvals and consents should be held | 0 | 0
Specific Scope
4 | Chainage exclusions | × | × | × | tie to make provision for outwith LOD risks |  | BSC to confirm these are within Pheonix price - airport and depot programme track. Also suitable tie in to complete design, track and OHL equipment at Haymarket & Airport | 100 | 500
5 | Immunisation | √ | √ | √ | tie provision. |  | Works virtually complete - no mention made in Phoenix. BSC to confirm. | 0 | 0
Exclusions
6 | Edinburgh Gateway excluded | × | × | × | tie/CEC to make provision |  | OK | 9500 | 11500
7 | Noise and vibration floating slab | × | × | × | Provision for “special” locations |  | OK | 100 | 300
8 | Noise and vibration floating slab | × | × | × | Provison for all floating slab | R | Resist | 500 | 1500
9 | Utilities – no Change Order | × | × | × | tie to make provision |  | OK - consider that BSC Pheonix price should account for £1.1m of costs but need to clarify alignement between us on what is included | 100 | 200
10 | Unknown utilities | × | × | × | tie to make provision for above £50k each and every cap |  | OK - see tie Pheonix proposal | 500 | 1000
11 | Fossils and antiquities remain a tie risk | × | × | × | tie to make allocation for costs and programme EOT |  | OK | 100 | 200
12 | Airport kiosk and canopy excluded | × | × | × | Clarify re design and construction. BSC price should include £200k design costs | R | Resist | 650 | 800
"Clarifications"
13 | Roseburn viaduct scope to be finalised | × | × | × | tie to make provision |  | OK | 250 | 700
14 | Gogarburn surcharge solution to be finalised | × | × | × | tie to make provision | R | Resist - should be in BSC Pheonix price | 0 | 600
15 | 3 Party consents excluded | × | × | × | tie to make provision |  | OK | 0 | 50
16 | 3rd Party amendments | × | × | × | tie to make provision |  | OK | 0 | 1000
17 | Water connection issues at depot | × | × | × | tie to make provision | R | Resist - except for change of design to ductile and associated time with this | 400 | 600
18 | Trackform type now considered fixed | × | × | × | No provision - included in general contingency |  | Agreed provided meets ER's | 0 | 0
19 | Excludes transitions at 1A structures | × | × | × | tie provision | R | Resist | 50 | 250
20 | NIL scope appears to be excluded | × | × | × | tie to make provision | R | NIL scope should be in BSC Pheonix Price but is excluded in drawings | 600 | 1000
21 | Airport RW | × | × | × | tie to make provision |  | Subject to drawing check | 2500 | 5000
22 | Flooding risk at airport | × | × | × | tie provision. | R | Resist - BSC issue to deal with | 100 | 250
23 | Tramstop based on PPP – not the most up to date drawings which were through IDR in January. | × | × | × | Provision for any further Client changes only | R | Resist | 300 | 500
24 | Substation Design | x | x | x | No provision - included in general contingency |  | General Drawing issue and warranty to achieve ERs applies | 0 | 0
25 | Landscaping – planting risk potential EOT | √ | √ | √ | Clarify that BSC do not intend to recover any EOT costs |  | OK – subject to clarification | 0 | 0
26 | Landscaping – specification changes by client | × | × | × | tie to make provision for client changes |  | Client changes only | 0 | 200
27 | 1a/1b interface design drawings unlikely to be finished requirement | √ | √ | √ | No provision if BSC warrant deign meets ER's | R | BSC included old scope - should be saving but delay costs so left at zero | 0 | 0
28 | Phase 1b design and construction, including TRO | × | × | × | Provision for design scope only |  | Tradeable | -500 | 0
29 | NR Form C approvals | √ | Std timescales only | Standard timescales only | tie to make provision for costs and EOT relating to NR delay– subject to BSC meeting quality thresholds |  | OK | 100 | 200
30 | NR - additional NR project management costs as a result of delays | × | × | × | tie to make provision |  | OK | 500 | 1000
31 | NR possessions – not shown in programme | × | × | × | tie Provision for costs of any required disruptive possessions | R | Resist | 0 | 500
32 | Gogar Castle Access Road land availability | × | × | × | Provision/solve within LOD |  | OK | 0 | 20
33 | 3rd Party Agreements @ NEL & EAL | × | × | × | tie to make provision |  | OK | 0 | 100
34 | Traffic modelling | × | × | × | tie to make provision | R | Resist | 50 | 150
35 | TRO misalignment | × | × | × | Provision for client changes | R | Resist for Infraco errors etc as per Clause 10.12 etc | 0 | 100
36 | TRO2/3 | × | × | × | Provision for TRO2/3 as a result of the TRO strategy |  | OK | 2000 | 4000
37 | Drainage misalignment and integration risk | × | × | × | tie provision. | R | Resist - BSC design/construction issue and they have issued IFC's/INTC's | 0 | 500
38 | Earthing issues at depot - interfaces with energy suppliers at depot is an existing issue between BSC and Scottish Power which is BSC’s risk under the existing contract and which they are technically in the best position to resolve. | × | × | × | tie provision. |  | Resist - BSC integration issue | 0 | 250
39 | Combined poles as per the original design | √ | √ | √ | No Provision |  | OK | 0 | 0
40 | Cable ducts for UTN excluded | × | × | × | Provision to take ducts back to central control room | R | Resist | 0 | 500
41 | LV HV supply at airport to be checked | × | × | × | tie to make provision |  | OK | 100 | 300
42 | Contaminated land | Capped at 51000m 3 13000m 3 hazardous | Part – no downside benefit to tie | Don’t see how BSc have included the 51,000m3 in the programme | tie to make risk provision for extra over £7m assumed in PPP price |  | BSC to clarify what is in programme. tie to consider excluding this all from BSC price and tie manages in totality | 500 | 1000
43 | Below ground obstructions | √ | √ | × - BSC don’t appear to have taken account of this in programme – or have they? | No provision - allowance in general delay provision |  | BSC to clarify what is in programme | 0 | 0
44 | Ground conditions | × | × | × | tie to make cost provision |  | OK, but BSC to clarify drawings | 1000 | 2500
45 | Delays associated with ground conditions | × | × | × | tie to make time provision |  | OK, but BSC to clarify drawings | 1000 | 2500
46 | Murrayfield W18 and RRRW 4 LOD issues | × | × | × | tie provision | R | Resist - BSC have priced drawings. BSC to warrant that drawings deliver the ER's - errors, ommissions are an Infraco cost | 100 | 200
47 | Informatives - new ones from CEC | × | × | × | tie provision | R | Resist – part of BSC completing design. BSC to warrant that drawings deliver the ER's errors, ommissions are an Infraco cost | 0 | 100
48 | Informatives – actual new requirements from CEC | × | × | × | tie to make provision for “new “requirements |  | Only new requirements accepted under this | 100 | 200
49 | Informatives – CEC take longer than 20 days to close | × | × | × | tie to make provision |  | OK | 100 | 200
50 | Informatives –delay close out of tie informatives | × | × | × | tie to make provision |  | OK | 100 | 200
51 | Informative - BSC not responsible for those works not directly associated with Phoenix scope | × | × | × | No provision | R | Resist | 50 | 500
52 | Informatives – all construction works can commence ahead of close out of Planning and Technical informatives | × | × | × | No provision - UNABLE TO QUANTIFY risk of unaprovable construction | R | Resist in current for but capable of alteration to become acceptable. This should be at BSC risk | 0 | 0
53 | CEC open comments |  |  |  | tie to make time provision for CEC delays | R | Resist apart from client delay time/costs. BSC to warrant that drawings meet the ER's errors, omissions are an Infraco cost | 200 | 300
54 | Assurance and approvals qualified “ as defined in this proposals” | × | × | × | No provision - contained elsewhere - UNABLE TO QUANTIFY | R | BSC risk | 0 | 0
55 | Ongoing tie Change Order qualifications | × | × | × | tie to make provision | R | Resist - time impact of changes in general delay provision. OTHER UNABLE TO QUANTIFY | 0 | 0
56 | Siemens equipment storage | × | × | √ | tie to make provision for storage only |  | OK subject to negotiation on start date and warranty position to be resolved | 150 | 200
57 | All Siemens kit East of Haymarket in PPP Price | √ | √ | √ | No provision |  | Tradeable | -8000 | 0
58 | Caf novation to tie - 27 trams | √ | √ | √ | Provision for storage |  | OK subject to warranties on outstanding claims/ T&C’s and design assurance and integration complete prior to novation | 150 | 1000
59 | Design work to satisfy approvals | × | × | × | tie provision | R | Resist – part of BSC completing design. BSC to warrant that drawings meet ER's - errors, ommissions are an Infraco cost. | 50 | 150
60 | Price exclusions for design – page 151 - items 1 - 9 | × | × | × | tie provision | R | Resist | 50 | 150
61 | Price exclusions for design – page 151 - items 10 - 11 | × | × | × | tie provision |  | OK | 50 | 150
62 | Price exclusions for design – page 151 - items 12-13 | × | × | × | No provision |  | Contained elsewhere | 0 | 0
63 | Price exclusions for design – page 151 - items 14 | × | × | × | tie provision | R | Resist - SDS incentivisation | 0 | 200
64 | Revised List of Schedule Part 4 Assumptions | x | x | x | NOT POSSIBLE TO MAKE ASSESSMENT | R | Resist as Litmus test | 0 | 0
65 | Extend maintenance break to 10 years | × | × |  | tie to make provision | R | Resist | 0 | 7000
66 | Indexation cap removed | × | × |  | tie to make provision | R | Resist | 0 | 250
67 | Indexation applicable scope proposed to cover mobilisation and spares | × | × |  | tie to make provision | R | Resist | 0 | 120
68 | Renegotiation of liability caps | × | × |  | tie to make provision | R | Resist | 0 | 1000
69 | Introduction of general benchmarking point at 5 years | × | × |  | tie to make provision |  |  | 0 | 0
70 | Maintenance pricing | × | × |  | tie to make provision | R | Resist | 0 | 900
71 | General delay provision | × | × | × | tie to make provision |  | BSC programme is optimistic and contains no scope for delays but lots of opportunity for EOT claims | 5000 | 15000
72 | Revised EOT rates proposed 75% Increase from Infraco Contract | √ | × | × | tie to make provision | R | Resist | 0 | 10000
73 | General contingency | × | × | × | tie to make provision |  | Allow up to ~10% | 3000 | 9000
[8 empty] | 39600 | 106590
| Issue | Scope | Price | Programme | Risk |  | tie Position | Risk Provision
[8 empty] | Low | High
[8 empty] | £k | £k
39 | No VE | × | × | √ |  |  | See tie proposal | -9000 | -3000
| Infraco Risk avoided by agreeing to Phoenix | √ | √ | √ | Infraco have a number of contractual risks which they are liable for if the original scope of the contract is completed. By adopting Phoenix, this potential liability is avoided. |  | This should be considered as part of any evaluation in the proposed price for Phoenix. Numbers shown as negative as it is a potential saving to Infraco. | -21000 | -10000
| Loss of Profit and Overhead recovery claim by Infraco relating to reduced scope of Phoenix | √ | √ | x | Infraco claim loss of Profit / overhead recovery based on reduced scope of Phoenix. |  | Should be negotiated in conjunction with Risk avoided above. Based on Turnover of £91m | 0 | 9100