## Sheet1
Tie Report on Siemens On street Price updated upon receipt of revised proposal 4/8/11
General Information
Work Comprises 1.6km of full track and system and further 1km of system only (Princes Street Track already installed)
Full Contract on street section is 7.2km
Original Siemens Contract Price for on street is £17,454k plus system wide
Rate per km = £2.424k +£252k = £2,676
Materials = 41% (40m/96m) therefore Rate per km (instal only) is £1578k
Anticipated price for On street is 2.6km*1578= £4,102k plus changes 2,000 plus traffic lights 1300 = £7,402 plus programme implications
Details from Contract
Section B | Contract Price | Rate/m | m | total | less materials | claimed | difference
Track | 9822200 | 1364 | 1600 | 2183 | 1288 | 4531 | 3243
Comms | 1612356 | 224 | 2600 | 582 | 343
tramstops |  |  |  | 273 | 161 | 359 | 198
Overhead line | 5664900 | 787 | 2600 | 2046 | 1207 | 1314 | 107
System Wide
Testing | 40751 | 6 | 2600 | 16 | 10
Comms | 3492980 | 189 | 2600 | 491 | 290
Total |  |  |  | 5591 | 3299
Price offered by Siemens = £20,160
Reduced to £14,480
tie overview of 14,480
| Claimed | Tie view | Comments
Extended Prelims |  |  | All work claimed as being in 2014 - not logical
General PM | 1458693 | 784723 | rates taken back to 2013 - risk manager incl in off street - QS resource taken to 3 total
BACK OFFICES Germany | 212906 | 81301 | rates taken back to 2013 - allow 50% and 50% for resource in materials procurement
Depot | 102439 | 0 | Depot all included in Off street price
Operating cost | 339050 | 22930 | Bonds, Guarantees allowed - storage should be on site
Trackwork | 254757 | 0 | Trackwork not proved extended duration
Rail electrification | 173720 | 44373 | note as Back Offices above
Rail electrification UK | 152461 | 148526 | taken back to 2013 rates
Rail Automation | 447310 | 123286 | note as Back Offices above
Rail Automation UK | 171450 | 171343 | taken back to 2013 rates
Travel Expenses | 32776 | 25000 | reduced in line with staff reductions
Traffic Solutions | 110539 | 171771 | taken back to 2013 rates
Sub Total | 3456101 | 1573253 | this is a result of the programme
BAM | 4266657 | 1630319 | time costs reduced to 25% for shared resources - claim omitted
Internal Sub Contracts
Tram stops | 359404 | 161000 | as pro rate from contract above
Sub stations | 280165
OLE | 413702 | 1207000 | as pro rate from contract above incl substations
620561
Traffic Solutions | 1190392 | 1190392 | allow
Core HVLV | 157950 | 50000 | core quote of 35k
Bonds | 22931 | 22931
Risk Warranty | 345881 | 345881 | allow
Risk Implementation | 907684 | 211935 | 5%on construction works only
Changes | 2006500 | 2006500 | details required
unallocated? | 452222 | 0 | ?
Totals | 14480150 | 8399211 | tie maintains that the figure for installation is less than 10m
Note re Back Offices
Siemens has claimed that the 'Back Offices in Germany are extended by the Difference in the Section D end dates.
It is not possible to calculate with the information provided how much impact the on street works will have on the back of office resource
Siemens back office will provide support to the design,procurement and installation of the works. The design and procurement is already covered by the
lump sum price in the Settlement agreement and therefore only a portion should be extra. In addition there is an overlap with the off street installation
tie allows 50%reduction for installation only and 50% for overlap on all off shore costs.