## numbers
Cost Summary for Edinburgh Trams as at 2012/13 Period 6 Ending 15 September 2012
Cost headings | Cost prior to Settlement Agreement |  | Budget post Settlement Agreement |  | COWD to Date |  | ref to 25 October report
| £'m |  | £'m |  | £'m
Project Costs
On street infrastructure
Bilfinger Berger | 9.5 | 1 | 38.8 | 2 | 28.49 | 3 | £18.99m relates to item 2 on table below £9.5m relates to item 1
Siemens
Other | 0 |  | 0 |  | 0.18 | 4 | 2
TOTAL ON STREET | 9.5 |  | 38.8 |  | 28.67
Off street infrastructure
Bilfinger Berger | 31.24 | 5 | 130.71 | 6 | 68.54 | 7 | 1
Siemens
Other | 18.53 | 8 | 18.09 | 9 | 18.6 | 10 | 1
TOTAL OFF STREET | 49.77 |  | 148.8 |  | 87.14
Other Infraco
Bilfinger Berger | 0 |  | 0 |  | 0 |  | 1
Siemens | 0.27 |  | 3.2 |  | 0.66 |  | 1
Settlement of claims & contract de-risk | 49 | 11 | 131 | 12 | 131 | 13 | 1
System wide | 98.35 | 14 | 98.35 | 15 | 98.35 | 16 | 1
TOTAL | 147.62 |  | 232.55 |  | 230.01
Utilities
MUDFA | 57.252 | 17 | 57.252 | 18 | 57.252 | 19 | 6
Post Settlement Agreement | 0 |  | 2.91 | 20 | 2.91 | 21 | 4
Other | 26.168 | 22 | 27.428 | 23 | 25.55 | 24 | 6
TOTAL | 83.42 |  | 87.59 |  | 85.712
Vehicles
Construction/Fabrication | 23.448 |  | 62.4 |  | 23.45 |  | 5
Vehicle design | 2.752 |  |  |  | 2.752 |  | 5
Manuals, special tools and spare parts | 4.403 |  |  |  | 4.403 |  | 5
Delivery of trams | 4.513 |  |  |  | 4.513 |  | 5
Other | 12.78 |  |  |  | 25.71 |  | 5
TOTAL | 47.9 | 25 | 62.4 | 26 | 60.83 | 27
Project Management
Management & Supervision | 52.68 | 28 | 60.96 | 29 | 63.94 | 30 | 6
Insurance | 4.05 | 31 | 4.84 | 32 | 4.962 | 33 | 6
Accommodation, And Support Costs | 12.47 | 34 | 17.31 | 35 | 14.218 | 36 | 6
TOTAL | 69.2 |  | 83.11 |  | 83.12
Land, Property & other costs | 28.85 | 37 | 36.05 | 38 | 34.38 | 39
Readiness for Operations
Transdev and Edinburgh Trams staff | 2.834 |  | 12.07 |  | 3.807 |  | 7
Lothian Buses recharges and other costs | 2.428 |  |  |  | 2.672 |  | 7
Ticketing machines | 0.144 |  |  |  | 0.145 |  | 7
Others | 0.094 |  |  |  | 0.176 |  | 7
TOTAL | 5.5 | 40 | 12.07 | 41 | 6.8 | 42
Comms & Stakeholder
External comms & media | 2.204 |  | 4.36 |  | 2.629 |  | 6
Stakeholder | 0.756 |  |  |  | 0.801 |  | 6
TOTAL | 2.96 | 43 | 4.36 | 44 | 3.43 | 45
Design | 27.18 | 46 | 29.05 | 47 | 26.69 | 48
Legal
DLA | 3.501 |  | 7.22 |  | 3.502 |  | 6
Post Mediation | 0 |  |  |  | 1.294 |  | 6
Other | 2.869 |  |  |  | 2.414 |  | 6
TOTAL | 6.37 | 49 | 7.22 | 50 | 7.21 | 51
Contingency | 0 |  | 34 | 52 | 15.1 | 53
TOTAL | 478.27 |  | 776 |  | 669.092
1
2
3
4
5
6
7
Note on F27: Alan Coyle: remainder of COWD from risk

## notes
Appendix 3 notes;
1 | £9.5m taken from tie's assessment of Princes St works prior to settlement
source deckchair v3 (bdwb) tab
2 | £38.8m is the budget figure from the settlement agreement for on street works.
3 | £28.49m Calculated as follows;
£m
| BB COWD to P6 12/13 on street works | 16.67
| Siemens COWD as at P6 12/13 on street works | 2.32
| Pre settlement Princes St number as per note 1 | 9.5
28.49
4 | Direct York Place works COWD as at P6 12/13 | 0.18
5 | Total BBS COWD as at P4 11/12 | £m
185.82
| accruals | 2.25
188.07
(BB/S split apportioned on the basis of certified to date)
less MOV4 mobilisation and materials paid in period from
| mediation to settlement agreement | -49
| less tie assessment of Princes st work as per note 1 | -9.5
| less system wide costs from cert 47 | -98.35
(except design)
31.22
6 | £130.71 relates to;
| Settlement agreement of £362.5 (less FP descope £2.44) | 360.06
| less £82m as assessment of amounts for EOT | -82
(source scenarios spreadsheet and McGrigors report)
| less MOV4 mobilisation and materials paid in period from | -49
mediation to settlement agreement
| less system wide costs from cert 47 | -98.35
(except design)
130.71
7 | COWD as reported to council on 25 October | 310.42
(off st section)
| less £82m as assessment of amounts for EOT | -82
(source scenarios spreadsheet and McGrigors report)
| less MOV4 mobilisation and materials paid in period from | -49
mediation to settlement agreement
| less system wide costs from cert 47 | -98.35
(except design)
| less tie assessment of Princes st work as per note 1 | -9.5
| gateway adjustment as shown against risk COWD | -3.03
68.54
8 | COWD as at P4 11/12 | 14.78
(source council reports reconciliation v3 - filter off road other)
| Phase 1b | 3.75
18.53
9 | COWD as at P4 11/12 as per note 8 | 18.09
(source council reports reconciliation v3 - filter off road other) less £0.44m gateway adjustment
10 | COWD as at P6 12/13 | 18.6
(source council reports reconciliation v3 - filter off road other)
11 | MOV4 mobilisation and materials | 49
12 | MOV4 mobilisation and materials | 49
| EOT | 82
131
13 | MOV4 mobilisation and materials | 49
| EOT | 82
131
14,15,16 | Cert 47 system wide | 98.35
(mobilisation and prelims less design)
17,18,19 | COWD line | 57.25
(source council reports reconciliation v3 - lines 154-169 COWD P4 11/12 & P6 12/13)
20 | Post Settlement utilities budget from Sept 11 confidential appendix | 2.91
21 | COWD figure = to budget. Remaining COWD £10.7m is shown against the COWD against risk. | 2.91
(total COWD of £13.578m is McNicolas COWD as at P6 12/13 drawn from line 276 of council reports reconciliation v3)
22 | COWD P6 12/13 figure for third party related utilities (eg. BAA, SGN) | 26.17
lines 242-244, 249-250, 253-257, 259,261,264, 270-273
(source council reports reconciliation v3 - COWD P6 12/13)
23 | Post Settlement utilities budget from Sept 11 confidential appendix | 27.43
24 | COWD P4 11/12 figure for third party related utilities (eg. BAA, SGN) | 25.55
lines 242-244, 249-250, 253-257, 259,261,264, 270-273
(source council reports reconciliation v3 - COWD P4 11/12)
25 | COWD P4 11/12 Vehicles | 47.9
(source council reports reconciliation v3 - COWD P4 11/12)
26 | Post Settlement utilities budget from Sept 11 confidential appendix | 62.4
27 | COWD P6 12/13 Vehicles | 60.83
(source council reports reconciliation v3 - COWD P6 12/13)
28 | COWD P4 11/12 | 52.68
(source council reports reconciliation v3 - COWD P4 11/12 - filter PM supervision & PM management column D)
29 | Post Settlement utilities budget from Sept 11 confidential appendix | 60.96
30 | COWD P6 12/13 | 63.94
(source council reports reconciliation v3 - COWD P6 12/13 - filter PM supervision & PM management column D)
31 | COWD P4 11/12 | 4.05
(source council reports reconciliation v3 - COWD P4 11/12 - lines 145-152)
32 | Post Settlement utilities budget from Sept 11 confidential appendix | 4.84
33 | COWD P6 11/12 | 4.96
(source council reports reconciliation v3 - COWD P6 12/13 - lines 145-152)
34 | COWD P4 11/12 | 12.47
(source council reports reconciliation v3 - COWD P4 11/12 - lines 11-15 & 17)
35 | Post Settlement utilities budget from Sept 11 confidential appendix | 17.31
36 | COWD P6 12/13 | 14.22
(source council reports reconciliation v3 - COWD P6 12/13 - lines 11-15 & 17) less £0.5m offset against legal line 71
37 | COWD P4 11/12 | 28.85
(source council reports reconciliation v3 - COWD P4 11/12 - filter PM other column D)
38 | Post Settlement utilities budget from Sept 11 confidential appendix | 36.05
39 | COWD P6 12/13 | 34.38
(source council reports reconciliation v3 - COWD P6 12/13 - filter PM other column D)
40 | COWD P4 11/12 | 5.5
(source council reports reconciliation v3 - COWD P4 11/12 - filter operations column D)
41 | Post Settlement utilities budget from Sept 11 confidential appendix | 12.07
42 | COWD P6 12/13 | 6.8
(source council reports reconciliation v3 - COWD P6 12/13 - filter operations column D)
43 | COWD P4 11/12 | 2.96
(source council reports reconciliation v3 - COWD P4 11/12 - filter PR column D)
44 | Post Settlement utilities budget from Sept 11 confidential appendix | 4.36
45 | COWD P6 12/13 | 3.43
(source council reports reconciliation v3 - COWD P6 12/13 - filter PR column D)
46 | COWD P4 11/12 | 27.18
(source council reports reconciliation v3 - COWD P4 11/12 - filter design column D)
47 | Post Settlement utilities budget from Sept 11 confidential appendix | 29.05
48 | COWD P6 12/13 | 26.69
(source council reports reconciliation v3 - COWD P6 12/13 - filter design column D)
49 | COWD P4 11/12 | 6.37
(source council reports reconciliation v3 - COWD P4 11/12 - filter legal column D)
50 | Post Settlement utilities budget from Sept 11 confidential appendix | 7.22
51 | COWD P6 12/13
| (source council reports reconciliation v3 - COWD P6 12/13 - filter legal column D) less £0.5m against line 45 | 7.21
52 | Post Settlement utilities budget from Sept 11 confidential appendix | 34
53 | T&T cost report P6 12/13 | 15.1