## GRBV 03.04.14 - Appendix 2
Appendix 2 – Cost Summary as at 2013/14 Period 12
Cost headings | Cost heading notes | Cost prior to Settlement Agreement | Budget pre Settlement (tie Ltd figures) | Budget post Settlement Agreement | COWD since Settlement | COWD to Date - Period 6 | COWD to Date - Period 12 | Movement in reporting period | Notes
|  | £'m | £m | £'m | £m | £m | £m | £m
Project Costs
On street infrastructure
Bilfinger Berger |  |  | 65.338 | 38.8 | 44.386 | 39.278 | 44.386 | 5.108 | £6.6m COWD drawn down against contingency. Most of this relates to the value engineering initiative. The remainder relates to on street scope change.
Siemens
On street infrastructure - pre settlement |  | 9.5 |  | 0 | 0 | 9.5 | 9.5 | 0.001
Other |  | 0 | 0 | 0 | 1.44 | 1.439 | 1.44
TOTAL ON STREET | 1 | 9.5 | 65.338 | 38.8 | 45.826 | 50.217 | 55.326 | 5.109
Off street infrastructure
Bilfinger Berger |  | 31.24 | 72.631 | 130.71 | 81.822 | 107.44 | 113.062 | 5.622 | £3.4m drawn down against contingency for Edinburgh Gateway - funded by Transport Scotland
Siemens
Other |  | 18.53 | 0 | 18.09 | 0.43 | 18.792 | 18.96 | 0.168
TOTAL OFF STREET |  | 49.77 | 72.631 | 148.8 | 82.252 | 126.232 | 132.022 | 5.79
Other Infraco
Bilfinger Berger |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Siemens |  | 0.27 | 0 | 3.2 | 0.94 | 1.214 | 1.21 | -0.004
Settlement of claims & contract de-risk |  | 49 | 0 | 131 | 82 | 131 | 131 | 0
System wide |  | 98.35 | 121.93 | 98.35 | 0 | 98.35 | 98.35 | 0
TOTAL |  | 147.62 | 121.93 | 232.55 | 82.94 | 230.564 | 230.56 | -0.004
Utilities
MUDFA |  | 57.252 | 65.7 | 57.252 | -0.002 | 57.25 | 57.25 | 0
Post Settlement Agreement |  | 0 |  | 2.91 | 2.98 | 2.912 | 2.98 | 0.068 | £18.087m has been drawn down for utilities, the COWD of which is allocation against the contingency draw down line.
Other |  | 26.168 |  | 27.428 | -0.418 | 25.868 | 25.75 | -0.118
TOTAL |  | 83.42 | 65.7 | 87.59 | 2.56 | 86.03 | 85.98 | -0.05
Vehicles
Construction/Fabrication |  | 23.448 | 58.2 | 62.4 | -0.0036 | 23.447 | 23.4444 | -0.0026
Vehicle design |  | 2.752 |  |  | 0 | 2.752 | 2.752 | 0
Manuals, special tools and spare parts |  | 4.403 |  |  | 0.551 | 4.954 | 4.954 | 0
Delivery of trams |  | 4.513 |  |  | 0 | 4.513 | 4.513 | 0
Other |  | 12.78 |  |  | 14.94 | 27.128 | 27.72 | 0.592
TOTAL |  | 47.9 | 58.2 | 62.4 | 15.4874 | 62.794 | 63.3834 | 0.5894
Project Management
Management & Supervision | 2 | 52.68 | 87.765 | 60.96 | 18.513 | 68.191 | 71.193 | 3.002
Insurance |  | 4.05 |  | 4.84 | 1.89 | 5.639 | 5.94 | 0.301
Accommodation, And Support Costs | 3 | 12.47 |  | 17.31 | 1.81 | 14.05 | 14.28 | 0.23
TOTAL |  | 69.2 | 87.765 | 83.11 | 22.213 | 87.88 | 91.413 | 3.533
Cost headings | Cost heading notes | Cost prior to Settlement Agreement | Budget pre Settlement (tie Ltd figures) | Budget post Settlement Agreement | COWD since Settlement | COWD to Date - Period 6 | COWD to Date - Period 6 | Movement in reporting period | Notes
Land, Property & other costs | 4 | 28.85 | 20.3 | 36.05 | 1 | 34.534 | 29.85 | -4.684
Readiness for Operations
Transdev and Edinburgh Trams staff |  | 2.834 | 5.567 | 12.07 | 2.366 | 6.301 | 5.2 | -1.101
Lothian Buses recharges and other costs |  | 2.428 |  |  | -0.384 | 2.992 | 2.044 | -0.948
Ticketing machines |  | 0.144 |  |  | 1.196 | 0.811 | 1.34 | 0.529
Others |  | 0.094 |  |  | 0.486 | 0.323 | 0.58 | 0.257
TOTAL |  | 5.5 | 5.567 | 12.07 | 3.664 | 10.427 | 9.164 | -1.263
Comms & Stakeholder | 5
External comms & media |  | 2.204 | 2.962 | 4.36 | 0.506 | 2.691 | 2.71 | 0.019
Stakeholder |  | 0.756 |  |  | 0.080779 | 0.837 | 0.83678 | -0.00022109
TOTAL |  | 2.96 | 2.962 | 4.36 | 0.58678 | 3.528 | 3.5468 | 0.018779
Design |  | 27.18 | 34.2 | 29.05 | -0.49 | 26.69 | 26.69 | 0
Legal
DLA |  | 3.501 | 6.106 | 7.22 | 0.001 | 3.502 | 3.502 | 0
Post Mediation |  | 0 |  |  | 2.14 | 1.867 | 2.14 | 0.273
Other |  | 2.869 |  |  | -0.399 | 2.431 | 2.47 | 0.039
TOTAL |  | 6.37 | 6.106 | 7.22 | 1.742 | 7.8 | 8.112 | 0.312
Contingency |  | 0 | 4.3 | 34 | 33.5 | 33.284 | 33.5 | 0.216
TOTAL |  | 478.27 | 544.999 | 776 | 291.2812 | 759.98 | 769.5472 | 9.5672
[7 empty] | 769.55 | -9.5672
[6 empty] | -759.98 | -0.0028211
Additional cost heading information
1. It should be noted that the cost of the on-street section does not include the utility costs. These are captured in a stand alone line item.
2. Management & Supervision includes;
Project management Staff Costs
Short Term Contractors
Archaeology
DRP Costs
Tax Planning / Governance Costs (Non DLA)
Technical Services
Land agreement/negotiations
CEC staff costs
TSS Second to CEC-Approvals support
T&T Costs
3. Accomodation and Support Costs;
Recruitment Fees
Travel & Subsistence / Conference
Central Overheads
IT & Software Costs
Citypoint - rent,rates,s/c
City Point Overheads
4. Land, Property and other costs;
Integrated Transport Model
Surveys
Consultancy
Network Rail - FDA Work Contract 1
Network Rail - Basic Implementation Agreement
Network Rail - Asset Protection Agreement
Advisors
Advance Purchases of land
Haymarket station compensation
TRO's - Technnical
Financial Consultancy
Commercial advice
5. Comms and Stakeholder
Fees
Tram branding
PR Support
Business development and marketing
Media monitoring
Promotional materials
Websites
Advertising
Internal communications
Communication consultancy services
Public Information
External Resources
S/H – Wider Community Consultations
S/H – Events
S/H – Open for Business
S/H – Communications - MUDFA
S/H – Communications - Infraco

## notes (hidden)
Appendix 3 notes;
1 | £9.5m taken from tie's assessment of Princes St works prior to settlement
source deckchair v3 (bdwb) tab
2 | £38.8m is the budget figure from the settlement agreement for on street works.
3 | £28.49m Calculated as follows; | P9 | P13
£m
| BB COWD to P6 12/13 on street works | 24.79
| Siemens COWD as at P6 12/13 on street works | 2.32
| Pre settlement Princes St number as per note 1 | 9.5
36.61
4 | Direct York Place works COWD as at P6 12/13 | 0.18
5 | Total BBS COWD as at P4 11/12 | £m
185.82
| accruals | 2.25
188.07
(BB/S split apportioned on the basis of certified to date)
less MOV4 mobilisation and materials paid in period from
| mediation to settlement agreement | -49
| less tie assessment of Princes st work as per note 1 | -9.5
| less system wide costs from cert 47 | -98.35
(except design)
31.22
6 | £130.71 relates to;
| Settlement agreement of £362.5 (less FP descope £2.44) | 360.06
| less £82m as assessment of amounts for EOT | -82
(source scenarios spreadsheet and McGrigors report)
| less MOV4 mobilisation and materials paid in period from | -49
mediation to settlement agreement
| less system wide costs from cert 47 | -98.35
(except design)
130.71
7 | COWD as reported in P9 SFLA | 325.73 |  | 338.873
(off st section)
| less £82m as assessment of amounts for EOT | -82 |  | -82
(source scenarios spreadsheet and McGrigors report)
| less MOV4 mobilisation and materials paid in period from | -49 |  | -49
mediation to settlement agreement
| less system wide costs from cert 47 | -98.35 |  | -98.35
(except design)
| less tie assessment of Princes st work as per note 1 | -9.5 |  | -9.5
| gateway adjustment as shown against risk COWD | -3.03 |  | -3.03
|  | 83.85 |  | 96.993
8 | COWD as at P4 11/12 | 14.78
(source council reports reconciliation v3 - filter off road other)
| Phase 1b | 3.75
18.53
9 | COWD as at P4 11/12 as per note 8 | 18.09
(source council reports reconciliation v3 - filter off road other) less £0.44m gateway adjustment
10 | COWD as at P6 12/13 | 18.6
(source council reports reconciliation v3 - filter off road other)
11 | MOV4 mobilisation and materials | 49
12 | MOV4 mobilisation and materials | 49
| EOT | 82
131
13 | MOV4 mobilisation and materials | 49
| EOT | 82
131
14,15,16 | Cert 47 system wide | 98.35
(mobilisation and prelims less design)
17,18,19 | COWD line | 57.25
(source council reports reconciliation v3 - lines 154-169 COWD P4 11/12 & P6 12/13)
20 | Post Settlement utilities budget from Sept 11 confidential appendix | 2.91
21 | COWD figure = to budget. Remaining COWD £10.7m is shown against the COWD against risk. | 2.91
(total COWD of £13.578m is McNicolas COWD as at P6 12/13 drawn from line 276 of council reports reconciliation v3)
22 | COWD P6 12/13 figure for third party related utilities (eg. BAA, SGN) | 26.17
lines 242-244, 249-250, 253-257, 259,261,264, 270-273
(source council reports reconciliation v3 - COWD P6 12/13)
23 | Post Settlement utilities budget from Sept 11 confidential appendix | 27.43
24 | COWD P4 11/12 figure for third party related utilities (eg. BAA, SGN) | 25.55
lines 242-244, 249-250, 253-257, 259,261,264, 270-273
(source council reports reconciliation v3 - COWD P4 11/12)
25 | COWD P4 11/12 Vehicles | 47.9
(source council reports reconciliation v3 - COWD P4 11/12)
26 | Post Settlement utilities budget from Sept 11 confidential appendix | 62.4
27 | COWD P6 12/13 Vehicles | 60.83
(source council reports reconciliation v3 - COWD P6 12/13)
28 | COWD P4 11/12 | 52.68
(source council reports reconciliation v3 - COWD P4 11/12 - filter PM supervision & PM management column D)
29 | Post Settlement utilities budget from Sept 11 confidential appendix | 60.96
30 | COWD P6 12/13 | 63.94
(source council reports reconciliation v3 - COWD P6 12/13 - filter PM supervision & PM management column D)
31 | COWD P4 11/12 | 4.05
(source council reports reconciliation v3 - COWD P4 11/12 - lines 145-152)
32 | Post Settlement utilities budget from Sept 11 confidential appendix | 4.84
33 | COWD P6 11/12 | 4.96
(source council reports reconciliation v3 - COWD P6 12/13 - lines 145-152)
34 | COWD P4 11/12 | 12.47
(source council reports reconciliation v3 - COWD P4 11/12 - lines 11-15 & 17)
35 | Post Settlement utilities budget from Sept 11 confidential appendix | 17.31
36 | COWD P6 12/13 | 14.22
(source council reports reconciliation v3 - COWD P6 12/13 - lines 11-15 & 17) less £0.5m offset against legal line 71
37 | COWD P4 11/12 | 28.85
(source council reports reconciliation v3 - COWD P4 11/12 - filter PM other column D)
38 | Post Settlement utilities budget from Sept 11 confidential appendix | 36.05
39 | COWD P6 12/13 | 34.38
(source council reports reconciliation v3 - COWD P6 12/13 - filter PM other column D)
40 | COWD P4 11/12 | 5.5
(source council reports reconciliation v3 - COWD P4 11/12 - filter operations column D)
41 | Post Settlement utilities budget from Sept 11 confidential appendix | 12.07
42 | COWD P6 12/13 | 6.8
(source council reports reconciliation v3 - COWD P6 12/13 - filter operations column D)
43 | COWD P4 11/12 | 2.96
(source council reports reconciliation v3 - COWD P4 11/12 - filter PR column D)
44 | Post Settlement utilities budget from Sept 11 confidential appendix | 4.36
45 | COWD P6 12/13 | 3.43
(source council reports reconciliation v3 - COWD P6 12/13 - filter PR column D)
46 | COWD P4 11/12 | 27.18
(source council reports reconciliation v3 - COWD P4 11/12 - filter design column D)
47 | Post Settlement utilities budget from Sept 11 confidential appendix | 29.05
48 | COWD P6 12/13 | 26.69
(source council reports reconciliation v3 - COWD P6 12/13 - filter design column D)
49 | COWD P4 11/12 | 6.37
(source council reports reconciliation v3 - COWD P4 11/12 - filter legal column D)
50 | Post Settlement utilities budget from Sept 11 confidential appendix | 7.22
51 | COWD P6 12/13
| (source council reports reconciliation v3 - COWD P6 12/13 - filter legal column D) less £0.5m against line 45 | 7.21
52 | Post Settlement utilities budget from Sept 11 confidential appendix | 34
53 | T&T cost report P6 12/13 | 15.1

## cap to rev adj (hidden)
Centre | Description | Account | Acc Description | Corp | Sub Centre | Sub Description | CY Budget | Period Budget | Actual | Encumbrance | Budget Variance | Forecast Budget | Forecast Variance | Notes
55023 | PROJECT MANAGEMENT | 1031 | APTC Basic Pay | 1 | 0 | General | 0 | 0 | 289133.73 | 0 | 289133.73 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1032 | APTC Overtime | 1 | 0 | General | 0 | 0 | 970.97 | 0 | 970.97 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1034 | APTC Allowances & Other | 1 | 0 | General | 0 | 0 | 250.47 | 0 | 250.47 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1036 | APTC Absence Pay | 1 | 0 | General | 0 | 0 | 7150.73 | 0 | 7150.73 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1038 | APTC N.I. | 1 | 0 | General | 0 | 0 | 27257.5 | 0 | 27257.5 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1039 | APTC Superann | 1 | 0 | General | 0 | 0 | 46032.16 | 0 | 46032.16 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1621 | Technical Staff Basic Pay | 1 | 0 | General | 0 | 0 | 176118.56 | 0 | 176118.56 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1622 | Technical Staff Overtime | 1 | 0 | General | 0 | 0 | 459.03 | 0 | 459.03 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1628 | Technical Staff N.I. | 1 | 0 | General | 0 | 0 | 17574.72 | 0 | 17574.72 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1629 | Technical Staff Superan | 1 | 0 | General | 0 | 0 | 22525.93 | 0 | 22525.93 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1801 | Pension Payments | 1 | 0 | General | 0 | 0 | 3713.88 | 0 | 3713.88 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1893 | Vera Payment | 1 | 0 | General | 0 | 0 | 11994.48 | 0 | 11994.48 | 0 | 0 | CEC staffing costs Apr - Dec 12
55023 | PROJECT MANAGEMENT | 1991 | IFRS Holiday Accrual | 1 | 0 | General | 0 | 0 | -36021.72 | 0 | -36021.72 | 0 | 0
55023 | PROJECT MANAGEMENT | 2151 | Electricity | 1 | 0 | General | 0 | 0 | 8145.47 | 0 | 8145.47 | 0 | 0
55023 | PROJECT MANAGEMENT | 2161 | Gas | 1 | 0 | General | 0 | 0 | 1521.56 | 0 | 1521.56 | 0 | 0
55023 | PROJECT MANAGEMENT | 2185 | Carbon Tax | 1 | 0 | General | 4583.19 | 4583.19 | 4583.19 | 0 | 0 | 0 | -4583.19
55023 | PROJECT MANAGEMENT | 2692 | Vehicle Hire - External | 1 | 0 | General | 0 | 0 | 122.86 | 0 | 122.86 | 0 | 0
55023 | PROJECT MANAGEMENT | 2801 | Staff Travel - Edinburgh | 1 | 0 | General | 0 | 0 | 1726.55 | 0 | 1726.55 | 0 | 0
55023 | PROJECT MANAGEMENT | 2811 | Staff Travel - Within Uk | 1 | 0 | General | 0 | 0 | 373.1 | 0 | 373.1 | 0 | 0
55023 | PROJECT MANAGEMENT | 2871 | Taxis | 1 | 0 | General | 0 | 0 | 86.69 | 0 | 86.69 | 0 | 0
55023 | PROJECT MANAGEMENT | 3061 | Operational Materials | 1 | 0 | General | 0 | 0 | 32.94 | 0 | 32.94 | 0 | 0
55023 | PROJECT MANAGEMENT | 3091 | Books & Publications | 1 | 0 | General | 0 | 0 | 42.39 | 0 | 42.39 | 0 | 0
55023 | PROJECT MANAGEMENT | 3301 | Food & Drink | 1 | 0 | General | 0 | 0 | 1710.32 | 0 | 1710.32 | 0 | 0
55023 | PROJECT MANAGEMENT | 3311 | Other Catering Recharges | 1 | 0 | General | 0 | 0 | 425.72 | 0 | 425.72 | 0 | 0
55023 | PROJECT MANAGEMENT | 3421 | Stationery | 1 | 0 | General | 0 | 0 | 30.06 | 0 | 30.06 | 0 | 0
55023 | PROJECT MANAGEMENT | 3461 | Computer Consumables | 1 | 0 | General | 0 | 0 | 249.83 | 0 | 249.83 | 0 | 0
55023 | PROJECT MANAGEMENT | 3501 | Legal Fees | 1 | 0 | General | 0 | 0 | 2127 | 0 | 2127 | 0 | 0
55023 | PROJECT MANAGEMENT | 3531 | Marketing | 1 | 0 | General | 0 | 0 | 5000 | 0 | 5000 | 0 | 0
55023 | PROJECT MANAGEMENT | 3601 | Telephone & Fax Charges | 1 | 0 | General | 0 | 0 | 3161.25 | 0 | 3161.25 | 0 | 0
55023 | PROJECT MANAGEMENT | 3611 | Computer Equipment | 1 | 0 | General | 0 | 0 | 3161.16 | 0 | 3161.16 | 0 | 0
55023 | PROJECT MANAGEMENT | 3621 | Syntegra Charges | 1 | 0 | General | 0 | 0 | 109.62 | 0 | 109.62 | 0 | 0
55023 | PROJECT MANAGEMENT | 3721 | Conference & Subsistence Edin | 1 | 0 | General | 0 | 0 | 28.46 | 0 | 28.46 | 0 | 0
55023 | PROJECT MANAGEMENT | 3995 | Other Expenses | 1 | 0 | General | 0 | 0 | 740.76 | 0 | 740.76 | 0 | 0
55023 | PROJECT MANAGEMENT | 4003 | Ers Rchrg-Hghwy Maint Non-Comp | 1 | 0 | General | 0 | 0 | 77.34 | 0 | 77.34 | 0 | 0
55023 | PROJECT MANAGEMENT | 4511 | Ext Contractors - Recoverable | 1 | 0 | General | 0 | 0 | 517.21 | 0 | 517.21 | 0 | 0
55023 | PROJECT MANAGEMENT | 4833 | Fees General | 1 | 0 | General | 0 | 0 | 42052.65 | 0 | 42052.65 | 0 | 0 | Audit fees
55023 | PROJECT MANAGEMENT | 4841 | Fees Consultants | 1 | 0 | General | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | Alastair Richards' 'fee'
55023 | PROJECT MANAGEMENT | 7197 | Recharge Salaries To Capital | 1 | 0 | General | 0 | 0 | -586989.15 | 0 | -586989.15 | 0 | 0 | CEC staffing recharge to capital Apr - Dec 12
55024 | COMMUNICATIONS | 1031 | APTC Basic Pay | 1 | 0 | General | 0 | 0 | 36475.15 | 0 | 36475.15 | 0 | 0 | Non-Core Comms staffing costs | 81197.42
55024 | COMMUNICATIONS | 1034 | APTC Allowances & Other | 1 | 0 | General | 0 | 0 | 201.31 | 0 | 201.31 | 0 | 0 | Non-Core Comms staffing costs
55024 | COMMUNICATIONS | 1037 | APTC - Agency Staff | 1 | 0 | General | 0 | 0 | 13377.83 | 0 | 13377.83 | 0 | 0 | Non-Core Comms staffing costs
55024 | COMMUNICATIONS | 1038 | APTC N.I. | 1 | 0 | General | 0 | 0 | 3103.82 | 0 | 3103.82 | 0 | 0 | Non-Core Comms staffing costs
55024 | COMMUNICATIONS | 1039 | APTC Superann | 1 | 0 | General | 0 | 0 | 6254.41 | 0 | 6254.41 | 0 | 0 | Non-Core Comms staffing costs
55024 | COMMUNICATIONS | 2061 | R & M - Security | 1 | 0 | General | 0 | 0 | 180 | 0 | 180 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2091 | R & M - Internal Fees | 1 | 0 | General | 0 | 0 | 882 | 0 | 882 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2101 | R & M - External Fees | 1 | 0 | General | 0 | 0 | 25146.9 | 0 | 25146.9 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2151 | Electricity | 1 | 0 | General | 0 | 0 | 2218.08 | 0 | 2218.08 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2161 | Gas | 1 | 0 | General | 0 | 0 | 113.82 | 0 | 113.82 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2185 | Carbon Tax | 1 | 0 | General | 111.77 | 111.77 | 111.77 | 0 | 0 | 0 | -111.77 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2201 | Rents - External | 1 | 0 | General | 0 | 0 | 35424.66 | 0 | 35424.66 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 2801 | Staff Travel - Edinburgh | 1 | 0 | General | 0 | 0 | 21.1 | 0 | 21.1 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 3311 | Other Catering Recharges | 1 | 0 | General | 0 | 0 | 32.8 | 0 | 32.8 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 3441 | Advertising - External | 1 | 0 | General | 0 | 0 | 2470.6 | 0 | 2470.6 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 3501 | Legal Fees | 1 | 0 | General | 0 | 0 | 2664 | 0 | 2664 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 3601 | Telephone & Fax Charges | 1 | 0 | General | 0 | 0 | 507.71 | 0 | 507.71 | 0 | 0 | Non-Core Comms (Incl. Shandwick Place Shop)
55024 | COMMUNICATIONS | 4841 | Fees Consultants | 1 | 0 | General | 0 | 0 | 169315.66 | 0 | 169315.66 | 0 | 0 | Primarily BIG partnership
55024 | COMMUNICATIONS | 7197 | Recharge Salaries To Capital | 1 | 0 | General | 0 | 0 | -16628.77 | 0 | -16628.77 | 0 | 0 | Non-Core Comms staffing correction | 281872.85
55025 | GETTING READY FOR OPERATIONS | 1940 | 3rd Party Staff Recharges | 1 | 0 | General | 0 | 0 | 702102.01 | 0 | 702102.01 | 0 | 0 | LB monthly recharge - Staffing element
55025 | GETTING READY FOR OPERATIONS | 2151 | Electricity | 1 | 0 | General | 0 | 0 | 58004.45 | 0 | 58004.45 | 0 | 0 | Depot running costs
55025 | GETTING READY FOR OPERATIONS | 2185 | Carbon Tax | 1 | 0 | General | 2779.98 | 2779.98 | 2779.98 | 0 | 0 | 0 | -2779.98
55025 | GETTING READY FOR OPERATIONS | 2231 | Rates | 1 | 0 | General | 0 | 0 | 641200 | 0 | 641200 | 0 | 0 | Depot rates
55025 | GETTING READY FOR OPERATIONS | 2261 | Water | 1 | 0 | General | 0 | 0 | 16820.18 | 0 | 16820.18 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 2301 | Cleaning | 1 | 0 | General | 0 | 0 | -609 | 0 | -609 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 2312 | Refuse Disposal Int Recharges | 1 | 0 | General | 0 | 0 | -69.16 | 0 | -69.16 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 2911 | Vehicle Insurance | 1 | 0 | General | 0 | 0 | 2650 | 0 | 2650 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 3001 | Operational Equipment | 1 | 0 | General | 0 | 0 | 403942.42 | 0 | 403942.42 | 0 | 0 | LB monthly recharge - Non-staffing element
55025 | GETTING READY FOR OPERATIONS | 3003 | Operational Equip - Lease/Hire | 1 | 0 | General | 0 | 0 | 2095.59 | 0 | 2095.59 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 3301 | Food & Drink | 1 | 0 | General | 0 | 0 | 780 | 0 | 780 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 3501 | Legal Fees | 1 | 0 | General | 0 | 0 | 59342.72 | 0 | 59342.72 | 0 | 0 | Ashurst / Shepherd & Wedderburn
55025 | GETTING READY FOR OPERATIONS | 3561 | Security - External | 1 | 0 | General | 0 | 0 | 149284.87 | 54816.32 | 204101.19 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 3601 | Telephone & Fax Charges | 1 | 0 | General | 0 | 0 | 4550.53 | 0 | 4550.53 | 0 | 0
55025 | GETTING READY FOR OPERATIONS | 4841 | Fees Consultants | 1 | 0 | General | 0 | 0 | 142635.21 | 0 | 142635.21 | 0 | 0 | Navigant / Invercap | 2185509.8
59431 | T01 - PROJECT MANAGEMENT | 7841 | Internal Fees General | 1 | 0 | General | 0 | 0 | 122650.55 | 0 | 122650.55 | 0 | 0 | CEC agency staff
59431 | T01 - PROJECT MANAGEMENT | 7841 | Internal Fees General | 1 | 471 | Trams 01 | 0 | 0 | 585470.46 | 0 | 585470.46 | 0 | 0 | CEC staffing recharge to capital Apr - Dec 12
59431 | T01 - PROJECT MANAGEMENT | 7843 | External Fees General | 1 | 472 | Trams 02 | 0 | 0 | 97146.72 | 1100 | 98246.72 | 0 | 0 | T01.05 IT / fit-out costs
59431 | T01 - PROJECT MANAGEMENT | 7852 | Technical Support | 1 | 0 | General | 0 | 0 | 5188.26 | 0 | 5188.26 | 0 | 0 | T01.05 IT costs
59431 | T01 - PROJECT MANAGEMENT | 7852 | Technical Support | 1 | 471 | Trams 01 | 0 | 0 | 735 | 0 | 735 | 0 | 0 | T01.05 IT costs
59431 | T01 - PROJECT MANAGEMENT | 7852 | Technical Support | 1 | 472 | Trams 02 | 0 | 0 | 423501.18 | 0 | 423501.18 | 0 | 0 | T01.05 IT costs
59434 | T03 - LEGALS | 7849 | Legal Services | 1 | 0 | General | 0 | 0 | 30179.5 | 0 | 30179.5 | 0 | 0 | CEC internal recharges
59434 | T03 - LEGALS | 7849 | Legal Services | 1 | 471 | Trams 01 | 0 | 0 | 143762.1 | 0 | 143762.1 | 0 | 0 | External legal fees
59443 | T12 - COMMUNICATIONS | 7843 | External Fees General | 1 | 0 | General | 0 | 0 | 1625.68 | 0 | 1625.68 | 0 | 0 | Core Comms costs (excl. staff)
59443 | T12 - COMMUNICATIONS | 7843 | External Fees General | 1 | 474 | Trams 04 | 0 | 0 | 45279.26 | 0 | 45279.26 | 0 | 0 | Core Comms costs (excl. staff)
59443 | T12 - COMMUNICATIONS | 7843 | External Fees General | 1 | 476 | Trams 06 | 0 | 0 | 10920.61 | 0 | 10920.61 | 0 | 0 | Core Comms costs (excl. staff)
59448 | T17 - INSURANCE | 7843 | External Fees General | 1 | 0 | General | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | CEC internal recharge
59448 | T17 - INSURANCE | 7843 | External Fees General | 1 | 474 | Trams 04 | 0 | 0 | 20980.9 | 0 | 20980.9 | 0 | 0 | Insurance claims / fees
59433 | T02 - DPOF | 7843 | External Fees General | 1 | 0 | General | 0 | 0 | 69408.62 | 0 | 69408.62 | 0 | 0 | Power for commissioning (excl. Depot running costs)
59436 | T05 - JRC | 7845 | External Fees Consultants | 1 | 0 | General | 0 | 0 | 127165 | 0 | 127165 | 0 | 0
4242593.91
Note on P40: Alan Coyle: deducted from PM management costs
Note on P58: Alan Coyle: deducted from PM management costs
Note on P73: Alan Coyle: deducted from off street infraco