## Summary of Options
Financial Comparison of Core Possible Outcomes
| Continue as is w/Silver Bullet |  | Carlisle |  |  | COWD |  | Terminate & Reprocure Now (Separation) | [7 empty] | Infraco Build to HYM | Infraco Build to HYM |  | Terminate & Postpone
| w/Silver Bullet | BSC Obstinacy | Carlisle tie price | Carlisle BSC price |  | to P11 Jan-11 (fcst Cert Feb-11) | Win litigation (Infraco Default) | Win litigation (Infraco Default) | Win litigation (Infraco Default) | Lose litigation (tie Default) | Lose litigation (tie Default) | Lose litigation (tie Default) | Settle out of court | Settle out of court | Settle out of court | Phoenix | Phoenix | Phoenix | Reprocure after winning Litigation | Reprocure after winning Litigation | Reprocure after winning Litigation | Cancel after losing litigation
| (P'fork 3C) | [5 empty] | Low | QS View | High | Low | QS View | High | Low | QS View | High | QS View | QS View | BB 'View' | Low | QS View | High
| B | C | D | E |  | A |  | F |  |  | G |  |  | H |  | Low | High |  |  | I |  | J
Infrastructure ready to operate: |  |  |  |  | Infrastructure ready to operate:
Airport to Haymarket | 2012-10-01 | 2013-12-01 | 2012-10-01 | 2013-06-01 | Airport to Haymarket | n/a | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2014-12-01 | 2014-12-01 | 2014-12-01 | n/a
Haymarket to St A Sq | 2012-10-01 | 2015-12-01 | 2013-12-01 | 2013-12-01 | Haymarket to St A Sq | n/a | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | n/a
St A Sq to FOW | 2012-10-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | St A Sq to FOW | n/a | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | n/a
FOW to Newhaven | 2012-10-01 | 2015-12-01 | 2017-12-01 | 2017-12-01 | FOW to Newhaven | n/a | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2019-12-01 | 2019-12-01 | 2019-12-01 | n/a
BB+S |  |  |  |  | BB+S
Constn Works Price (BB+S) | 239.6 | 239.6 | 180.3 | 333.9 | Constn Works Price (BB+S) | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | linked
Value Engineering (included) | -6.1 | -6.1 | -11.3 | 0
Existing Change - Princes St | 9 | 9 | 9 |  | Existing Change - Princes St | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | linked
Existing Change - Other | 35.5 | 45.3 | 43.8 |  | Existing Change - Other | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | linked
Existing Prolongation | 21 | 21 | 3.5
Further on-street change and disruption | 21.1 | 21.1
Further allowance for risks and delay | 20.4 | 150 | 16.5 | 40
Infrastructure (BB+S) | 340.5 | 479.9 | 241.8 | 373.9 | Entitlement for work done (BB+S) | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625
[5 empty] | Certified in advance of work done (BB+S) | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | linked
[5 empty] | Certified to Date (BB+S) | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008
-11.039
Infrastructure (BB+S) | 340.5 | 479.9 | 241.8 | 373.9 | Infrastructure (BB+S) Certified | 112.969 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008
[5 empty] | Infraco Build to Haymarket | [10 empty] | 144.763 | 144.763 | 249.892
Vehicles (CAF) | 58.5 | 58.5 | 58.5 | 60.8 | Vehicles (CAF) | 47.458 | 61.5 | 62.5 | 63.5 | 61.5 | 62.5 | 63.5 | 61.5 | 62.5 | 63.5 | 62.5 | 62.5 | 60 | 61.5 | 62.5 | 63.5 | 62.5
Design Cost Post Novation (SDS) | 5 | 14 | 14 | 15.9 | Design Post Novation (SDS) | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | linked
[5 empty] | SDS design risk | 1.029 | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 2 | 8 | 2 | 2 | 6
Total BSC | 404 | 552.4 | 314.3 | 450.6 | Total BSC | 169.456 | 195.508 | 196.508 | 201.508 | 195.508 | 196.508 | 201.508 | 195.508 | 196.508 | 201.508 | 341.271 | 341.271 | 449.9 | 195.508 | 196.508 | 201.508 | 194.508
Interim Works & Reinstatement
[5 empty] | Interim Works during Reprocure |  | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 0 | 0 | 0
[5 empty] | Reinstate/remedials during Reprocure |  | 1.5 | 2.5 | 5 | 1.5 | 2.5 | 5 | 1.5 | 2.5 | 5 | 2.5 | 2.5 | 2.5 | 10 | 10 | 10 | 10
[5 empty] | Reinstatement following cancellation | [16 empty] | 40
[5 empty] | Total |  | 11.393 | 12.393 | 14.893 | 11.393 | 12.393 | 14.893 | 11.393 | 12.393 | 14.893 | 2.5 | 2.5 | 2.5 | 10 | 10 | 10 | 50
New Procurement Costs |  |  |  |  | New Procurement Costs
Infrastructure - to HYM |  |  |  |  | Infrastructure - to HYM |  | 140.816 | 144.763 | 169.215 | 140.816 | 144.763 | 169.215 | 140.816 | 144.763 | 169.215 |  |  |  | 162.7305 | 167.2917 | 195.5491
Infrastructure - to SAS |  |  | 13.9 | 22.9 | Infrastructure - to SAS |  | 17.388 | 19.21 | 20.203 | 17.388 | 19.21 | 20.203 | 17.388 | 19.21 | 20.203 | 19.21 | 19.21 | 19.21 | 20.094 | 22.1996 | 23.3471
Infrastructure - to FOW |  |  | 40 | 40 | Infrastructure - to FOW |  | 30.743 | 35.121 | 36.578 | 30.743 | 35.121 | 36.578 | 30.743 | 35.121 | 36.578 | 35.121 | 35.121 | 35.121 | 35.5274 | 40.5867 | 42.2705
Infrastructure - to NHN |  |  | 20 | 20 | Infrastructure - to NHN |  | 40.297 | 45.915 | 55.991 | 40.297 | 45.915 | 55.991 | 40.297 | 45.915 | 55.991 | 45.915 | 45.915 | 45.915 | 46.5682 | 53.0605 | 64.7046
Risk allowance on new procurement |  |  | 20 | 30 | Further Risk allowance on new procurement | [13 empty] | 29 | 29 | 29
[5 empty] | Value Engineering Opportunities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 3rd Party funded (base allowed) |  | -4.3 | -4.3 | -4.3 | -4.3 | -4.3 | -4.3 | 0 | 0 | 0 | 0 | 0 | 0 | -4.3 | -4.3 | -4.3
Total New Procurement | 0 | 0 | 93.9 | 112.9 | Total New Procurement | 0 | 224.944 | 240.709 | 277.687 | 224.944 | 240.709 | 277.687 | 229.244 | 245.009 | 281.987 | 100.246 | 100.246 | 100.246 | 289.6201 | 307.8385 | 350.5712 | 0
Total Infrastructure & vehicles | 404 | 552.4 | 408.2 | 563.5 | Total Infrastructure & vehicles | 169.456 | 431.845 | 449.61 | 494.088 | 431.845 | 449.61 | 494.088 | 436.145 | 453.91 | 498.388 | 444.017 | 444.017 | 552.646 | 495.1281 | 514.3465 | 562.0792 | 244.508
Termination Costs
[5 empty] | Securing sites |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 2
[5 empty] | Third party costs (Project Termination Scenario) | [16 empty] | 14.8
[5 empty] | Total Termination Costs |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 16.8
Other Costs |  |  |  |  | Other Costs
Ph1b Payment to BSC | 3.2 | 3.2 | 3.2 | 3.2 | Ph1b Payment to BSC | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
Design Pre Nov incl Ph1b and Utilities | 28.7 | 32.3 | 32.3 | 32.3 | Design Pre Nov incl Ph1b and Utilities | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7
Utilties and Other Infrastructure | 78.7 | 89.9 | 89.9 | 89.9 | Utilties and Other Infrastructure | 95.208 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 98.925
Project Costs | 91.5 | 109.5 | 94.2 | 94.2 | Project Costs - to date | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156
Project Costs - Post Termination |  |  |  |  | Project Costs - to go |  | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 23.2 | 23.2 | 23.2 | 27.7 | 27.7 | 27.7 | 8.6
Other Costs - Incl Land | 33.8 | 33.8 | 33.8 | 33.8 | Other Costs - Incl Land | 35.234 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973
Other Costs | 235.9 | 268.7 | 253.4 | 253.4 | Other Costs | 236.498 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 266.354 | 266.354 | 266.354 | 270.854 | 270.854 | 270.854 | 250.554
Gross Outturn Costs | 639.9 | 821.1 | 661.6 | 816.9 | Gross Outturn Costs | 405.954 | 705.199 | 722.964 | 767.442 | 705.199 | 722.964 | 767.442 | 709.499 | 727.264 | 771.742 | 710.371 | 710.371 | 819 | 772.4821 | 791.7005 | 839.4332 | 511.862
Highly Sensitive Variable Elements
Gross Outturn Costs
[5 empty] | General and Specifc Scope Risk + Exclusions | [10 empty] | 39.6 | 106.6
[5 empty] | Infraco Avoidance and Loss of Profit | [12 empty] | -3.9
[5 empty] | Bond call (BB+S) |  | -25 | -25 | -25 | -10 | -10 | -10 | -10 | -10 | -10 | 0 | 0 | 0 | -25 | -25 | -25 | -25
[5 empty] | BSC - Settlement Premium |  | 2017-12-01: 10; 2017-12-01: 10; 2017-12-01: 10 | 0 | 0 | 0
[5 empty] | Vehicles - Lease / Sale recoveries |  | -10.5 | -10.5 | 0 | -10.5 | -10.5 | 0 | -10.5 | -10.5 | 0 | 0 | 0 | 0 | -13.5 | -13.5 | -13.5 | -46.8
[5 empty] | Vehicles - Lease / Sale recoveries - Ops Stripped back out |  | 2017-12-01: 10.5; 2017-12-01: 10.5; 2017-12-01: 0
[5 empty] | Re-Design (risk of SDS not completing) |  | 5 | 10 | 15 | 5 | 10 | 15 | 5 | 10 | 15 | 10 | 10 | 10 | 15 | 15 | 15
[5 empty] | tie litigation & professional costs |  | 30 | 30 | 30 | 30 | 30 | 30 | 2 | 3 | 4 | 3 | 3 | 3 | 30 | 30 | 30 | 30
[5 empty] | BSC Loss of profits in case of tie default |  | 5: 35; 10: 35; 15: 35 | [6 empty] | 35
[5 empty] | BSC Litigation Costs |  | 5: 30; 10: 30; 15: 30 | [6 empty] | 30
[5 empty] | Recovery in case of Infraco Default |  | 5: -67.72; 10: -47.72; 15: -23.86 |  |  |  | -67.72 | -47.72 | -23.86
[5 empty] | Sub-total HS Variable Elements |  | -68.22 | -43.22 | -3.86 | 79.5 | 84.5 | 100 | 7 | 13 | 19 | 52.6 | 119.6 | 9.1 | 6.5 | 6.5 | 6.5 | 23.2
Total Phase 1a | 639.9 | 821.1 | 661.6 | 816.9 | Total Phase 1a | 405.954 | 636.979 | 679.744 | 763.582 | 784.699 | 807.464 | 867.442 | 716.499 | 740.264 | 790.742 | 762.971 | 829.971 | 828.1 | 778.9821 | 798.2005 | 845.9332 | 535.062
Incremental Options |  |  |  |  | Incremental Options
[5 empty] | Summary of Positions |  | Low | QS view | High | Low | QS view | High | Low | QS view | High | QS view | QS view | QS view | Low | QS view | High
[5 empty] | Sub-total - Newhaven |  | 636.979 | 679.744 | 763.582 | 784.699 | 807.464 | 867.442 | 716.499 | 740.264 | 790.742 | 762.971 | 829.971 | 828.1 | 778.9821 | 798.2005 | 845.9332
[5 empty] | Sub-total - Foot of the Walk |  | 596.682 | 633.829 | 707.591 | 744.402 | 761.549 | 811.451 | 676.202 | 694.349 | 734.751 | 717.056 | 784.056 | 782.185 | 732.4139 | 745.14 | 781.2286
[5 empty] | Sub-total - St Andrews Square |  | 565.939 | 598.708 | 671.013 | 713.659 | 726.428 | 774.873 | 645.459 | 659.228 | 698.173 | 681.935 | 748.935 | 747.064 | 696.8865 | 704.5533 | 738.9582
[5 empty] | Sub-total - Haymarket |  | 548.551 | 579.498 | 650.81 | 696.271 | 707.218 | 754.67 | 628.071 | 640.018 | 677.97 | 662.725 | 729.725 | 727.854 | 676.7925 | 682.3537 | 715.6111
Notes:
It is assumed that the ETP will be completed in the incremental options and therefore, for the purpose of optioneering "recovery for Infraco default" is assumed
Note on B13: SMcGarrity: CWP £238.6m Less: Prov Sums 3rd party funded £3.1m Less: Target savings on Prov Sums (Picardy) £3.0m Add: Contingency for non VE delivery £1.2m Add £6.1m VE forecast
Note on B16: SMcGarrity: Design Development £14.1m Ground Conditions £9.9m Cleint & Other changes £11.5m NB All based on QS view of change register as it stood back in March 2010 at time of Pitchfork 1
Note on B17: SMcGarrity: Per DM workings attached to 16/3/ email - includes EOT1 agreed
Note on B18: SMcGarrity: On-street scope changes £9.9m On-street dealy and dusruption £8.2m Risk re OSSA credit £3m Assumes no premium costs which would be associated with doing remaining on-street under an OSSA similar to PSSA See DM email to SMcG of 6/3 and SMcG powerpoint analysis of option 3c
Note on B19: SMcGarrity: 4mth Delay to start on street £4m (see DM workings attached to 16/3 email) Further Delay allowance £12.1m (as above) VE Deliverability £4.3m
Note on B20: SMcGarrity: Pitchfork was based upon the Change Register(s) and QS view extant back in March 2010. I dont think it would move around by more than a few £m +/_ but we need to keep an eye on reconciliation to the current reported QS view!
Note on B57: SMcGarrity: See seprate tab which reconciles what was included in P'fork 3C (£78.7m) compared to whats getting reported as AFC now (£89.9m) - needs watching as MUDFA final account settled.
Note on B58: SMcGarrity: See Project Costs tab - forecast to Feb 12 = £87.5m plus £0.5m per month for prolongation to Oct 2012 = £91.5m.
Note on C19: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years prelims for BSC = £80m plus estimate for on street premium costs £40m plus movement to top end of on-street design = £30m.
Note on C27: SMcGarrity: Assumes we'd end up haing to pay them the £14m design costs as per Carlisle 'Explantory Note'
Note on C58: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years at £500k per month on top of the Sillver Bullet scenario. Big factor would be the Commercial/DRP costs associated with toughing it out issue by issue.
Note on E20: SMcGarrity: Recon to tie Carlisle offer for 'Part A' as per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on E42: SMcGarrity: Allowance for market uncertainties in procurement and subsequent retained risk - final amount would be an output from a formal QRA.
Note on E45: SMcGarrity: Recon to Carlisle "Explanatory Note" per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on E58: SMcGarrity: Aggregate Project Costs assumed materially the same as the term & reprocurement option in aggregate.
Note on F13: SMcGarrity: From BSC revised proposal dated 12/9/10 - BB £215.3m plus Siemens £118.8m to Haymarket only.
Note on F19: SMcGarrity: Draft terms from BSC fall well short of a genuine GMP. Also would need to pick up the pieces on Princes st defects and figure out who is taking responsibility for Princes St. Final amount would be an output from a formal QRA.
Note on F26: SMcGarrity: CAF price including storage costs from BSC revised proposal dated 12/9/10.
Note on I20: SMcGarrity: As estimated by DM at end P8 Cert - see tab included.
Note on I22: SMcGarrity: As certified end P9
Note on I24: SMcGarrity: BB+S per Latest AFC sheet Less Post Novation design £5.7m (see below)
Note on L38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on L70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on L76: Assumption taken currently that 20% of CWP is recoverable with Infraco Default scenario. Legal view to confirm if this is the case or whether or not the full construction cost would apply. If building incrementally is this pro-rata? Low £236.8m CWP + £100m change * 20% Medium £236.8m CWP * 20% High £236.8m/2 * 20%
Note on N57: See Latest AFC reconciliation sheet. Includes £3m contingency and £3m tax
Note on N58: SMcGarrity: See tab for Project Costs
Note on N59: SMcGarrity: See tab for Project Costs
Note on N60: Gregor Roberts: see latest AFC worksheet
Note on O38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on O44: TP cost forecast P8: Fports: BP Rd £0.6m; LRd £2.2m; OT £0.5m; Tow Pl £0.1m & RBS £0.4m
Note on O68: Gregor Roberts: assumes £10m bond call appropriate in lose situation for Princes St defective works
Note on O70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on Q44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on R20: SMcGarrity: As estimated by DM at end P6 Cert - see tab included. Will need to be updated to date of termination but on the basis they stopped work in Oct and we're not paying prelims it should not move a lot?
Note on R32: SMcGarrity: Placemaker - assuming its legal, honest and decent to engage with existing subbies, and CEC are happy with exposure (ie we are not going to canx) - we assume there will be works which it will be good VfM to do works (especially at Depot and other bits off-street) between termination and new procurement. DM updated view is hat this will be no more than £10m maximum. Pricing has now been finalised and any value taken off the "to go" element
Note on R33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on R38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on R44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on R69: SMcGarrity: Highly uncertain what BSC would walk away for - assume here they'd want the bond call back plus something for their trouble. Very hard to prove VfM except against what it avoids (uncertain litigation, protracted uncertainty as to financial outcome) . Additional £10m included, which would take our assessment of value premium to c£45m
Note on R70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on R73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on S44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on U25: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on U32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on U33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on U38: Assumed that BB are able to build in-line with CWP+Changes+EoT+Escalation
Note on U44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on U50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on U70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on U73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on V25: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on V32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on V33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on V38: Assumed that BB are able to build in-line with CWP+Changes+EoT+Escalation
Note on V44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on V50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on V70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on V73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on W25: Includes Infraco Price £333.9m (Infraco Carlisle Offer) +£40m further risk for behaviour and lack of change in contract less Value certified to Date
Note on W32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on W33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on W44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on W50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on W70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on W73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on Y59: SMcGarrity: Additional 2 yrs prolongation and escalation - say £5m
Note on Z33: SMcGarrity: Assumes that if we are doing nothing till litigation is over the cost of required interim reinstatement will be considerably higher.
Note on Z38: Gregor Roberts: DM view of new procurement costs with 7.5% compound interest for 2 years
Note on Z50: Assumed securing sites cost will be £2m per annum for 3 yrs
Note on Z51: TP cost forecast P8: Fports: BP Rd £0.6m; LRd £2.2m; OT £0.5m; Tow Pl £0.1m & RBS £0.4m (contingency range £-,£1m or £2m
Note on Z59: SMcGarrity: Additional 2 yrs prolongation and escalation - say £5m
Note on Z70: SMcGarrity: Additional 2 year lease income - this assumes 17 trams doing nothing for a considerable preiod of time.
Note on Z76: Assumption taken currently that 20% of CWP is recoverable with Infraco Default scenario. Legal view to confirm if this is the case or whether or not the full construction cost would apply. If building incrementally is this pro-rata? Low £236.8m CWP + £100m change * 20% Medium £236.8m CWP * 20% High £236.8m/2 * 20%
Note on AB34: SMcGarrity: Very uncertain - placemarker only.
Note on AB51: 3rd party costs higher in this instance due to blight claims (+£10m)
Note on AB57: SMcGarrity: Wouldnt do the utilities at Baltic street if you're Canx
Note on AB70: SMcGarrity: Assumes 80% recovery on cost

## Profile - F (hidden)
Profile for Termination and Reprocurement
Design and reprocurement
Continuing works/off street
On street to SAS
SAS to Newhaven
[5 empty] | End Litig |  | OFRS to SAS
| to P7 9 Oct 10 | 2011-06-01 | 2011-12-01 | 2012-06-01 | 2012-12-01 | 2013-06-01 | 2013-12-01 | 2014-06-01 | 2014-12-01 | 2015-06-01 | 2015-12-01 | 2016-06-01 | 2016-12-01 | 2017-06-01 | 2017-12-01 | Win litigation | Check
BB+S
Constn Works Price (BB+S) | 65.2 | [14 empty] | 65.2 | 68.1968
Existing Change - Princes St | 9.5 | [14 empty] | 9.5 | 9.5
Existing Change - Other | 11.8 | [14 empty] | 11.8 | 13.0657
Existing Prolongation | [15 empty] | 0 | 0
Further on-street change and disruption | [15 empty] | 0 | 0
Further allowance for risks and delay | [15 empty] | 0 | 0
Entitlement for work done (BB+S) | 86.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.5 | 90.7625
Certified in advance of work done (BB+S) | 31.9 | [14 empty] | 31.9 | 33.2455
Certified to Date (BB+S) | 118.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4 | 124.008
Net Accounting accruals/prepayments | -8.4 | 2011-06-01: 8.4 | 0 | 0
Bond call (BB+S) |  | 2011-06-01: -25 | -25 | #REF!
Settlement Premium | [15 empty] | 0 | #REF!
Infrastructure (BB+S) | 110 | -16.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.4 | 124.008
Vehicles (CAF) | 46.4 | 2011-06-01: 12.1 | 58.5 | 62.5
Design Post Novation (SDS) | 5 | [14 empty] | 5 | 8
Total BSC | 161.4 | -4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156.9 | 196.508
Interim Works & Reinstatement
Interim Works during Reprocure |  | 2011-06-01: 20 | 20 | 9.893
Reinstate/remedials during Reprocure |  | 2011-06-01: 3 | 3 | 2.5
Reinstatement following cancellation | [16 empty] | 0
Total | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 12.393
New Procurement Costs
Infrastructure - to SAS |  | 2012-06-01: 20; 2012-12-01: 50; 2013-06-01: 75; 2013-12-01: 50 | 195 | 144.763
Infrastructure - to FOW |  | 2014-12-01: 10; 2015-06-01: 20; 2015-12-01: 10 | 40 | 35.121
Infrastructure - to NHN |  | 2016-12-01: 5; 2017-06-01: 10; 2017-12-01: 5 | 20 | 45.915
Vehicles - Lease / Sale recoveries |  | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -0.75 | -10.5 | #REF!
Design |  | 2011-06-01: 10; 2011-12-01: 5 | 15 | #REF!
Direct Reprocurement Costs | [15 empty] | 0 | -4.3
Risk allowance on new procurement |  | 2013-12-01: 10; 2015-12-01: 10; 2017-12-01: 5 | 25 | #REF!
Total New Procurement | 0 | 9.25 | 4.25 | 19.25 | 49.25 | 74.25 | 59.25 | -0.75 | 9.25 | 19.25 | 19.25 | -0.75 | 4.25 | 9.25 | 9.25 | 284.5 | 240.709
Total Infrastructure & vehicles | 161.4 | 27.75 | 4.25 | 19.25 | 49.25 | 74.25 | 59.25 | -0.75 | 9.25 | 19.25 | 19.25 | -0.75 | 4.25 | 9.25 | 9.25 | 464.4 | 449.61
Termination Costs | [16 empty] | 0
Securing sites |  | 2011-06-01: 2 | 2 | 2
Our litigation costs |  | 2011-06-01: 7.5; 2011-12-01: 7.5; 2012-06-01: 7.5; 2012-12-01: 7.5 | 30 | #REF!
Third party costs |  | 2011-06-01: 5; 2011-12-01: 5 | 10 | 0
BSC Loss of profits | [15 empty] | 0 | #REF!
BSC Litigation Costs | [15 empty] | 0 | #REF!
Total Termination Costs | 0 | 14.5 | 12.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2
Other Costs
Ph1b Payment to BSC | 3.2 | [14 empty] | 3.2 | 3.2
Design Pre Nov incl Ph1b and Utilities | 32.3 | [14 empty] | 32.3 | 28.7
Utilties and Other Infrastructure | 87.6 | 2011-06-01: 1.1; 2014-06-01: 1.2 | 89.9 | 100.125
Project Costs | 70.2 | 2011-06-01: 2.5 | 72.7 | 74.156
Project Costs - Post Termination |  | 4.0449 | 2.6707 | 1.9171 | 1.9171 | 3.5346 | 3.5346 | 0.52596 | 0.52596 | 1.026 | 1.026 | 0.52596 | 0.52596 | 0.72946 | 0.72946 | 23.2336 | 28.2
Other Costs - Incl Land | 32.5 | 2011-06-01: -0.2 | 32.3 | 36.973
Other Costs | 225.8 | 7.4449 | 2.6707 | 1.9171 | 1.9171 | 3.5346 | 3.5346 | 1.726 | 0.52596 | 1.026 | 1.026 | 0.52596 | 0.52596 | 0.72946 | 0.72946 | 253.6336 | 271.354
Gross Outturn Costs | 387.2 | 49.6949 | 19.4207 | 28.6671 | 58.6671 | 77.7846 | 62.7846 | 0.97596 | 9.776 | 20.276 | 20.276 | -0.22404 | 4.776 | 9.9795 | 9.9795 | 760.0336 | 722.964
Recovery 75% of Costs from BSC |  | 2012-12-01: -88.8 | -88.8 | #REF!
Net Outturn Costs | 387.2 | 49.6949 | 19.4207 | 28.6671 | -30.1329 | 77.7846 | 62.7846 | 0.97596 | 9.776 | 20.276 | 20.276 | -0.22404 | 4.776 | 9.9795 | 9.9795 | 671.2336 | #REF!
Cumulative Funding Req | 387.2 | 436.8949 | 456.3156 | 484.9827 | 454.8498 | 532.6344 | 595.419 | 596.395 | 606.1709 | 626.4469 | 646.7228 | 646.4988 | 651.2747 | 661.2542 | 671.2336
Note on I56: SMcGarrity: Baltic St

## Liability P6 (hidden)
[7 empty] | Milestone Payment Certification |  |  | Milestone Payment Difference
| Edinburgh Tram Network | [8 empty] | Certified v Application
Infraco Contract
[6 empty] | Date : | #REF! |  | Date : | #REF!
Milestone Analysis
[6 empty] | Certification Nr : | #REF! |  | Certification Nr : | #REF!
23 September 2010
[6 empty] | Period End : | #REF! |  | Period End : | #REF!
[5 empty] | CERTIFIED |  |  | DIFFERENCE |  |  |  | ACTUAL EARNED VALUE
[5 empty] | Current Cumulative | Previous Cumulative | Period | Current Application | Current Certified | Difference |  | Milestones | Incomplete Milestones | Preliminaries | Change | Total
Preliminaries
00 Mobilisation and Preliminaries
00A Mobilisation
|  | BBUK |  |  | 22600000 | 22600000 | 0 | #REF! | 22600000 | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Siemens |  |  | 22600000 | 22600000 | 0 | #REF! | 22600000 | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | 00A Preliminaries - BBUK |  |  | 21741298.2356 | 21741298.2356 | 0 | #REF! | 21741298.2356 | #REF! |  | 0 | 0 | 28242666 | 0 | 28242666
|  | 00C Preliminaries - Siemens |  |  | 9348999.5237 | 9348999.5237 | 0 | #REF! | 9348999.5237 | #REF! |  | 0 | 0 | 10841000 | 0 | 10841000
|  | 00D Network Rail Immunisation |  |  | 379421.42 | 379421.42 |  | #REF! | 379421.42 | #REF! |  | 0 | 0 | 379421.42 | 0 | 379421.42
|  | 00E SDS Interface |  |  | 3800000 | 3800000 | 0 | #REF! | 3800000 | #REF! |  | 0 | 0 | 1900000 | 0 | 1900000
|  | 00F Incentivisation |  |  | 0 | 0 | 0 | #REF! | 0 | #REF! |  | 0 | 0 | 0 | 0 | 0
Construction Milestones
01 Newhaven Road to Haymarket
01A Newhaven Road (inc.) to Foot of the Walk (exc.)
|  | BBUK |  |  | 498692.22 | 174346.11 | 324346.11 | #REF! | 498692.22 | #REF! | 1651204 | 498692.22 | 1152511.78 | 0 | 0 | 1651204
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01B Foot of the Walk (inc.) to McDonald Road (exc.)
|  | BBUK |  |  | 89898.6503 | 89898.6503 | 0 | #REF! | 89898.6503 | #REF! | 315849 | 89898.6503 | 225950.3497 | 0 | 0 | 315849
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01C McDonald Road (inc.) to Princess Street West (exc.)
|  | BBUK |  |  | 150908.67 | 150908.67 | 0 | #REF! | 150908.67 | #REF! | 76217 | 150908.67 | -74691.67 | 0 | 0 | 76217
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
01D Princes Street (inc.) to Haymarket (exc.)
|  | BBUK |  |  | 1324475.7871 | 1324475.7871 | 0 | #REF! | 1324475.7871 | #REF! | 2409450 | 2175743.8971 | 233706.1029 | 0 | 0 | 2409450
|  | Siemens |  |  | 851268.11 | 851268.11 | 0 | #REF! | 851268.11 | #REF!
02 Haymarket Corridor
|  | BBUK |  |  | 728410.951 | 728410.951 | 0 | #REF! | 728410.951 | #REF! | 979171 | 728410.951 | 250760.049 | 0 | 0 | 979171
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
05 Roseburn Junction to Gogar
05A Roseburn Junction (exc.) to Balgreen Road (inc.)
|  | BBUK |  |  | 209533.53 | 209533.53 | 0 | #REF! | 209533.53 | #REF! | 635036 | 209533.53 | 425502.47 | 0 | 0 | 635036
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
05B Balgreen Road (exc.) to Edinburgh Park (inc.)
|  | BBUK |  |  | 2782537.1738 | 2782537.1738 | 0 | #REF! | 2782537.1738 | #REF! | 6617732 | 5028467.6038 | 1589264.3962 | 0 | 0 | 6617732
|  | Siemens |  |  | 2245930.43 | 2245930.43 | 0 | #REF! | 2245930.43 | #REF!
05C Edinburgh Park (exc.) to Gogarburn (inc.)
|  | BBUK |  |  | 484331.56 | 484331.56 | 0 | #REF! | 484331.56 | #REF! | 1371637 | 484331.56 | 887305.44 | 0 | 0 | 1371637
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
06 Gogar Depot
|  | BBUK |  |  | 5819249.75 | 5633873.42 | 185376.33 | #REF! | 5819249.75 | #REF! | 7818988 | 5819249.75 | 1999738.25 | 0 | 0 | 7818988
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
07 Gogar to Edinburgh Airport
|  | BBUK |  |  | 1129672.68 | 972310.68 | 157362 | #REF! | 1129672.68 | #REF! | 1660972 | 1129672.68 | 531299.32 | 0 | 0 | 1660972
|  | Siemens |  |  | 0 | 0 | 0 | #REF! | 0 | #REF!
CAF
| 08A Tram Supply Contract |  |  |  | 46005858.3982 | 45675608.6482 | 330249.75 | #REF! | 46005858.3982 | #REF! |  | 46005858.3982 | 0 | 0 | 0 | 46005858.3982
Maintenance
Infraco Maintenance Mobilisation
|  | BBUK |  |  | 13000 | 13000 | 0 | #REF! | 13000 | #REF! |  | 267343.8 | 0 | 0 | 0 | 267343.8
|  | Siemens |  |  | 254343.8 | 254343.8 | 0 | #REF! | 254343.8 | #REF!
Tram Maintenance Mobilisation
CAF
Infraco Spare Parts
Infraco
|  |  | Subtotal |  | 143057830.8897 | 142060496.6997 | 997334.19 | #REF! | 143057830.8897 | #REF! | 23536256 | 62588111.7104 | 7221346.4878 | 41363087.42 | 0 | 111172545.6182
Additional Works
| 01 | SDS Application for payment excl Change identified in (2) |  |  | 5438490 | 5325819 | 112671 | #REF! | 5438490 | #REF! |  | 0 | 0 | 0 | 5438490 | 5438490
| 02 | Change Application | [7 empty] | 0
|  | SDS |  |  | 2265678.5 | 2242285.87 | 23392.63 | #REF! | 2265678.5 | #REF! |  | 0 | 0 | 0 | 2265678.5 | 2265678.5
|  | BBUK |  |  | 19489343.17 | 18174763.57 | 1314579.6 | #REF! | 19489343.17 | #REF! |  | 0 | 0 | 0 | 19489343.17 | 19489343.17
|  | Siemens |  |  | 1768309.32 | 1659309.32 | 109000 | #REF! | 1768309.32 | #REF! |  | 0 | 0 | 0 | 1768309.32 | 1768309.32
|  | CAF |  |  | 328471.26 | 328471.26 | 0 | #REF! | 328471.26 | #REF! |  | 0 | 0 | 0 | 328471.26 | 328471.26
| 02 | Value Engineering Not Achieved | [5 empty] | #REF! | 0 | #REF!
|  | Clause 22/65 Changes |  |  | 114177.34 |  | 114177.34 |  |  |  |  | 0 | 0 | 0 | 114177.34 | 114177.34
|  |  | Total |  | 172462300.4797 | 169791145.7197 | 2671154.76 | #REF! | 172348123.1397 | #REF! | 118423802.3215 | 62588111.7104 | 7221346.4878 | 41363087.42 | 29404469.59 | 140577015.2082 | 86538517.05
Summary Information
Preliminaries
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Maintenance
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | CAF | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Construction Milestones
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tram Supply Agreement
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Change | [16 empty] | 262522
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Value Engineering
|  | BBUK | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design
|  | SDS Application | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | SDS Change | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Totals |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
By Company
|  | BBUK (incl SDS) | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Siemens | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | 125706.49
|  | CAF | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Totals |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45000
95000
17023
121847
750000
5366
20000
-260973.48
6665
34460
22000
83029
34059
18750
12991
9006972
50000
1565
250000
3931
9000
35000
10000
15000
6500
37036.01
16870.93
15000
25000
2000
1500

## Latest AFC Rec
Updated - per Period 11 Consolidated PD Review Report
1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Project Control Budget (PCB) AFC | Approved changes | Current Approved Budget (CAB) AFC | Project to Date P11 | Current AFC forecast P11 | Filter
T01.01 | Project management Staff Costs | 26697669.9218 | 523193.5343 | 27220863.4561 | 29907878.9935 | 35206408.3268 | 405070204.9669 | x
T01.02 | Recruitment Fees | 466202.6166 | -0.02 | 466202.5966 | 448675.02 | 466204.5756 | 5990533.3242 | x
T01.03 | Travel & Subsistence / Conference | 356214.2 | -0.44462 | 356213.7554 | 345622.23 | 366158.98 | 4638138.3969 | x
T01.04 | Central Overheads | 5580828.4493 | 0.38 | 5580828.8293 | 5059496 | 5595424 | 70538419.6974 | x
T01.05 | IT & Software Costs / fitout | 3109074.5062 | 0.27308 | 3109074.7792 | 3141965.17 | 4241492.77 | 46211623.92 | x
T01.06 | Citypoint - rent,rates,s/c | 2171872.6414 | 807239.8241 | 2979112.4655 | 2709127.94 | 3465481.2457 | 40887607.6744 | x
T01.07 | Recovered from SDS | 0 | 0 | 0 | 0 | 0 | 0 | x
T01.08 | Short Term Contractors | 196804 | 0 | 196804 | 196804 | 196804 | 2558452 | x
T01.09 | City Point Overheads | 25270.8462 | 0 | 25270.8462 | 25271.09 | 25271.09 | 328523.1946 | x
T01.10 | Active Risk Manager | 83665 | 0 | 83665 | 83666 | 83666 | 1087654 | x
T01.11 | Archaeological supervisor - Gogar works | 267879 | -82646.11 | 185232.89 | 153992.9103 | 247729.9103 | 2512906.6423 | x
T01.13 | Archaeology - Non Gogar | 0 | 642742.2423 | 642742.2423 | 334183 | 580469 | 7452788.2115 | x
T01.14 | DRP Costs | 0 | 2985327 | 2985327 | 4484172.56 | 4865624.56 | 57191448.04 | x
T01.15 | Tax Planning / Governance Costs (Non DLA) | 0 | 0 | 0 | 21960 | 301816 | 1596920 | x
T01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T01.20 | Period Adjustments | 0 | 0 | 0 | 0 | 0 | 0 | x
T01 | Total tie PM costs | 38955481.1814 | 4875856.6792 | 43831337.8606 | 46912814.9138 | 55642550.4583 | 646065220.0683 | Project Costs
T02.01 | Core Team | 7631160.25 | 0 | 7631160.25 | 2679140 | 7631160.0888 | 79397001.4442 | x
T02.02 | Retention | 0 | 0 | 0 | 0 | 0 | 0 | x
T02.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T02.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T02.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T02 | Total DPOF | 7631160.25 | 0 | 7631160.25 | 2679140 | 7631160.0888 | 79397001.4442 | Project Costs
T03.01 | DLA-SDS | 140728.89 | -105 | 140623.89 | 140623.89 | 140623.89 | 1828005.57 | x
T03.02 | DLA-TSS | 31999.37 | 0 | 31999.37 | 32000.37 | 32000.37 | 416000.81 | x
T03.03 | DLA- Site Investigation | 1116.25 | 0 | 1116.25 | 1116.25 | 1116.25 | 14511.25 | x
T03.04 | DLA-MUDFA | 684194.34 | 55982 | 740176.34 | 834631.81 | 834631.81 | 10528373.65 | x
T03.05 | DLA-Network Rail / Scotrail | 119986.15 | -5427 | 114559.15 | 114559.32 | 114559.32 | 1483843.48 | x
T03.06 | DLA-JRC | 27382.82 | 0 | 27382.82 | 27382.82 | 27382.82 | 355976.66 | x
T03.07 | DLA-Infraco | 1164593.92 | 327052.1 | 1491646.02 | 1525372.28 | 1525372.28 | 20021986.7 | x
T03.08 | DLA-Vehicles & Driver supply contract | 461014.65 | 10214 | 471228.65 | 471228.65 | 471228.65 | 6136186.45 | x
T03.09 | DLA-BAA | 22199.82 | 2013 | 24212.82 | 24212.74 | 24212.74 | 316778.94 | x
T03.10 | DLA-Land & Property (3rd parties) | 25946.24 | 0 | 25946.24 | 25946.24 | 25946.24 | 337301.12 | x
T03.11 | DLA-Ticketing Agreements | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.12 | DLA-DPOF | 85711.01 | -732 | 84979.01 | 96071.26 | 96071.26 | 1203825.38 | x
T03.13 | DLA-Tram Netwk/Roads Interface | 22149.45 | 0 | 22149.45 | 22149.45 | 22149.45 | 287942.85 | x
T03.14 | DLA-EARL interface | 39217.39 | 0 | 39217.39 | 39217.39 | 39217.39 | 509826.07 | x
T03.15 | DLA-Commissioning Svcs Agmt | 6892.48 | 0 | 6892.48 | 6892.48 | 6892.48 | 89602.24 | x
T03.16 | OCIP | 24280.06 | 2806 | 27086.06 | 27086.06 | 27086.06 | 354924.78 | x
T03.17 | Infraco Enabling | 3950.63 | 432 | 4382.63 | 4383 | 4383 | 57409.52 | x
T03.18 | HR Issues | -0.31 | 0 | -0.31 | -0.31 | -0.31 | -4.03 | x
T03.19 | Mass Earthworks | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.01 | DLA - HSQE | -0.5 | 0 | -0.5 | 9022.6 | 9022.6 | 81201.4 | x
T03.19.02 | DLA - Governance | 1136.06 | 0 | 1136.06 | 84054.66 | 171561.16 | 1198568.68 | x
T03.19.03 | DLA - CEC Interface | 0 | 0 | 0 | 17509.05 | 17509.05 | 157581.45 | x
T03.19.04 | DLA - Misc Procurement | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.05 | DLA - DRP | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.19.10 | DLA - Reserve | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.01-19 | DLA | 2862498.72 | 392235.1 | 3254733.82 | 3503460.01 | 3590966.51 | 45379842.97 | Project Costs
T03.20 | D&W-General Advice | 745652.0769 | -27001 | 718651.0769 | 704900.77 | 704900.77 | 9191710.2377 | x
T03.21 | D&W-TRO's | 801982.6001 | -315996 | 485986.6001 | 544373.05 | 544373.05 | 6527307.8504 | x
T03.22 | D&W-Property | 841934 | 303096 | 1145030 | 1163961.83 | 1190867.1633 | 15493399.1367 | x
T03.23 | D&W-Planning Monitoring | 292542 | -85080 | 207462 | 181253 | 181253 | 2376045 | x
T03.24 | D&W-TDWG | 87860 | 0 | 87860 | 85982 | 85982 | 1125278 | x
T03.25 | D&W -Public Realm | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.26 | D&W-Litigation | 260 | 14230 | 14490 | 10490 | 10490 | 166600 | x
T03.27 | D&W-Secondments | 152123 | 0 | 152123 | 152123 | 152123 | 1977599 | x
T03.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T03.20-35 | Subtotal D&W | 2922353.677 | -110751 | 2811602.677 | 2843083.65 | 2869988.9833 | 36857939.2248 | Project Costs
T03 | Total LEGALS | 5784852.397 | 281484.1 | 6066336.497 | 6346543.66 | 6460955.4933 | 82237782.1948 | x
T04.01 | Design Services under SDS | 11665951.25 | 0 | 11665951.25 | 31314931.11 | 31314931.11 | 328498184.99 | x
T04.01.01 | Overall Value Main Works ( Unallocated ) | 5857253 | 2476772.3319 | 8334025.3319 | 0 | 1488578.829 | 43255767.8046 | x
T04.01.02 | Section 1 Newhaven Road to Haymarket | 2628790.1526 | 0 | 2628790.1526 | 0 | 0 | 10515160.6106 | x
T04.01.03 | Section 2 Haymarket Corridor | 243792.9765 | 0 | 243792.9765 | 0 | 0 | 975171.9062 | x
T04.01.04 | Section 3 Haymarket to Granton Sq | 2172265.8672 | 0 | 2172265.8672 | 0 | 0 | 8689063.4687 | x
T04.01.05 | Section 3 1B deduction | -1858755 | 0 | -1858755 | 0 | 0 | -7435020 | x
T04.01.06 | Section 4 Granton Sq to Newhaven Rd | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.07 | Section 5 Roseburn Junction to Gogar | 1453607.1771 | 0 | 1453607.1771 | 0 | 0 | 5814428.7083 | x
T04.01.08 | Section 6 Gogar Depot | 328781.4435 | 0 | 328781.4435 | 0 | 0 | 1315125.774 | x
T04.01.09 | Section 7 Gogar to Edinburgh Airport | 443207.1446 | 0 | 443207.1446 | 0 | 0 | 1772828.5785 | x
T04.01.10 | Section 8 Ingliston West / Newbridge | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.11 | MUDFA / Utilities | 552625.2348 | -8690 | 543935.2348 | 0 | 0 | 2167050.9391 | x
T04.01.12 | Claim | 1925000 | 0 | 1925000 | 0 | 0 | 7700000 | x
T04.01.13 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.01.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.02 | Site Investigation under SDS | 0 | 1415000 | 1415000 | 1415000 | 1415000 | 19810000 | x
T04.03 | 0 | 1415000 | -1415000 | 0 | 0 | 0 | -1415000 | x
T04.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
T04 | Total SDS | 26827519.2463 | 2468082.3319 | 29295601.5782 | 32729931.11 | 34218509.939 | 421662762.78 | SDS
T05.01 | Integrated Transport Model | 2454444.1575 | 38825.24 | 2493269.3975 | 2475682 | 2557967 | 32704465.83 | x
T05.02 | Surveys (MM) | 165588.78 | 0 | 165588.78 | 165589 | 165589 | 2152656.12 | x
T05.03 | Consultancy (Halcrow) | 9916.21 | 0 | 9916.21 | 9916 | 9916 | 128908.84 | x
T05.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T05 | Total JRC | 2629949.1475 | 38825.24 | 2668774.3875 | 2651187 | 2733472 | 34986030.79 | Other Costs/ Inc Land
T06.01 | Technical Services | 9302558.4403 | 927723.35 | 10230281.7903 | 10399109.01 | 11056921.5399 | 138729894.2507 | x
T06.02 | Land agreement/negotiations | 113000 | 0 | 113000 | 113000 | 113000 | 1469000 | x
T06.04 | TSS Second to CEC-Approvals support | 92381 | 0 | 92381 | 92381 | 92381 | 1200953 | x
T06.05 | T&T Costs |  | 81177 | 81177 | 81176.99 | 81176.99 | 1136477.91 | x
T06.01-03 | Subtotal TSS | 9507939.4403 | 1008900.35 | 10516839.7903 | 10685667 | 11343479.5299 | 142536325.1607 | Project Costs
T06.03 | CEC staff costs | 1168277 | 1011312.49 | 2179589.49 | 2182684 | 2378622 | 30353516.45 | x
T06.03a | Subtotal CEC | 1168277 | 1011312.49 | 2179589.49 | 2182684 | 2378622 | 30353516.45 | Project Costs
T06 | Total TSS and CEC | 10676216.4403 | 2020212.84 | 12696429.2803 | 12868351 | 13722101.5299 | 172889841.6107 | x
T07.01 | Consultancies | 20521.46 | 0 | 20521.46 | 20521.46 | 20521.46 | 266778.98 | x
T07.02 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T07.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T07.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T07.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T07 | Total UTILITIES | 20521.46 | 0 | 20521.46 | 20521.46 | 20521.46 | 266778.98 | Other Costs/ Inc Land
T08.01 | Tech. Advisors-Parl.Support | 268642.76 | 0 | 268642.76 | 268642.76 | 268642.76 | 3492355.88 | x
T08.02 | Tech. Advisors-Parl.Support-PM | 29382.99 | 0 | 29382.99 | 29382.99 | 29382.99 | 381978.87 | x
T08.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T08.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T08.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T08 | Total DESIGN SUPPORT | 298025.75 | 0 | 298025.75 | 298025.75 | 298025.75 | 3874334.75 | Other Costs/ Inc Land
T09.01.01 | Network Rail - FDA Work Contract 1 | 437342.71 | -219964 | 217378.71 | 217378.35 | 217378.35 | 2605955.99 | x
T09.01.02 | Network Rail - Basic Implementation Agreement | 7500 | 107018 | 114518 | 114517.85 | 114517.85 | 1595750.65 | x
T09.02 | BAA legal costs | 0 | 0 | 0 | -0.49 | -0.49 | -4.41 | x
T09.03 | Network Rail - Asset Protection Agreement | 0 | 1403303 | 1403303 | 1333582.91 | 1411028.91 | 19405991.19 | x
T19.07.01 | Network Rail - Development Services Agreement | 172682 | 42855 | 215537 | 214954.25 | 215537.25 | 2842506.25 | x
T19.07.02 | Network Rail - Immunisation Implementation | 4152 | 124862.4 | 129014.4 | 0.4 | 129015.4 | 1285998.6 | x
T19.07.03 | Network Rail - Others | 823166.0031 | -813946.5 | 9219.5031 | 9219.17 | 9219.17 | -694095.9577 | x
T09 | Total 3RD PARTY NEGOTIATIONS | 1444842.7131 | 644127.9 | 2088970.6131 | 1889652.44 | 2096696.44 | 27042102.3123 | Other Costs/ Inc Land
T10.01 | D&W (10.01 &11.01) | 25843 | 0 | 25843 | 25843 | 25843 | 335959 | x
T10.02 | Advisors (Colliers / DV) | 201120.75 | 0 | 201120.75 | 176259 | 201119.9231 | 2515118.6154 | x
T10.03 | Technical | 0 | 0 | 0 | 0 | 0 | 0 | x
T10.04 | Advance Purchases 05/06 (Fees) | 60181 | 0 | 60181 | 60181 | 60181 | 782353 | x
T10.05.01 | Advance Purchases (GVD) | 13486953 | -1935210 | 11551743 | 11688397 | 11481392 | 148432310 | x
T10.05.02 | Advance Purchases (gifted / free issue) | 4807286 | 0 | 4807286 | 4807286 | 4807286 | 62494718 | x
T10.05.07 | Misc Land Costs | 0 | 5000 | 5000 | 138251 | 138251 | 1269259 | x
T10.05.03 | BAA Contractor Costs | 0 | 0 | 0 | 604586.12 | 604586.12 | 5441275.08 | x
T10.05.04 | BAA PM costs | 0 | 703764 | 703764 | 197667.25 | 197667.25 | 5297825.25 | x
T10.05.05 | BAA Utilities | 0 | 150000 | 150000 | 150000 | 150000 | 2100000 | x
T10.05.06 | BAA Infraco | 0 | 0 | 0 | 0 | 0 | 0 | x
T10.05.08 | Haymarket station compensation |  | 1049593 | 1049593 | 888204 | 888204 | 13241801 | x
T10.05.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.05.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.01-.05 | Subtotal Land | 18581383.75 | -26853 | 18554530.75 | 18736674.37 | 18554530.2931 | 241910618.9454 | Other Costs/ Inc Land
T10.06.01 | Business Support Primary payment | 1599791 | 59209 | 1659000 | 1651848 | 1651848 | 21561841 | x
T10.06.02 | Business Support Enhanced payment | 350000 | -350000 | 0 | 0 | 0 | -350000 | x
T10.06.03 | Business Support Admin | 50000 | 0 | 50000 | 44698.86 | 44698.86 | 602289.74 | x
T10.06.04 | Sundry costs |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.06 | Subtotal Business Support | 1999791 | -290791 | 1709000 | 1696546.86 | 1696546.86 | 21814130.74 | Other Costs/ Inc Land
T10.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.11 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.12 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T10.07-13 | Subtotal Other | 0 | 0 | 0 | 0 | 0 | 0 | Other Costs/ Inc Land
T10 | Total LAND & PROPERTY | 20581174.75 | -317644 | 20263530.75 | 20433221.23 | 20251077.1531 | 263724749.6854 | x
T11.01 | Legal | 0 | 0 | 0 | 0 | 0 | 0 | x
T11.02 | TRO's - Technnical | 1312.95 | 0 | 1312.95 | 1313 | 1313 | 17068.8 | x
T11.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T11 | Total TROs | 1312.95 | 0 | 1312.95 | 1313 | 1313 | 17068.8 | Other Costs/ Inc Land
T12.01 | Fees / production Items - WS | 851027.8 | -42874 | 808153.8 | 808154.12 | 808154.12 | 10463128.28 | x
T12.02 | Fees / production Items - MH | 658692.9 | -217925 | 440767.9 | 440767.92 | 440767.92 | 5512057.88 | x
T12.03 | Tram branding | 37500 | 560 | 38060 | 38060.39 | 38060.39 | 495343.51 | x
T12.04 | PR Support | 0 | 20381 | 20381 | 20381 | 20381 | 285334 | x
T12.05 | Business development and marketing | 901 | 9645 | 10546 | 10546.25 | 10546.25 | 146745.25 | x
T12.06 | Media monitoring | 31080 | -18020.6923 | 13059.3077 | 13059 | 13059 | 151747.5385 | x
T12.07 | Media training | 19500 | -19500 | 0 | 0 | 0 | -19500 | x
T12.08 | Promotional materials | 80951 | 62574 | 143525 | 143525 | 143525 | 1928399 | x
T12.09 | Websites | 78490 | -52559 | 25931 | 25931 | 25931 | 284544 | x
T12.10 | Events including Edinburgh Fringe | 39000 | -22885 | 16115 | 16115 | 16115 | 186610 | x
T12.11 | Advertising | 91118 | -36348 | 54770 | 54770 | 54770 | 675662 | x
T12.12 | Internal communications | 13585 | -5014 | 8571 | 8571 | 8571 | 106409 | x
T12.23 | Sponsorship | 0 | 17225 | 17225 | 17225 | 17225 | 241150 | x
T12.24 | Communication consultancy services | 0 | 0 | 0 | 0 | 0 | 0 | x
T12.25 | Sundries | 0 | 340 | 340 | 340 | 340 | 4760 | x
T12.26 | Princes Street Costs | 0 | 73637 | 73637 | 123637 | 123637 | 1480918 | x
T12.27 | Public Information | 0 | 189847 | 189847 | 119456 | 187004 | 2362079 | x
T12.28 | Team Costs | 0 | 12903 | 12903 | 5103 | 12903 | 149442 | x
T12.29 | External Resources | 0 | 296504 | 296504 | 264475 | 313375 | 4107295 | x
T12.30 | Festival - dressing the city (CEC funded) |  | 0 | 0 | 0 | 0 | 0 | x
T12.31 | Winter Festival |  | 0 | 0 | 0 | 0 | 0 | x
T12.32 | Preparing for Operations |  | 0 | 0 | 0 | 200000 | 1000000 | x
T12.33 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.34 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.35 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.36 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.38 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.39 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.40 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.01-12,23-40 | Subtotal Communications | 1901845.7 | 268490.3077 | 2170336.0077 | 2110116.68 | 2434364.68 | 29562124.4585 | Project Costs
T12.13 | S/H – Wider Community Consultations | 573176 | -536906 | 36270 | 36265.44 | 36265.44 | -65437.04 | x
T12.14 | S/H – Events | 4649 | 12379 | 17028 | 17028 | 17028 | 233743 | x
T12.15 | S/H – Open for Business | 19745 | 560046 | 579791 | 566249 | 579790.8 | 8043160 | x
T12.16 | S/H – Communications - MUDFA | 26800 | 54987 | 81787 | 81786.86 | 81786.86 | 1118216.74 | x
T12.17 | S/H – Communications - Infraco | 0 | 26634 | 26634 | 26635 | 26635 | 372885 | x
T12.18 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.19 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.20 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.21 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.22 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T12.13-22 | Subtotal Stakeholder | 624370 | 117140 | 741510 | 727964.3 | 741506.1 | 9702567.7 | Project Costs
T12 | Total COMMS / MARKETING | 2526215.7 | 385630.3077 | 2911846.0077 | 2838080.98 | 3175870.78 | 39264692.1585 | x
T13.01 | Non Executive Board | 34352 | 0 | 34352 | 34352 | 34352 | 446576 | x
T13.02 | Search Fees | 5000 | 0 | 5000 | 5000 | 5000 | 65000 | x
T13.03 | Overheads | 2683781 | 0 | 2683781 | 2376352.33 | 2889636.33 | 34688714.97 | x
T13.04 | Ticketing Machines |  | 74100 | 74100 | 72649 | 94701.1429 | 1134601.7143 | x
T13.05 | Tram Display Costs |  | 0 | 0 | 22429.34 | 22429.34 | 201864.06 | x
T13 | Total TEL | 2723133 | 74100 | 2797233 | 2510782.67 | 3046118.8129 | 36536756.7443 | Project Costs
T14.01 | Operator Consultancy | 0 | 0 | 0 | 0 | 0 | 0 | x
T14.02 | Financial Consultancy | 174893 | 0 | 174893 | 174893 | 174893 | 2273609 | x
T14.03 | WP1 modelling (FM) | 17184.03 | 0 | 17184.03 | 17184 | 17184 | 223392.12 | x
T14.04 | WP2 modelling (MVA) | 11148.39 | 0 | 11148.39 | 11148 | 11148 | 144925.56 | x
T14.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T14 | Total SERVICE INTEGRATION | 203225.42 | 0 | 203225.42 | 203225 | 203225 | 2641926.68 | Other Costs/ Inc Land
T15.01 | INFRACO (PUK) | 264920.64 | 0 | 264920.64 | 261852 | 261852 | 3416350.56 | x
T15.02 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T15.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T15.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T15.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T15 | Total PUK | 264920.64 | 0 | 264920.64 | 261852 | 261852 | 3416350.56 | Other Costs/ Inc Land
T16.01 | Financial advisor 05/06 | 285286 | 0 | 285286 | 285286 | 285286 | 3708718 | x
T16.02 | Commercial advice | 0 | 11864 | 11864 | 11864 | 11864 | 166096 | x
T16.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T16.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T16.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T16 | Total FINANCIAL ADVISOR | 285286 | 11864 | 297150 | 297150 | 297150 | 3874814 | Other Costs/ Inc Land
T17.01 | Insurance consultancy | 362118.2444 | 0 | 362118.2444 | 259181.9 | 335874.9 | 4164575.0774 | x
T17.02 | OCIP | 3591000.3407 | 0 | 3591000.3407 | 3079075.91 | 3616949.91 | 44765054.5526 | x
T17.03 | Claims below deductible | 554350 | 0 | 554350 | 1012 | 509211 | 4767503 | x
T17.04 | Insurance Claims professional fees | 0 | 2343 | 2343 | 11931.37 | 11931.37 | 119097.33 | x
T17.05 | Recoverable insurance claims - MUDFA | 0 | 189171 | 189171 | 214141.53 | 214141.53 | 2873128.77 | x
T17.06 | Non-recoverable insurance claims - MUDFA | 0 | 448 | 448 | 510 | 510 | 6830 | x
T17.07 | Recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | x
T17.08 | Non-recoverable insurance claims - Infraco | 0 | 0 | 0 | 0 | 0 | 0 | x
T17.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.11 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.12 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.14 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.15 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.16 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.17 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.18 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.19 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17.20 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T17 | Total INSURANCE | 4507468.585 | 191962 | 4699430.585 | 3565852.71 | 4688618.71 | 56696188.73 | Other Costs/ Inc Land
T01.12 | MUDFA Site Overheads | 13458 |  | 13458 | 27720 | 27720 | 303312 | x
T01.12a | Subtotal MUDFA Overheads | 13458 | 0 | 13458 | 27720 | 27720 | 303312 | x
T18.01.01 | Pre-construction Services | 0 | 3278 | 3278 | 8743 | 8743 | 95077 | x
T18.01.02 | Contract prelims | 2498294 | 3063677 | 5561971 | 7765360 | 7765360 | 95199801 | x
T18.01.03 | Section 1a | 4745026 | -3346547 | 1398479 | 4932189 | 4932189 | 46637070 | x
T18.01.04 | Section 1b | 1432072 | 100560 | 1532632 | 1532632 | 1532632 | 20024776 | x
T18.01.05 | Section 1c | 3098049 | 780495 | 3878544 | 5316033 | 5316033 | 64138968 | x
T18.01.06 | Section 1d | 3132338 | -290451 | 2841887 | 3171887 | 3171887 | 39624080 | x
T18.01.07 | Section 2 | 3318721 | -1209032 | 2109689 | 2209689 | 2209689 | 27116925 | x
T18.01.08 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.09 | Section 3b | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.10 | Section 3c | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.11 | Section 4a | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.12 | Section 4b | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.13 | Section 5a | 158424 | 0 | 158424 | 158424 | 158424 | 2059512 | x
T18.01.14 | Section 5b | 0 | 601934 | 601934 | 601934 | 601934 | 8427076 | x
T18.01.15 | Section 5c | 0 | 20324 | 20324 | 0 | 0 | 101620 | x
T18.01.16 | Section 6 | 285046 | 1730466 | 2015512 | 2015512 | 2015512 | 27932122 | x
T18.01.17 | Section 7 | 4767438 | -1800647 | 2966791 | 2966791 | 2966791 | 36767636 | x
T18.01.18 | Unallocated to section | 11417922.0699 | 18339423 | 29757345.0699 | 22303952 | 22303952 | 338104371.2794 | x
T18.01.19 | Variations | 1937162 | 2465716 | 4402878 | 3740542 | 3740542 | 53742106 | x
T18.01.20 | Reserve | 0 | 0 | 0 | 0 | 0 | 0 | x
T18.01.21 | Claim(s) | 0 | 0 | 0 | 525000 | 525000 | 4725000 | x
T18.01.22 | Transfer to / from Infraco | 125000 | -125000 | 0 | 0 | 0 | -125000 | x
T18.01 | Subtotal MUDFA | 36915492.0699 | 20334196 | 57249688.0699 | 57248688 | 57248688 | 764571140.2795 | x
T18.02.18 | Unallocated to section | 11627213.77 | -5923589 | 5703624.77 | 10230870 | 13795514 | 126791960.08 | x
T18.02.19 | MUDFA related Non SUC costs | 0 | 0 | 0 | 2758194 | 2791194 | 24988746 | x
T18.02.22 | Transfer to infraco |  | -575000 | -575000 | -3413357 | -8113034 | -57093598 | x
T18.02 | Subtotal utilities | 11627213.77 | -6498589 | 5128624.77 | 9575707 | 8473674 | 94687108.08 | x
T18 | Total MUDFA / Utilities | 48556163.8399 | 13835607 | 62391770.8399 | 66852115 | 65750082 | 859561560.3594 | Utilities/ Other Infrastructure
T19.01.01 | Prelims | 53329721.6799 | 0.099088 | 53329721.779 | 80090298.1277 | 98107466.5808 | 1024217412.6302 | x
T19.01.02 | Infraco early mobilisation | 8537744.63 | -0.37 | 8537744.26 | 0.00013 | 0.00041 | 34150976.6726 | x
T19.01.03 | Advanced purchases | 18000000 | 0 | 18000000 | 0.00013 | 0.00041 | 72000000.0026 | x
T19.01.04 | 0 | 27287 | 0 | 27287 | 0.0001 | 0.0001 | 109148.0009 | x
T19.01.05 | Section 1a | 15692627.7819 | 0 | 15692627.7819 | 1545538.4424 | 15431638.077 | 146110855.2824 | x
T19.01.06 | Section 1b | 6707491.4436 | 0 | 6707491.4436 | 107878.3804 | 6707484.8037 | 60798903.3145 | x
T19.01.07 | Section 1c | 9815693.0039 | 0 | 9815693.0039 | 150908.67 | 9815691.2681 | 88944863.0359 | x
T19.01.08 | Section 1d | 6112236.1346 | 0 | 6112236.1346 | 2207522.6153 | 6112234.9182 | 63840209.5904 | x
T19.01.09 | Section 2 | 5501667.2031 | 0 | 5501667.2031 | 728411.216 | 5501667.2008 | 52428649.6802 | x
T19.01.10 | Section 3a | 0 | 0 | 0 | 0 | 0 | 0 | x
T19.01.11 | Section 3b | 0 | 0 | 0 | 1e-05 | 1e-05 | 9e-05 | x
T19.01.12 | Section 3c | 0 | 0 | 0 | 1e-05 | 1e-05 | 9e-05 | x
T19.01.13 | Section 4a | 0 | 0 | 0 | 1e-05 | 1e-05 | 9e-05 | x
T19.01.14 | Section 4b | 0 | 0 | 0 | 1e-05 | 1e-05 | 9e-05 | x
T19.01.15 | Section 5a | 19029806.3921 | 0 | 19029806.3921 | 257870.1216 | 19029806.8717 | 172299740.4133 | x
T19.01.16 | Section 5b | 20041708.9132 | 0 | 20041708.9132 | 5555113.0272 | 20041712.2032 | 202595848.7773 | x
T19.01.17 | Section 5c | 11057009.8717 | 0 | 11057009.8717 | 1743733.1102 | 11057008.8018 | 106488015.9364 | x
T19.01.18 | Section 6 | 12967064.682 | 0 | 12967064.682 | 6809846.3717 | 12967065.1043 | 143942969.7362 | x
T19.01.19 | Section 7 | 11129563.9561 | 0 | 11129563.9561 | 1289905.3505 | 11129584.9505 | 105325801.9786 | x
T19.01.20 | Unallocated to section | 18240000 | 0 | 18240000 | 0 | 0 | 72960000 | x
T19.01.21 | NR Immunisation | 3000000.231 | 0 | 3000000.231 | 735918.1026 | 2999995.1026 | 29943648.8471 | x
T19.01.22 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.23 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.24 | Report adjustment |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.05-24 | Subtotal Construction | 219189622.923 | -0.27091 | 219189622.6521 | 101222943.5359 | 218901355.8835 | 2376157043.8988 | BB+S
T19.01.25 | Testing and commissioning |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.26 | Maintenance mobilisation and spare parts | 2795381 | 0 | 2795381 | 2349809 | 2795382 | 34557670 | Other Costs/ Inc Land
T19.01.35 | Variations - Prelims |  | 3738732 | 3738732 | 214732 | 3738732 | 38246248 | BB+S
T19.01.36 | Variations - Section 1a |  | 46286 | 46286 | 243200.51 | 443660.24 | 3422533.24 | BB+S
T19.01.37 | Variations - Section 1b |  | 43015.61 | 43015.61 | 323203 | 463203 | 3823905.05 | BB+S
T19.01.38 | Variations - Section 1c |  | 23811.58 | 23811.58 | 464938 | 996163 | 6959624.9 | BB+S
T19.01.39 | Variations - Section 1d |  | 2111004 | 2111004 | 10064326 | 10272162 | 102173134 | BB+S
T19.01.40 | Variations - Section 2 |  | 413404.76 | 413404.76 | 371874 | 791213 | 7510584.8 | BB+S
T19.01.41 | Variations - Section 3a |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.42 | Variations - Section 3b |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.43 | Variations - Section 3c |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.44 | Variations - Section 4a |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.45 | Variations - Section 4b |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.46 | Variations - Section 5a |  | 2802447.11 | 2802447.11 | 1455602 | 6243662 | 51052953.55 | BB+S
T19.01.47 | Variations - Section 5b |  | 2610645.99 | 2610645.99 | 1956846 | 5680432 | 49282773.95 | BB+S
T19.01.48 | Variations - Section 5c |  | 2701710.08 | 2701710.08 | 1924583 | 3487521.76 | 38644491.2 | BB+S
T19.01.49 | Variations - Section 6 |  | 2071424.19 | 2071424.19 | 2623102 | 3319331 | 37446183.95 | BB+S
T19.01.50 | Variations - Section 7 |  | 3140028.67 | 3140028.67 | 4145894.55 | 6458422.36 | 64575833.35 | BB+S
T19.01.27 | Variations - Unallocated to section |  | 1881927 | 1881927 | 2855033 | 13159972 | 86629627 | BB+S
T19.01.51 | Variations - NR Immunisation |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.52 | Variations - Princes Street |  | 0 | 0 | 346687.82 | 346687.82 | 3120190.38 | Utilities/ Other Infrastructure
T19.01.53 | Variations - Line 1b Costs |  | 3200000 | 3200000 | 3200000 | 3200000 | 44800000 | Phase 1b payment to BSC
T19.01.27, 35-54 | Subtotal Variations / Changes | 2795381 | 24784436.99 | 27579817.99 | 32539830.88 | 61396544.18 | 572245753.37 | x
T19.01.28 | Infraco contingency | 16395328 | -16248650 | 146678 | 370025.5417 | 413999.5417 | -12111838.1249 | Utilities/ Other Infrastructure
T19.01.91 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.92 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.93 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.94 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.95 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.96 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.54 | Network Rail Compliant Ballast |  |  | 0 | 0 | 0 | 0 | BB+S
T19.01.55 | Allowance for demolition of existing Leith Walk substation (if required) |  | 55659 | 55659 | 50000 | 200000 | 1478295 | BB+S
T19.01.56 | Accommodation Works |  | 781242 | 781242 | 612477 | 1000000 | 11356118 | BB+S
T19.01.57 | PICOPS / COSS / Possession Protection Staff support when undertaking works adjacent or over the railway |  | 655312 | 655312 | 280000 | 450000 | 6646560 | BB+S
T19.01.58 | Additional Crew Relief Facilities at Haymarket |  | 148004 | 148004 | 15000 | 140401 | 1502025 | BB+S
T19.01.59 | RBS requirement for enhancement of Gogarburn Tramstop |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.60 | Pumped surface water outfall at A8 underpass (by depot) |  | 100006 | 100006 | 100000 | 100000 | 1400030 | BB+S
T19.01.61 | Relocation of Ancient Monuments |  | -0.95 | -0.95 | 0 | 0 | -4.75 | BB+S
T19.01.62 | Extra over for revised alignment to Picardy Pl, York Pl and London Rd junctions (see also next item) |  | 2855646 | 2855646 | 0 | 2950000 | 29028230 | BB+S
T19.01.63 | Extra over for major utility diversions Picardy Pl, York Pl and London Rd junctions |  | 2999999 | 2999999 | 0 | 1000000 | 19999995 | BB+S
T19.01.64 | Extra over for shell grip at junctions |  | 319344 | 319344 | 156259 | 800000 | 6221756 | BB+S
T19.01.65 | Allowance for SP connections to new street lights and new traffic signals |  | 115289 | 115289 | 50000 | 115287 | 1352880 | BB+S
T19.01.66 | UTC associated with the delivery of the alignment |  | 2400000 | 2400000 | 1050000 | 4213950 | 37269750 | BB+S
T19.01.67 | Various FP requirements |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.68 | FP requirements at Ocean Terminal amendments |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.69 | Allowance for minor utility diversions |  | 487586 | 487586 | 370258 | 750000 | 7668962 | BB+S
T19.01.70 | Archaeological Officer – impact on productivity |  | 405753 | 405753 | 0 | 405755 | 4057540 | BB+S
T19.01.71 | UTC associated with the wider area impacts |  | 1973408 | 1973408 | 504000 | 1991300 | 21839540 | BB+S
T19.01.72 | FP requirements for design and construction of by-pass road to adoptable standard |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.73 | FP requirements for Lindsay Rd amendments |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.74 | NR compliant ballast |  | 300004 | 300004 | 0 | 300000 | 3000020 | BB+S
T19.01.75 | SP connections to the depot and IPR |  | 1060996 | 1060996 | 873725 | 1365045 | 15625105 | BB+S
T19.01.76 | SP connections to Phase 1a sub-stations |  | 399993 | 399993 | 400000 | 400000 | 5599965 | BB+S
T19.01.77 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.78 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.79 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.80 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.81 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.82 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.83 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.84 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.85 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.86 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.87 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.88 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.89 | 0 |  | 0 | 0 | 0 | 0 | 0 | BB+S
T19.01.90 | Prov sum balancing code |  | -98052 | -98052 | 0 | 0 | -490260 | BB+S
T19.01.55-90 | Subtotal Provisional sums | 16395328 | -1288461.95 | 15106866.05 | 4831744.5417 | 16595737.5417 | 161444668.1251 | x
T19.01.29 | Contingency (VE) | 1199999.5676 | 0 | 1199999.5676 | -0.46154 | 1199999.5385 | 10799994.1164 | Utilities/ Other Infrastructure
T19.01.30 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | Utilities/ Other Infrastructure
T19.01.31 | 0 | 1000000 | -1000000 | 0 | 0 | 0 | -1000000 | Utilities/ Other Infrastructure
T19.01.32 | Provisional sum saving | -350000 | 0 | -350000 | 0 | 0 | -1400000 | Utilities/ Other Infrastructure
T19.01.33 | Tapered poles | 176381 | 0 | 176381 | 0 | 176381 | 1587429 | Utilities/ Other Infrastructure
T19.01.34 | Power for comissioning | 1030000 | 0 | 1030000 | 57222.2222 | 1030000.4444 | 9498891.1111 | Utilities/ Other Infrastructure
T19.01.97 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.98 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.99 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.100 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.101 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.102 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.103 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.104 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.105 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.106 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.107 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.108 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.109 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.110 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.111 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.112 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.113 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.114 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.115 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.116 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.117 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.118 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.119 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.120 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.121 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.122 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.123 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.124 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01.125 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.01 | Subtotal Infraco main works | 241436712.4906 | 22495974.7691 | 263932687.2597 | 138651740.7183 | 299300018.5881 | 3129333779.6215 | x
T19.04.01 | Advanced purchases |  | -0.00033569 | -0.00033569 | -14359219.7174 | 0.31703 | -57436877.2862 | x
T19.04.02 | ??????????????? |  | 0 | 0 | 0 | 0 | 0 | x
T19.04.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.04.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.04.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.04 | Subtotal Funding adjustment | 0 | -0.00033569 | -0.00033569 | -14359219.7174 | 0.31703 | -57436877.2862 | Advanced Payments
T19.02.01 | SRU Murrayfield pitches | 0 | 0 | 0 | 0 | 0 | 0 | x
T19.02.02 | Relocate historic monuments | 42000 | -42000 | 0 | 0 | 0 | -42000 | x
T19.02.03 | Environ. impacts - badgers | 32000 | -2088 | 29912 | 26576.05 | 26576.05 | 356744.45 | x
T19.02.04 | Invasive species | 299917 | -30000 | 269917 | 253500 | 268277 | 3405053 | x
T19.02.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.11 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.12 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.14 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02.15 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.02 | Subtotal advance works | 373917 | -74088 | 299829 | 280076.05 | 294853.05 | 3719797.45 | Utilities/ Other Infrastructure
T19.03.01 | Unallocated | 134574 | -609 | 133965 | 134574 | 134574 | 1746417 | x
T19.03.02 | Set up / mobilisation | 179741 | 0 | 179741 | 179741 | 179741 | 2336633 | x
T19.03.03 | Phase 1 (150,000m3) | 2914685 | 0 | 2914685 | 2914685 | 2914685 | 37890905 | x
T19.03.04 | Phase 2 (100,000m3) | 2209987 | 0 | 2209987 | 2209378 | 2209378 | 28724350 | x
T19.03.05 | Phase 3 (94,093m3) |  | 0 | 0 | 0 | 0 | 0 | x
T19.03.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.03.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.03.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.03.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.03.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.03 | Subtotal depot advance works | 5438987 | -609 | 5438378 | 5438378 | 5438378 | 70698305 | Utilities/ Other Infrastructure
T19.06.01 | VE - Optimise the work site lengths wherever practical to ensure efficient construction outputs |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.02 | VE - Accept more disruption over shorter period to maximise efficiency of construction operations - |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.03 | VE - Option to lease UPS provision from Supplier rather than purchase |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.04 | VE - PM Integration including shared resources and co-location. |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.05 | VE - Further project management integration over 3 years |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.06 | VE - SDS design scope economy, variation and reduction |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.07 | VE - Edinburgh Park Bridge - 7 span to 2 , utilise steel beams in lieu of concrete Edinburgh Park Viaduct |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.08 | VE - Carricknowe Bridge Parapet - down grade from P6 / P5 to N2 (reduced cost of parapet plus knock on effect on deck design/cost) |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.09 | VE - A8 Underpass various initiatives |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.10 | VE - Roseburn Street viaduct various initiatives |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.11 | VE - Water of Leith various intiatives |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.12 | VE - Eight maintenance walkway structures - delete or reduce |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.13 | VE - Class 7 material conversion |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.14 | VE - Value engineer finishes on EPV and other structures |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.15 | VE - Tramstops, standard finishes to circa 20-30% of stops |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.16 | VE - Delete depot pumping station/storm tanks by utilising existing gravity system. |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.17 | VE - Depot - Build part now with provision to expand in the future/reduce size of car park facilities |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.18 | VE - Depot - delete split vehicle accommodation system - requirement dependant on tram vehicle selection |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.19 | VE - Depot - Track Maintenance Equipment - rationalise scope requirement and consider renting. |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.20 | VE - Depot - deletion of one pavement (inner) . |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.21 | VE - Depot - delete requirement for concrete apron to security fence |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.22 | VE - Consolidated VE items 7, 10, 11, 19 which results from changes to initial Depot design driven by proximity to BAA runway and EARL decision. |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.23 | VE - Delete standby generator and substitute with hardstanding and power connection for portable generator. |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.24 | VE - Material recovery and reprocessing (Infraco); 2 options - reconstituted planings & Type 1R |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.25 | VE - Reduce Kerb and associated re-instatement of pavement |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.26 | VE - Reduce drainage run from guideway |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.27 | VE - UTC associated with wider area impacts |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.28 | VE - Picardy place level flexing - MUDFA savings |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.29 | VE - Picardy place level flexing - construction savings |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.30 | VE - Noise attenuation |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.31 | VE - Reduce ballast thickness |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.32 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.33 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.34 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.35 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.36 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.38 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.39 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.40 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.41 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.42 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.43 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.44 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.45 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.46 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.47 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.48 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.49 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.50 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.51 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.52 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.53 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.54 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.55 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.56 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.57 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.58 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.59 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.60 | 0 |  | 0 | 0 | 0 | 4790000 | 23950000 | x
T19.06.01-60 | Subtotal VE - Infraco | 0 | 0 | 0 | 0 | 4790000 | 23950000 | VE not achieved
T19.06.61 | VE - Marerial recovery / reprocessing - MUDFA | -120000 | 0 | -120000 | 0 | -120000 | -1080000 | x
T19.06.62 | VE - Reduction in extent of road reinstatement | -116000 | 0 | -116000 | 0 | -116000 | -1044000 | x
T19.06.63 | VE - Deferred Leasing | -2961000 | 0 | -2961000 | 0 | -2961000 | -26649000 | x
T19.06.64 | VE - Network Reinforcement | -1363000 | 0 | -1363000 | -1363000 | -1363000 | -17719000 | x
T19.06.65 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.66 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.67 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.68 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.69 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.70 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.71 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.72 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.73 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.74 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.75 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.76 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.77 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.78 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.79 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.80 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.81 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.82 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.83 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.84 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.85 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.86 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.87 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.88 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.89 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.90 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.91 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.92 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.93 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.94 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.95 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.96 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.97 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.98 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.99 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.100 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.06.61-100 | Subtotal VE - Non-Infraco | -4560000 | 0 | -4560000 | -1363000 | -4560000 | -46492000 | Utilities/ Other Infrastructure
T19.06 | Subtotal VE | -4560000 | 0 | -4560000 | -1363000 | 230000 | -22542000 | x
T19.07.04 | Power - Network reinforcement | 1579674 | 0 | 1579674 | 1579674 | 1579674 | 20535762 | x
T19.07.05 | Ticket machines | 750000 | 0 | 750000 | 140625 | 750000 | 7312500 | x
T19.07.06 | IPR2 contingency | 300000 | 0 | 300000 | 300000 | 300000 | 3900000 | x
T19.07.07 | Traffic signal and UTC | 0 | 0 | 0 | 0 | 0 | 0 | x
T19.07.08 | Murrayfield modifications | 940010 | 223014 | 1163024 | 1174843 | 1185843 | 15503697 | x
T19.07.16 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.10 | Office land rental |  | 209601.37 | 209601.37 | 189437.88 | 313499.88 | 3373257.77 | x
T19.07.11 | Leith goods yard |  | 56000.08 | 56000.08 | 79541.0223 | 79541.0223 | 995869.6003 | x
T19.07.12 | Traffic management design |  | 400000 | 400000 | 78125 | 400000 | 4312500 | x
T19.07.17 | Burnside Road - Construction Costs |  | 1611394 | 1611394 | 1564042.99 | 1564042.99 | 22133356.91 | x
T19.07.18 | Burnside Road - BAA Costs |  | 349142 | 349142 | 414643.46 | 414643.46 | 5477501.14 | x
T19.07.19 | Burnside Road - Consultancy Costs |  | 215000 | 215000 | 200097.76 | 200097.76 | 2875879.84 | x
T19.07.20 | Burnside Road - Other Costs |  | 330000 | 330000 | 3802.08 | 246813.08 | 2899273.72 | x
T19.07.21 | BAA MUDFA - Construction Costs |  | 445081 | 445081 | 439643.44 | 439643.44 | 6182195.96 | x
T19.07.22 | BAA MUDFA - BAA Costs |  | 119119 | 119119 | 144119.07 | 144119.07 | 1892666.63 | x
T19.07.23 | BAA MUDFA - Consultancy Costs |  | 155000 | 155000 | 116793.71 | 116793.71 | 1826143.39 | x
T19.07.24 | BAA MUDFA - Other Costs |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.25 | 0 |  | 0 | 0 | 1810345 | 0 | 7241380 | x
T19.01-08, 10-12,17-20 | Subtotal non Infraco works | 3569684 | 4113351.45 | 7683035.45 | 8235733.4123 | 7734711.4123 | 106461983.9603 | Utilities/ Other Infrastructure
T19.07.26 | SW Global Resourcing |  | 0 | 0 | 442409 | 792000 | 5729636 | x
T19.07.27 | Stray Current Monitoring |  | 110800 | 110800 | 136223 | 156223 | 1880007 | x
T19.07.28 | Manhole at Balbirnie Place (Frontline cost) |  | 45000 | 45000 | 219000 | 219000 | 2196000 | x
T19.07.29 | SGN Gas main haymarket |  | 38372 | 38372 | 47687 | 47687 | 621043 | x
T19.07.30 | Crash Gate 10 |  | 0 | 0 | 175000 | 175000 | 1575000 | x
T19.07.31 | Constitution Street – Mock-up |  | 0 | 0 | 46037.4033 | 46037.4033 | 414336.63 | x
T19.07.32 | SGN Gas diversion |  | 302000 | 302000 | 552000 | 592000 | 6678000 | x
T19.07.33 | MUDFA scoped side entry manholes |  | 616043 | 616043 | 523209 | 616043 | 8253266 | x
T19.07.34 | Power network Reinforcement |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.35 | Section 1a Utilities |  | 3099374 | 3099374 | 3399337.0585 | 3399337.0585 | 46090903.5266 | x
T19.07.36 | Clancy Docwra Utilities Works |  | 1451657 | 1451657 | 5484051 | 5484051 | 56614744 | x
T19.07.37 | Section 5C Edinburgh Park Clancy |  | 215306 | 215306 | 256957 | 256957 | 3389143 | x
T19.07.38 | Mass Barier Costs |  | 200000 | 200000 | 395000 | 401000 | 4585000 | x
T19.07.39 | Baltic Street |  | 12739 | 12739 | 0 | 1200000 | 6063695 | x
T19.07.40 | South Gyle - Sewer Diversion |  | 852274 | 852274 | 852274 | 852274 | 11931836 | x
T19.07.41 | Visirail / Rubber Kerbs |  | 773600 | 773600 | 773600 | 773600 | 10830400 | x
T19.07.42 | SUC Costs - from MUDFA |  | 782500 | 782500 | 650000 | 650000 | 9762500 | x
T19.07.43 | SUC Betterment - from MUDFA |  | -458309 | -458309 | 0 | -380400 | -4193545 | x
T19.07.44 | Grontmij design novation section 7 BAA |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.45 | Trial Holes S. Gyle |  | 0 | 0 | 70000 | 70000 | 630000 | x
T19.07.46 | Bus Tracker Work |  | 0 | 0 | 45000 | 45000 | 405000 | x
T19.07.47 | POL HA Temp Retention Works |  | 100000 | 100000 | 100000 | 100000 | 1400000 | x
T19.07.48 | 0 |  | 160218 | 160218 | 0 | 0 | 801090 | x
T19.07.26-48 | Subtotal non Infraco changes | 0 | 8301574 | 8301574 | 14167784.4618 | 15495809.4618 | 175658055.1566 | Utilities/ Other Infrastructure
T19.07.09 | Fastlink alternative |  | 491105 | 491105 | 549000 | 549000 | 7396525 | x
T19.07.13 | Ancient monuments |  | 95700 | 95700 | 174500 | 174500 | 2049000 | x
T19.07.14 | TMi cycle integration study |  | 17700 | 17700 | 19657 | 19657 | 265413 | x
T19.07.15 | Siemens out of hours monitoring |  | 100000 | 100000 | 79992 | 100000 | 1319968 | x
T19.07.49 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.50 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.51 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.52 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.53 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.54 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.55 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.56 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.57 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.58 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.59 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.60 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.61 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.62 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.63 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.64 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.65 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.66 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.67 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T19.07.09,13-15,49-67 | Subtotal non Infraco Provisional Sums | 0 | 704505 | 704505 | 823149 | 843157 | 11030906 | Utilities/ Other Infrastructure
T19.07 | Subtotal Non Infraco works | 3569684 | 13119430.45 | 16689114.45 | 23226666.8741 | 24073677.8741 | 293150945.1168 | x
T19 | Total Infraco | 246259300.4906 | 35540708.2188 | 281800008.7093 | 151874641.925 | 329336927.8292 | 3416923949.9021 | x
T20.01.01 | Prelims | 0 | 6215 | 6215 | 6215 | 6215 | 87010 | x
T20.01.02 | Tramco early mobilisation | 0 | 0 | 0 | 0 | 0 | 0 | x
T20.01.03 | Approval of preliminary design | 1102616.6402 | -1784 | 1100832.6402 | 1100833 | 1100833 | 14309043.5608 | x
T20.01.04 | Delivery of mock up | 0 | 0 | 0 | 0 | 0 | 0 | x
T20.01.05 | Approval of final design / mock up | 1653924.9603 | -2676 | 1651248.9603 | 1651249 | 1651249 | 21463560.8412 | x
T20.01.06 | Approvals and consents | 0 | 0 | 0 | 0 | 0 | 0 | x
T20.01.07 | Commencenent of tram works | 9703026.4338 | -15700 | 9687326.4338 | 9687326 | 9687326 | 125919539.7352 | x
T20.01.08 | Completion 1st set bodyshells | 3307849.9206 | -5353 | 3302496.9206 | 3302497 | 3302497 | 42927107.6824 | x
T20.01.09 | Completion 1st set bogies | 3307849.9206 | -5353 | 3302496.9206 | 3302497 | 3302497 | 42927107.6824 | x
T20.01.10 | Completion 1st tram assembly | 3307849.9206 | -5353 | 3302496.9206 | 3302497 | 3302497 | 42927107.6824 | x
T20.01.11 | Completion factory based type testing | 3859158.2407 | -6244 | 3852914.2407 | 3852914 | 3852914 | 50081638.9629 | x
T20.01.12 | Delivery of preliminary tram maintenance manuals | 3307849.9206 | -5353 | 3302496.9206 | 3302497 | 3302497 | 42927107.6824 | x
T20.01.13 | Delivery of spares | 1102616.6402 | -1784 | 1100832.6402 | 1100832.5 | 1100832.5 | 14309039.0608 | x
T20.01.14 | Delivery of final documentation | 1102616.6402 | -1784 | 1100832.6402 | 0 | 1100833 | 9905711.5608 | x
T20.01.15 | Delivery of special tools | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.16 | Completion of driver training | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.17 | Completion of maintainer training | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.18 | Completion of integrated system testing | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.19 | Commencement of shadow running | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.20 | Opening for passenger service | 551308.3201 | -892 | 550416.3201 | 0 | 550416 | 4952853.2804 | x
T20.01.21 | Supply chain mobilisation | 11026166.402 | 55443 | 11081609.402 | 11075131 | 11081609 | 144090449.6082 | x
T20.01.22 | Adjustment | 0 | 0 | 0 | 0 | 0 | 0 | x
T20.01.23 | Delivery of trams | 4520728.2248 | -4817 | 4515911.2248 | 4074149.76 | 4515910.76 | 56934980.7393 | x
T20.01.24 | Testing and commissioning | 4520728.2248 | 0 | 4520728.2248 | 0 | 4520729 | 40686557.8993 | x
T20.01.25 | Advance maintenance mobilisation | 2274883.9414 | -316725 | 1958158.9414 | 846600 | 1958159 | 20693105.7657 | x
T20.01.26 | Depot equipment | 739709.1058 | 317775 | 1057484.1058 | 465477 | 1057484 | 11697039.4232 | x
T20.01.27 | Variations / changes |  | 337506.86 | 337506.86 | 378333 | 378333 | 5092531.3 | x
T20.01.28 | Contingency |  | 0 | 0 | 8995 | 8995 | 80955 | x
T20.01.29 | Claims |  | 0 | 0 | 0 | 0 | 0 | x
T20.01 | Subtotal Tramco main works | 58145425.0574 | 338661.86 | 58484086.9174 | 47458043.26 | 58533906.26 | 716776713.8696 | CAF
T20.02.01 | Funding Adjustment |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.02 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T20.02 | Subtotal Funding adjustment | 0 | 0 | 0 | 0 | 0 | 0 | x
T20 | Total Tramco | 58145425.0574 | 338661.86 | 58484086.9174 | 47458043.26 | 58533906.26 | 716776713.8696 | x
T44.01 | Specified risk | 30336196 | -37170088.89 | -6833892.89 | 0 | 0 | -64505660.45 | x
T44.02 | Contingency |  | 9793610.59 | 9793610.59 | 0 | 0 | 48968052.95 | x
T44.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.11 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.12 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.14 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.15 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.16 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.17 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.18 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.19 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44.20 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T44 | Total Risk | 30336196 | -27376478.3 | 2959717.7 | 0 | 0 | -15537607.5 | Risk Adjustments
T99.01 | Miscellaneous | 265615.74 | -30000.03 | 235615.71 | 168727.64 | 232616.64 | 2750456.57 | x
T99.02 | Previous years | 3093000 | 0 | 3093000 | 3093000 | 3093000 | 40209000 | x
T99.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.04 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.05 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.07 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.08 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.09 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99.10 | 0 |  | 0 | 0 | 0 | 0 | 0 | x
T99 | Total Miscellaneous | 3358615.74 | -30000.03 | 3328615.71 | 3261727.64 | 3325616.64 | 42959456.57 | Other Costs/ Inc Land
T999 | Total | 512017006.7585 | 32983000.1475 | 545000006.906 | 405954172.7487 | 611695751.3446 | 6895278475.4895 | Sub-total
| All BB+S AFC's and scope captured within Total Inf & Vehicles |  |  |  | 132327996.5959 | 290137568.2435 |  | BB+S
| CAF costs included in Vehicles elements |  |  |  | 47458043.26 | 58533906.26 |  | CAF
| To confirm that £28.7m+£8m post+£2m risk incl. 1b (£3m) |  |  |  | 32729931.11 | 34218509.939 |  | SDS
| Ok - phase 1b as noted |  |  |  | 3200000 | 3200000 |  | Phase 1b payment to BSC
| Add tax Write-off £2961k, add £3m (const contingency) |  |  |  | 95208171.0465 | 94164059.2687 | 100125059.2687 | Utilities/ Other Infrastructure
| Total Project costs (see Project Costs Note sheet) |  |  |  | 74155713.2238 | 89678757.1633 | 97389354.1445 | Project Costs
| included in latest AFC |  |  |  | 35233537.23 | 36972950.1531 |  | Other Costs/ Inc Land
[5 empty] | -14359219.7174 | 0.31703 |  | Advanced Payments
[5 empty] | 0 | 0 |  | Risk Adjustments
| All BB+S AFC's and scope captured within |  |  |  | 0 | 4790000 |  | VE not achieved
[5 empty] | 0 | 0 |  | Risk Adjustments
[5 empty] | 405954172.7487 | 611695751.3446 |  | Sub-total
[5 empty] | 0 | 0

## Util & Other Infa (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Utilities and other Infrastructure |  |  |  |  | Period 7 1011 Consolidation | [5 empty] | Pitchfork 3C Based on P12 0910 AFC
[5 empty] | PCB | Approved changes | CAB | P7 AFC | P9 AFC |  | Included in Pitchfork 3c | P12 AFC Excluded | Other Changes |  | Why exclude reported P12 AFC?
T18 | Total MUDFA / Utilities |  |  |  | 48556163.8399 | 5554917 | 54111080.8399 | 58190955 | 62405033 |  | 59320000 |  | -1129045
Risk - conflicts, utiliites, work to complete | [8 empty] | 5000000
T19.01.26 | Maintenance mobilisation and spare parts |  |  |  | 2795381 | 0 | 2795381 | 2795382 | 2349809 |  | 2795000 | [8 empty] | Utilities/ Other Infrastructure
T19.01.34 | Power for comissioning |  |  |  | 1030000 | 0 | 1030000 | 1030000.4444 | 57222.2222 |  | 1030000 | [8 empty] | Utilities/ Other Infrastructure
T19.02.02 | Relocate historic monuments |  |  |  | 42000 | -42000 | 0 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.02.03 | Environ. impacts - badgers |  |  |  | 32000 | -2088 | 29912 | 26576.05 | 26576.05 |  | 27000 | [8 empty] | Utilities/ Other Infrastructure
T19.02.04 | Invasive species |  |  |  | 299917 | -31000 | 268917 | 268277 | 253500 |  | 268000 | [8 empty] | Utilities/ Other Infrastructure
T19.03.01 | Unallocated |  |  |  | 134574 | 0 | 134574 | 111574 | 134574 |  |  |  | 111574 | [6 empty] | Utilities/ Other Infrastructure
T19.03.02 | Set up / mobilisation |  |  |  | 179741 | 0 | 179741 | 179741 | 179741 |  |  |  | 179741 | [6 empty] | Utilities/ Other Infrastructure
T19.03 | Subtotal depot advance works |  |  |  | 5438987 | 0 | 5438987 | 5415378 | 5438378 |  | 5438000 |  | -22622 | [6 empty] | Utilities/ Other Infrastructure
T19.06.61 | VE - Marerial recovery / reprocessing - MUDFA |  |  |  | -120000 | 0 | -120000 | -120000 | 0 |  | -120000 | [8 empty] | Utilities/ Other Infrastructure
T19.06.62 | VE - Reduction in extent of road reinstatement |  |  |  | -116000 | 0 | -116000 | -116000 | 0 |  | -116000 | [8 empty] | Utilities/ Other Infrastructure
T19.06.63 | VE - Deferred Leasing |  |  |  | -2961000 | 0 | -2961000 | -2961000 | 0 |  | -2961000 | [8 empty] | Utilities/ Other Infrastructure
T19.06.64 | VE - Network Reinforcement |  |  |  | -1363000 | 0 | -1363000 | -1363000 | -1363000 |  | -1363000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.04 | Power - Network reinforcement |  |  |  | 1579674 | 0 | 1579674 | 1579674 | 1579674 |  | 1580000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.05 | Ticket machines |  |  |  | 750000 | 0 | 750000 | 750000 | 140625 |  | 750000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.06 | IPR2 contingency |  |  |  | 300000 | 0 | 300000 | 300000 | 300000 |  | 300000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.07 | Traffic signal and UTC |  |  |  | 0 | -38372 | -38372 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.07.08 | Murrayfield modifications |  |  |  | 940010 | 223014 | 1163024 | 1104356 | 1174843 |  | 999000 |  | 105356 | [6 empty] | Utilities/ Other Infrastructure
T19.07.16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.07.10 | Office land rental |  |  |  |  | 209601.37 | 209601.37 | 313499.88 | 189437.88 |  | 313000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.11 | Leith goods yard |  |  |  |  | 56000.08 | 56000.08 | 79541.0223 | 79541.0223 |  | 80000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.12 | Traffic management design |  |  |  |  | 400000 | 400000 | 400000 | 78125 |  | 400000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.17 | Burnside Road - Construction Costs |  |  |  |  | 1611394 | 1611394 | 1564042.99 | 1564042.99 |  | 1564042.99 | [8 empty] | Utilities/ Other Infrastructure
T19.07.18 | Burnside Road - BAA Costs |  |  |  |  | 349142 | 349142 | 414643.46 | 414643.46 |  | 414643.46 | [8 empty] | Utilities/ Other Infrastructure
T19.07.19 | Burnside Road - Consultancy Costs |  |  |  |  | 215000 | 215000 | 200097.76 | 200097.76 |  | 200097.76 | [8 empty] | Utilities/ Other Infrastructure
T19.07.20 | Burnside Road - Other Costs |  |  |  |  | 330000 | 330000 | 246813.08 | 3802.08 |  | 246813.08 | [8 empty] | Utilities/ Other Infrastructure
T19.07.21 | BAA MUDFA - Construction Costs |  |  |  |  | 445081 | 445081 | 439643.44 | 439643.44 |  |  | 440000 |  |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.22 | BAA MUDFA - BAA Costs |  |  |  |  | 119119 | 119119 | 144119.07 | 144119.07 |  |  | 144000 |  |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.23 | BAA MUDFA - Consultancy Costs |  |  |  |  | 75000 | 75000 | 116793.71 | 116793.71 |  |  | 117000 |  |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.24 | BAA MUDFA - Other Costs |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.07.25 | Forth Ports Section 1a |  |  |  |  | 0 | 0 | 0 | 1810345 | [10 empty] | Utilities/ Other Infrastructure
T19.07.26 | SW Global Resourcing |  |  |  |  | 0 | 0 | 792000 | 442409 |  | 560000 |  | 232000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.27 | Stray Current Monitoring |  |  |  |  | 89596 | 89596 | 156223 | 136223 |  | 156000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.28 | Manhole at Balbirnie Place (Frontline cost) |  |  |  |  | 0 | 0 | 219000 | 219000 |  | 45000 |  | 174000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.29 | SGN Gas main haymarket |  |  |  |  | 0 | 0 | 47687 | 47687 |  | 48000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.30 | Crash Gate 10 |  |  |  |  | 0 | 0 | 175000 | 175000 |  | 175000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.31 | Constitution Street – Mock-up |  |  |  |  | 0 | 0 | 46037.4033 | 46037.4033 |  | 46000 | [8 empty] | Utilities/ Other Infrastructure
T19.07.32 | SGN Gas diversion |  |  |  |  | 302000 | 302000 | 592000 | 552000 |  |  | 552000 | 40000 |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.33 | MUDFA scoped side entry manholes |  |  |  |  | 0 | 0 | 616043 | 523209 |  |  | 616000 |  |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.34 | Power network Reinforcement |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.07.35 | Section 1a Utilities |  |  |  |  | 3099374 | 3099374 | 3399337.0585 | 3399337.0585 |  | 3350000 |  | 49337.0585 | [6 empty] | Utilities/ Other Infrastructure
T19.07.36 | Clancy Docwra Utilities Works |  |  |  |  | 1454000 | 1454000 | 4882963 | 5484051 |  |  | 2122000 | 2760963 |  | Included in MUDFA AFC |  |  |  |  | Utilities/ Other Infrastructure
T19.07.37 | Section 5C Edinburgh Park Clancy |  |  |  |  | 54284 | 54284 | 256957 | 256957 |  |  |  | 256957 | [6 empty] | Utilities/ Other Infrastructure
T19.07.38 | Mass Barier Costs |  |  |  |  | 200000 | 200000 | 401000 | 395000 |  | 200000 |  | 201000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.39 | Baltic Street |  |  |  |  | 12739 | 12739 | 1200000 | 0 |  |  |  | 1200000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.40 | South Gyle - Sewer Diversion |  |  |  |  | 892027 | 892027 | 892207 | 852274 |  |  |  | 892207 | [6 empty] | Utilities/ Other Infrastructure
T19.07.41 | Visirail / Rubber Kerbs |  |  |  |  | 678282 | 678282 | 773600 | 773600 |  |  |  | 773600 | [6 empty] | Utilities/ Other Infrastructure
T19.07.42 | SUC Costs - from MUDFA |  |  |  |  | 782500 | 782500 | 650000 | 650000 |  |  |  | 650000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.43 | SUC Betterment - from MUDFA |  |  |  |  | -458309 | -458309 | -380400 | 0 |  |  |  | -380400 | [6 empty] | Utilities/ Other Infrastructure
T19.07.44 | Grontmij design novation section 7 BAA |  |  |  |  | 80000 | 80000 | 0 | 0 | [10 empty] | Utilities/ Other Infrastructure
T19.07.45 | Trial Holes S. Gyle |  |  |  |  | 0 | 0 | 70000 | 70000 |  |  |  | 70000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.46 | Bus Tracker Work |  |  |  |  | 0 | 0 | 45000 | 45000 |  |  |  | 45000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.47 | POL HA Temp Retention Works |  |  |  |  | 0 | 0 | 100000 | 100000 |  |  |  | 100000 | [6 empty] | Utilities/ Other Infrastructure
T19.07.09 | Fastlink alternative |  |  |  |  | 529477 | 529477 | 549000 | 549000 |  |  | 549000 |  |  | Utilised Infraco Prov sum - avoid double count |  |  |  |  | Utilities/ Other Infrastructure
T19.07.13 | Ancient monuments |  |  |  |  | 95700 | 95700 | 174500 | 174500 |  |  | 175000 |  |  | Utilised Infraco Prov sum - avoid double count |  |  |  |  | Utilities/ Other Infrastructure
T19.07.14 | TMi cycle integration study |  |  |  |  | 17700 | 17700 | 19657 | 19657 |  |  | 20000 |  |  | Utilised Infraco Prov sum - avoid double count |  |  |  |  | Utilities/ Other Infrastructure
T19.07.15 | Siemens out of hours monitoring |  |  |  |  | 100000 | 100000 | 100000 | 79992 |  |  | 100000 |  |  | Utilised Infraco Prov sum - avoid double count |  |  |  |  | Utilities/ Other Infrastructure
T19 | Total Infraco |  |  |  | 8962284 | 11849261.45 | 20811545.45 | 28697964.3685 | 30303467.1463 |  | 16425597.29 | 4835000 | 7438713.0585
T999 | Total |  |  |  | 57518447.8399 | 17404178.45 | 74922626.2899 | 86888919.3685 | 92708500.1463 |  | 75745597.29 | 4835000 | 6309668.0585
[5 empty] | W/Off tax VE item |  |  | 2961000 | 2961000 |  | 2961000
[8 empty] | 89849919.3685 | 95669500.1463 |  | 78706597.29

## Project Costs
Pitchfork 2 - Project Costs
Design and re-procurement
Continuing works/off street
On street to SAS
On street remaining
|  |  | Extract from P7 Consolidation | [8 empty] | Cumulative to date |  | Post termination in the Terminate & Reprocure Option
|  |  | Cum COWD P11 | P7 COWD | PCB | App'd changes | CAB | P7 AFC | P11 AFC | Option 3C AFC |  |  | Cum to terminate | 4m to Jun 11 | 6m to Dec 11 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | Post terminate
T01.01 | Project management Staff Costs |  | 29907878.9935 | 420884.8065 | 26697669.9218 | 523193.5343 | 27220863.4561 | 35244468.8207 | 35206408.3268 | 36795388 |  |  | 29907878.9935 | 2676000 | 1170750 | 2174250 | 2174250 | 681460 | 681460 | 681460 | 681460 | 10921090
T01.02 | Recruitment Fees |  | 448675.02 | 0 | 466202.6166 | -0.02 | 466202.5966 | 466204.3333 | 466204.5756 | 466202.9 |  |  | 448675.02 | [8 empty] | 0
T01.03 | Travel & Subsistence / Conference |  | 345622.23 | 2886.94 | 356214.2 | -0.44462 | 356213.7554 | 366158.94 | 366158.98 | 366158 |  |  | 345622.23 | [8 empty] | 0
T01.04 | Central Overheads |  | 5059496 | 55957 | 5580828.4493 | 0.38 | 5580828.8293 | 5595423 | 5595424 | 5595422.222 |  |  | 5059496 | 223828 | 195849.5 | 363720.5 | 363720.5 | 72744.1 | 72744.1 | 72744.1 | 72744.1 | 1438094.9
T01.05 | IT & Software Costs / fitout |  | 3141965.17 | 33988 | 3109074.5062 | 0.27308 | 3109074.7792 | 4241492 | 4241492.77 | 3635042.8767 |  |  | 3141965.17 | 135952 | 118958 | 220922 | 220922 | 44184.4 | 44184.4 | 44184.4 | 44184.4 | 873491.6
T01.06 | Citypoint - rent,rates,s/c |  | 2709127.94 | 48838.766 | 2171872.6414 | -0.1759 | 2171872.4655 | 3465481.5003 | 3465481.2457 | 3481507.5914 |  |  | 2709127.94 | 195355.064 | 170935.681 | 317451.979 | 317451.979 | 158725.9895 | 158725.9895 | 158725.9895 | 158725.9895 | 1636098.6608
T01.08 | Short Term Contractors |  | 196804 | 0 | 196804 | 0 | 196804 | 196804 | 196804 | 196804 |  |  | 196804 | [8 empty] | 0
T01.09 | City Point Overheads |  | 25271.09 | 0 | 25270.8462 | 0 | 25270.8462 | 25271.09 | 25271.09 | 25270.8262 |  |  | 25271.09 | [8 empty] | 0
T01.10 | Active Risk Manager |  | 83666 | 0 | 83665 | 0 | 83665 | 83666 | 83666 | 83665 |  |  | 83666 | [8 empty] | 0
T01.11 | Archaeological supervisor - Gogar works |  | 153992.9103 | 0 | 267879 | -82646.11 | 185232.89 | 247730.9103 | 247729.9103 | 251487.9103 |  |  | 153992.9103 | [8 empty] | 0
T01.13 | Archaeology - Non Gogar |  | 334183 | 0 | 0 | 642742.2423 | 642742.2423 | 580469 | 580469 | 552454.2838 |  |  | 334183 | [8 empty] | 0
T01.14 | DRP Costs |  | 4484172.56 | 198679.43 | 0 | 2985327 | 2985327 | 3999809.43 | 4865624.56 | 2132505.93 |  |  | 4484172.56 | [8 empty] | 0
T01.15 | Tax Planning / Governance Costs (Non DLA) |  | 21960 | 0 | 0 | 0 | 0 | 301816 | 301816 | 301816 |  |  | 21960 |  |  |  | 300000 |  |  |  |  | 300000
T01 | Total tie PM costs |  | 46912814.9138 | 761234.9425 | 38955481.1814 | 4068616.6792 | 43024097.8606 | 54814795.0246 | 55642550.4583 | 53883725.5403 |  |  | 46912814.9138 | 3231135.064 | 1656493.181 | 3076344.479 | 3376344.479 | 957114.4895 | 957114.4895 | 957114.4895 | 957114.4895 | 15168775.1608
T02 | Total DPOF |  | 2679140 | 16911.16 | 7631160.25 | 0 | 7631160.25 | 7631160.2488 | 7631160.0888 | 7631159.7988 |  |  | 2679140 | 67644.64 | 118378.12 | 390000 | 3000000 |  | 1000000 |  | 407000 | 4983022.76
T03.01-19 | DLA |  | 3503460.01 | 10900.5 | 2862498.72 | 392235.1 | 3254733.82 | 3554224.95 | 3590966.51 | 3544591.19 |  |  | 3503460.01
T03.20-35 | Subtotal D&W |  | 2843083.65 | 2436 | 2922353.677 | -110751 | 2811602.677 | 2852731 | 2869988.9833 | 2730832 |  |  | 2843083.65
T03 | Total LEGALS |  | 6346543.66 | 13336.5 | 5784852.397 | 281484.1 | 6066336.497 | 6406955.95 | 6460955.4933 | 6275423.19 |  |  | 6346543.66 | 333000 | 500000 | [6 empty] | 833000
T06.01-03 | Subtotal TSS |  | 10685667 | 31251 | 9507939.4403 | 1008900.35 | 10516839.7903 | 11021365.08 | 11343479.5299 | 10652287 |  |  | 10685667
T06.03a | Subtotal CEC |  | 2182684 | 41669 | 1168277 | 1011312.49 | 2179589.49 | 2266022 | 2378622 | 2184381.93 |  |  | 2182684
T06 | Total TSS and CEC |  | 12868351 | 72920 | 10676216.4403 | 2020212.84 | 12696429.2803 | 13287387.08 | 13722101.5299 | 12836668.93 |  |  | 12868351 | 291680 | 255220 | 94796 | 94796 | 94796 | 94796 | 94796 | 94796 | 1115676
T12.01-12,23-40 | Subtotal Communications |  | 2110116.68 | 19146 | 1901845.7 | 272968.3077 | 2174814.0077 | 2424819.67 | 2434363.68 | 2410730.67 |  |  | 2110116.68
T12.13-22 | Subtotal Stakeholder |  | 727964.3 | 937 | 624370 | 112662 | 737032 | 741507.3 | 741506.1 | 723505.54 |  |  | 727964.3
T12 | Total COMMS / MARKETING |  | 2838080.98 | 20083 | 2526215.7 | 385630.3077 | 2911846.0077 | 3166326.97 | 3175869.78 | 3134236.21 |  |  | 2838080.98 | 80332 | 140581 | 261079 | 261079 |  |  |  |  | 743071
T13 | Total TEL |  | 2510782.67 | 10274 | 2723133 | 74100 | 2797233 | 3046117.6429 | 3046118.8129 | 3720365 |  |  | 2510782.67 | 41096 |  | 12000 | 337000 |  |  |  |  | 390096
T999 | Total |  | 74155713.2238 | 894759.6025 | 68297058.9687 | 6830043.9269 | 75127102.8956 | 88352742.9163 | 89678756.1633 | 87481578.6692 |  |  | 74155713.2238 | 4044887.704 | 2670672.301 | 3834219.479 | 7069219.479 | 1051910.4895 | 2051910.4895 | 1051910.4895 | 1458910.4895 | 23233640.9208
|  |  | 74155713.2238 | [5 empty] | 89678757.1633 |  |  |  | 74156 | [7 empty] | Increase to:
|  |  | 0 | [5 empty] | 1 | [11 empty] | expected total | 97389354.1445
|  | Staff Costs | Count
Payroll:
|  | Finance/ICT | 10 | 44000 | [9 empty] | 33000 | 33000 | 33000 | 33000 | 14520 | 14520 | 14520 | 14520 | ) | Simple modelling based on % of current costs. Assumes comms/stakeholder costs all part of operating costs from OFRS to SAS from which further step-down in resources allocated to Capex. Implicitly assumes no salary increments or bonus throughout.
|  | Comms/Stakeholder | 12 | 47000 | [9 empty] | 23500 | 23500 | 23500 | 23500 |  |  |  |  | )
|  | Exec/Secretarial/Admin | 8 | 36000 | [9 empty] | 36000 | 36000 | 36000 | 36000 | 9000 | 9000 | 9000 | 9000 | )
|  | Project | 46 | 236000 | [9 empty] | 59000 | 59000 | 59000 | 59000 | 23600 | 23600 | 23600 | 23600 | )
|  |  | 76 | 363000 | [9 empty] | 151500 | 151500 | 151500 | 151500 | 47120 | 47120 | 47120 | 47120
"Contractors":
|  | Comms/Stakeholder | 1 | 5000 | [9 empty] | 2500 | 2500 | 2500 | 2500
|  | Project | 10 | 53000 | [9 empty] | 13250 | 13250 | 13250 | 13250 | 5300 | 5300 | 5300 | 5300
|  |  | 11 | 58000 | [9 empty] | 15750 | 15750 | 15750 | 15750 | 5300 | 5300 | 5300 | 5300
|  | Per 4wk period | 87 | 421000 | [9 empty] | 167250 | 167250 | 167250 | 167250 | 52420 | 52420 | 52420 | 52420
Note on M34: Forecasts are to Feb 12. Included in Pitchfork 3C = £87.5m plus £0.5m per month for prolongation to Oct 2012 = £91.5m.
Note on P20: Assumed we burn all AFC for this prior to Dec. Professional fees related to post termination BSC matters included in the provision for Assumed we burn all AFC for this prior to Dec. Professional fees related to post termination BSC matters included in the provision for litigiation costs £30m
Note on U4: OFRS on section from Airport to SAS at end of 2013.
Note on Z9: Preliminary view of the post termination staff profile below - much smaller project team. it will be wrong. Needs to be based on a considered manpower plan which reflects inter-alia: -PM philosophy -Site supervision appropriate to contracting method -Proper integration/efficiencies with CEC and Operational Readiness budgets No allowance for any redundancy costs!
Note on Z12: Proportional to staff costs (kind of)
Note on Z13: Proportional to staff costs (kind-of). At some stage the joined up ICT strategy as between tie, LB and Tram operations needs to swim into focus.
Note on Z14: Assumes we all fit onto CP2 from July 2011 (and therefore that lease on CP1 extended till then) following which we occupy CP2 or equivalent space till OFRS to SAS in Dec 13. Thereafter occupancy costs half again for the smaller project team but they could be zero depending on overall accomodation needs of tie/TEL/LB/CEC
Note on Z21: Depends entirely on bus/tram business integration happening.
Note on Z23: Assumes phased spending of the existing operational readiness budget with bulk in 20134 for a OFRS Apt to SAS in 2013.
Note on Z26: This is the cost of professional services (mostly lawyers) to put the new procurements in place.
Note on Z29: CEC costs to be part of joined up manpower planning.
Note on Z32: Becomes part of operating costs from OFRS to SAS
Note on Z33: Mostly LB recharges - assumes A Richards is in our costs going forward. Cant justify any other recharges of LB management time myself.