## Sheet1
Printed On: 07 Nov 2008
Period 8 - 2008/009 Primary Risk Register
Risk Description
ARM Risk ID | Cause |  | Event | Effect | Risk Owner | Significance | Black Flag | Treatment Strategy |  | Previous Status |  | Current | Due Date |  | Action Owner
Status
139 | Utilities diversion outline specification only from plans |  | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD | Increase in MUDFA costs or delays as a result of carrying out more diversions than estimated | G Barclay | High - 25.00 |  | Carry out GPR Adien survey |  | Complete | Complete |  |  | 2007-10-31 | J Casserly
[8 empty] | Identify increase in services diversions. MUDFA to resource/re-programme to meet required timescales. |  | Complete | Complete |  |  | 2007-11-23 | J McAloon
[8 empty] | In conjunction with MUDFA, undertake trial excavations to confirm locations of Utilities and inform designer |  | On Programme | On Programme |  |  | 2008-11-30 | A Hill
164 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; asbestos found in excavation for utilities diversion; unknown cellars and basements intrude into works area; other physical obstructions; other contaminated land |  | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | I Clark | High - 25.00 |  | Carry out GPR Adien survey |  | Complete | Complete |  |  | 2007-10-31 | J Casserly
[8 empty] | Identify increase in services diversions. MUDFA to resource/re-programme to meet required timescales. |  | Complete | Complete |  |  | 2007-11-23 | J McAloon
[8 empty] | In conjunction with MUDFA, undertake trial excavations to confirm locations of Utilities and inform designer |  | On Programme | On Programme |  |  | 2008-11-30 | A Hill
44 | SDS contractor does not deliver the required prior approval consents in line with SDS V31 |  | Late prior aproval consents | Delay to programme with additional resource costs and delay to infraco. Impact upon risk balance. | D Sharp | High - 23.00 |  | Evaluation of prior approval programme |  | Complete | Complete |  |  | 2008-10-31 | D Sharp
[8 empty] | Hold fortnightly Roads Design Group |  | Complete | Complete |  |  | 2007-12-31 | T Glazebrook
[8 empty] | Informal consultation prior to statutory consultation |  | On Programme | On Programme |  |  | 2008-12-31 | T Glazebrook
[8 empty] | Integrate CEC into tie organisation/accomodation (office move) |  | Complete | Complete |  |  | 2007-06-04 | T Glazebrook
[8 empty] | Weekly Meetings of Approvals Task Force |  | On Programme | On Programme |  |  | 2008-12-31 | D Sharp
173 | Uncertainty over extent of contaminated land on route |  | Tramway runs through area of previously unidentified contamination and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | R Bell | High - 23.00 |  | Issue containation and gi report to Infraco bidders |  | Complete | Complete |  |  | 2007-03-02 | B Dawson
[8 empty] | tie to obtain ground investigation and contamination reports from SDS |  | Complete | Complete |  |  | 2007-03-30 | A McGregor
52 | Political and/or Stakeholder objectives change or require design developments that constitute a change of scope; Planning Department requires scope over and above baseline scope in order to give approval (may be as a result of lack of agreement over interpretation of planning legal requirements). |  | Amendments to design scope from current baseline and functional specification. | Programme delay as a result of re-work; Programme delay due late receipt of change requirements and lack of resolution; Scope/cost creep (dealt with through change process); Project ultimately could become unaffordable. | D Sharp | High - 22.00 |  | Close working relationship with CEC and stakeholders |  | On Programme | On Programme |  |  | 2011-01-31 | L Murphy
[8 empty] | Weekly critical issues meeting |  | On Programme | On Programme |  |  | 2008-07-31 | T Glazebrook
928 | Major single safety incident (including a dangerous occurrence) during construction |  | Safety incident during construction | Delay (potentially critical) due to HSE investigation and rework. PR risk to tie and stakeholders. | S Clark | High - 21.00 |  | All Site Staff to get CSCS or equivalent |  | On Programme | On Programme |  |  | 2008-04-30 | C McLauchlan
[8 empty] | Develop and Implement Incident Management Processes |  | Complete | Complete |  |  | 2007-04-27 | T Condie
[8 empty] | HSQE Audits, site inspections and Management Safety Tours to be carried out |  | On Programme | On Programme |  |  | 2010-12-31 | T Condie
[8 empty] | Safety Induction to be carried out for all site staff |  | On Programme | On Programme |  |  | 2010-12-31 | T Condie
[8 empty] | Site Supervisors to be appointed by tie |  | Complete | Complete |  |  | 2007-02-28 | S Clark
931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redudant utilities; unknown live utilities; unknown redundant utilities. |  | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | D Sharp | High - 20.00 |  | GPR surveys in areas where there are likey to be services |  | Complete | Complete |  |  | 2007-04-01 | T Glazebrook
[8 empty] | MUDFA trial holes to verify GPR surveys |  | On Programme | On Programme |  |  | 2009-01-31 | P Douglas
977 | Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. |  | Delay in achievement of TRO(s) due to a large number of public objections and/or a legal challenge to using a TTRO to construct Infraco. | Requirement to start construction using TTROs | K Rimmer | High - 20.00 |  | Use of TTROs to undertake construction of permanent works in advance of permanent TROs being approved. |  | On Programme | On Programme |  |  | 2011-01-30 | K Rimmer
271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. |  | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | D Sharp | High - 19.00 |  | Agree approvals submission arrangements with CEC to align with SDS design programme and procurement programme. |  | Complete | Complete |  |  | 2008-03-31 | T Glazebrook
[8 empty] | Assure the quality and timing of submissions |  | On Programme | On Programme |  |  | 2008-12-31 | D Sharp
[8 empty] | Final agreement to be approved by Roads Authority, CEC Promoter, CEC in-house legal and tie |  | Complete | Complete |  |  | 2007-02-28 | T Craggs
[8 empty] | Finalise alignments and gain agreement from CEC |  | Complete | Complete |  |  | 2006-12-29 | T Craggs
[8 empty] | Weekly meetings of Approvals Task Force |  | On Programme | On Programme |  |  | 2008-12-31 | D Sharp
[8 empty] | Where appropriate increase case officer resource to cope with programme compression |  | Complete | Complete |  |  | 2008-10-31 | D Fraser
1033 |  |  | Failure of Infraco to mobilise in time to commence work in line with programme. | Delay to programme. Cost overruns. Negative publicity. Criticism from stakeholders | S Bell | High - 19.00 |  | Continued focus at Infraco progress meetings as well as programme workshops to mitigate the impacts of any delay |  | On Programme | On Programme |  |  | 2008-10-01 | S Bell
[8 empty] | Implementation of Advanced Works programme in order to mitigate potential future issues during construction |  | On Programme | On Programme |  |  | 2008-08-01 | R Bell
[8 empty] | Infraco given instructions to proceed at risk |  | On Programme | On Programme |  |  | 2008-08-01 | R Bell
[8 empty] | Pressue from Approvals Task Force to ensure Technical and Prior Approvals are delivered |  | On Programme | On Programme |  |  | 2008-10-01 | D Sharp
1076 | Utilities do not finish diversion works prior to Tramworks commencing work |  | Tramworks are unable to commence work or work is delayed/disrupted | Delay and disruption claims from BSC. | R Bell | High - 18.00 |  | Tramworks PMs attendance at Traffic Management meetings. Weekly meetings between tie Tramworks and Utilities PMs. 4-weekly tie Tramworks/Utilities management meetings. Identification of programme clashes between Tramworks and Utilities works tracked |  | N/A | On Programme |  |  | 2009-07-31 | R Bell
1077 | Lack of visibility of design changes between November 2007 and May 2008 |  | Tramworks price based on a design which may have been altered. Unclear who authorised design change. |  | R Bell | High - 18.00 |  | Establish a process which will act as a control mechanism for design changes. (If one exists already then ensure process is complied with) |  | N/A | On Programme |  |  | 2008-12-31 | T Glazebrook
1078 | Lack of effective engagement from BSC leaders towards tie and third parties (NR, BAA, Forth Ports) and the Tram project as a whole. |  | Failure of partnership approach between tie and BSC. Failure to maintain effective third party relationships with key third parties. |  | R Bell | High - 18.00 |  | Engagement between tie and BSC at different levels. Regular review of BSC management of third parties as per Employers Requirements. |  | N/A | On Programme |  |  | 2008-12-31 | R Bell
1079 | Failure of BSC to effectively resource up for project |  | Lack of competent resources within BSC to safely and effectively deliver Tram project | Delay to programme and additional cost | R Bell | High - 18.00 |  | Ongoing review of BSC resources and formal review at 4-weekly meeting. Objectives to be set for BSC at monthly meetings in order to monitor progress. |  | N/A | On Programme |  |  | 2008-12-31 | R Bell
1080 | TPB have agreed a 5 week embargo on Leith Walk from 12 Dec 08 to 19 Jan 09. |  | Leith Walk embargo causes delay to construction and utility diversion works. | Delay to programme, extension of time claim. Additional costs. | R Bell | High - 18.00 |  | Minimise contractors exposure by identifying other work scopes outside the embargo area. |  | N/A | On Programme |  |  | 2008-12-12 | R Bell
1081 | Traffic modelling has shown that one lane needs to be kept open on Princes Street during works |  | Princes Street works take longer than programmed due to one lane being kept open. | Delay to programme, extension of time claim. Additional costs. | R Bell | High - 18.00 |  | Production of robust programme to mitigate losses |  | N/A | On Programme |  |  | 2009-01-05 | R Bell
Page 13 of 13