## Entitlement on GMP (hidden)
| Infraco | Off Street Section
Contract Works Price | 238607664 | 147555906
Changes
Civils | 12238000 | 12238000
Systems | 1543000 | 1543000
Total Changes | 13781000 | 13781000
Total CWP plus Changes | 252388664 | 161336906
GMP | 362500000 | 362500000
Delta | 110111336 | 201163094
Changes to Agree | 28942000 | 28942000
must assume they are in GMP
Entitlement plus Deal Premium | 81169336 | 172221094

## McG Structured Summary (hidden)
Edinburgh Tram Project
Mar Hall Budget Appraisal (VFM Comparison)
Based on Amounts Certified to Infraco on 6th June 2011
| MOV5 |  | Separate |  |  |  | Attrition
|  |  | Mothball/Cancel Project |  | Re-Procure
| MOV5 entered into on or before 1.7.11, and subsequently becomes unconditional |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract
BB/S Costs to Date as at 21/5/2011 | 174.4 | 1 | 174.4 | 1 | 174.4 | 1 | 174.4 | 1
CAF Costs to Date as at 21/5/2011 | 48 | 1 | 48 | 1 | 48 | 1 | 48 | 1
BSC Costs to Date | 222.4 |  | 222.4 |  | 222.4 |  | 222.4
BB/S Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 188.1 | 2
CAF Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 14.4 | 3 | 14.4 | 3 | 14.4 | 3 | 14.4 | 3
Haymarket to St Andrew Sq (Target Cost) | 22.5 | 4
Sub Total | 447.4 |  | 236.8 |  | 236.8 |  | 236.8
Remaining Infrastructure | [6 empty] | 189.4 | 18
New Contractor to replace Infraco |  |  |  |  | 189.8 | 11
Infrastructure and Vehicles | 447.4 |  | 236.8 |  | 426.6 |  | 426.2
Infraco Claims to be paid |  |  | 70 | 7 | 70 | 7 | 70 | 7
Prelims |  |  | 15 |  | 15 |  | 15
tie claims e.g. defects |  |  | -3 |  | -5
BSC Settlement Premium + Risk |  |  | 66 | 12 | 66 | 12
Loss of Profits
MOV4 Impacts |  |  | 13 | 8 | 13 | 8 | 13 | 8
Costs of Putting Project on Hold |  |  | 20 | 9
Total Budget "Final Account" | 447.4 |  | 417.8 |  | 585.6 |  | 524.2
Primary Risk |  |  |  |  | 32 | 13 | 32 | 13
Further Risk/Contingencies | 30 | 5 |  |  | 49 | 14 | 49 | 14
Systems Risk in relation to new contractor using existing materials |  |  |  |  | 10 | 15
Inflation Risk |  |  |  |  | 25 | 16
Further Delay | [6 empty] | 86 | 19
Exclusion Risk |  |  |  |  | 77 | 17 | 77 | 17
Litigation, Professional Fees |  |  | 3 |  | 3 |  | 60 | 20
Risk Related Items | 30 |  | 3 |  | 196 |  | 304
Non BSC Costs to date (incl design) | 239 |  | 239 |  | 239 |  | 239
Project Management Costs to go | 30 | 6 |  |  | 30 | 6 | 30 | 6
Site Security and Interim Works |  |  | 20 | 10
Non BSC Costs to Date plus PM costs to go | 269 |  | 259 |  | 269 |  | 269
Total Project Costs | 746.4 |  | 679.8 |  | 1050.6 |  | 1097.2
Notes
1. Includes payments made under MOV4, numbers taken from Dennis Murray on 6th June
2. Sum arrived as the difference between the AIR-HAY lump sum and payments to date.
3. Sum arrived at as the difference between the CAF budget plus EOT €5.1m (£4.4m) less payments to date. Undertaking given to CAF we will take trams in ant event, therefore included in all scenarios.
4. Target Price to be firmed up in MOV5 negotiations.
5. Risk and contingency required from Colin Smith and negotiations of MOV5.
6. To be followed up pending new structure.
7. Draft number from Cyril Sweet Report, this requires to be informed by McGrigors exercise. Plus EOT1 and INTC 429
8. MOV4 Impacts, remaining payments to be made under MOV4, primarily in relation to Siemens Materials
9. Cost associated with reinstatements, tram act consequences
10. Initial Reinstatement Costs
11. Taken from section 4 of Cyril Sweett Report
12. Assumes a further £56m premium for BB/S to walk away plus an additional £10m payment for sub contractors
13. Variable risk elements
14. This risk relates to a premium that would be expected to be paid to a new contractor for "bad project risk" and further re-work of the design. There are no time related costs for a new procurement or indeed the costs of running a new procurement.
15. Guestimate
16. A like for like comparision to the current Infraco contract cannot be made without allowing for inflation in any new procurement.
17. An assessment was made of the exclusions related to BSC's PPP. These exclusions are now off the table and included in the GMP, however, under a reprocurement it is possible these exclusions would either be included in the tender price or as risk items.
18. High side view of Infrastructure costs to - go from Deck chair spreadsheet to SAS.
19. 50% of Marhall v's CWP delta, rationale that the current contract would continue to drive delay
20. Continuing Litigation Costs from Deck chair spreadsheet.

## Summary (hidden)
Edinburgh Tram Project
Mar Hall Budget Appraisal (VFM Comparison)
2011-04-01
| Mar Hall Budget | Note | Separation | Note | Walk Away | Note | Attrition | Note | Notes & Assumptions | Description
Airport to Haymarket (Infraco) | 362.5 | [7 empty] | 1 | Haymarket to St Andrew Square a variable item to be closed out in negotiations. The £22.5m is based on our original bottom up assessment. This includes 15% risk allowance and a sum for Siemens Materials now covered elsewhere.
(Current Contract Arrangements) | [8 empty] | 2 | Client contingency/risk pot to be refined. Based on Infraco terms and conditions for Phoenix containing no exclusions of clarifications.
[9 empty] | 3 | Project Mgt costs to go assume no future recoveries by CEC Legal, Finance and Lothian Buses and requires a full review.
Haymarket to St Andrew Sq (Target Cost/Pain Gain Share) | 22.5 | 1 | [6 empty] | 4 | Total Project cost includes the cost of all Siemens materials to Newhaven and other specific items to Newhaven, thus securing value for future construction to Newhaven.
[9 empty] | 5 | Work certified to date for BB/S and SDS.
BSC Costs to Date |  |  | 133 | 5 | 133 | 14 | 133 |  | 6 | tie Commercial team assessment based on a Bill of Quantities.
[9 empty] | 7 | Variable risk elements.
Remaining Infrastructure | [6 empty] | 281.987 | 18 | 8 | This risk relates to a premium that would be expected to be paid to a new contractor for "bad project risk" and further re-work of the design. There are no time related costs for a new procurement or indeed the costs of running a new procurement.
[9 empty] | 9 | BSC would seek additional payment for delay they feel they have suffered as well as loss of profit and costs associated with their supply chain.
New Contractor to replace Infraco |  |  | 143 | 6 |  |  |  |  | 10 | There would be a risk associated with the reprocurement of Siemens equipment both in terms of price changes relating to steel and copper since the orignal procurement and interface risk related to two different systems suppliers.
[9 empty] | 11 | A like for like comparision to the current Infraco contract cannot be made without allowing for inflation in any new procurement.
Infrastructure | 385 |  | 276 |  | 133 |  | 414.987 |  | 12 | An assessment was made of the exclusions related to BSC's PPP. These exclusions are now off the table and included in the GMP, however, under a reprocurement it is possible these exclusions would either be included in the tender price or as risk items.
[9 empty] | 13 | This cost only relates to a terminal point at St Andrews Sq and does not secure the value of Siemens materials to Newhaven. There are also significant risks in relation to the separation approach regarding the availability of a willing contractor to undertake the work.
CAF | 62 |  | 63.5 |  | 63.5 | 15 | 63.5 | 19 | 14 | Values for BB/S and SDS from Deckchair spreadsheet mid range. This assumes BB/S keep what they have been paid.
[9 empty] | 15 | CAF Payments to Date plus to go costs.
Primary Risk |  |  | 32 | 7 |  |  |  |  | 16 | Assumes a further £56m premium for BB/S to walk away plus an additional £10m payment for sub contractors
[9 empty] | 17 | tie view of delay to date from Marhall Prep.
Further Risk/Contingencies | 30 | 2 | 49 | 8 |  |  |  |  | 18 | High side view of Infrastructure costs to - go from Deck chair spreadsheet
[9 empty] | 19 | High side CAF figure, though no account taken of further delay as a result of attrition
BSC Settlement Premium + Risk |  |  | 50 | 9 | 66 | 16 |  |  | 20 | The increase in the Original coff-street ontract works price to the Mar Hall number is £146m. Tie numbers would indicate that £30m has been paid for scope change, therefore the assumption is that the remaining increase must be down to delay. This assumes tie accountable for 50% of the balance of delay.
[9 empty] | 21 | Assumes same level of delay going forward as to date.
Systems Reprocurement |  |  | 25 | 10 |  |  |  |  | 22 | Continuing Litigation Costs from Deck chair spreadsheet.
Inflation Risk |  |  | 25 | 11
Delay to date |  |  |  |  | 40 | 17 | 58 | 20
Further Delay | [6 empty] | 58 | 21
Exclusion Risk |  |  | 77 | 12
Litigation, Professional Fees | [6 empty] | 60 | 22
Total Budget "Final Account" | 477 |  | 597.5 |  | 302.5 |  | 654.487
Non BSC Costs to date | 236.5 |  | 236.5 |  | 236.5 |  | 236.5
Project Management Costs to go | 30 | 3 | 49.3 |  |  |  | 49.3
Site Security and Interim Works |  |  |  |  | 14.393
| 266.5 |  | 285.8 |  | 250.893 |  | 285.8
Total Project Costs | 743.5 | 4 | 883.3 | 13 | 553.393 |  | 940.287
Note on B21: Alan Coyle: £58m + €5.1m (£4m) = £62.m

## McG Certified to Date Basis (hidden)
Edinburgh Tram Project
Mar Hall Budget Appraisal (VFM Comparison)
Based on Amounts Certified to Infraco on 6th June 2011
Separation
| Settlement Agreement | Mothball/Cancel Project (High) | Mothball/Cancel Project (Low) | Re-Procure (High) | Re-Procure (Low) | Continue with Infraco to York Place (High) | Continue with Infraco to York Place (Low)
| MOV5 entered into on or before 1.7.11, and subsequently becomes unconditional | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract
Section 1
BB/S Costs to Date as at 21/5/2011 |  | 213 | 174.4 | 213 | 174.4 | 213 | 174.4
CAF Costs to Date as at 21/5/2011 |  | 48 | 48 | 48 | 48 | 48 | 48
BSC Costs to Date | 0 | 261 | 222.4 | 261 | 222.4 | 261 | 222.4
BB/S Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 362.5
CAF Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 62.4 | 14.4 | 14.4 | 14.4 | 14.4 | 14.4 | 14.4
Haymarket to St Andrew Sq (Target Cost) | 22.5
Section 1 sub total | 447.4 | 275.4 | 236.8 | 275.4 | 236.8 | 275.4 | 236.8
Section 2
Remaining Infrastructure | [5 empty] | 189.4 | 189.4
New Contractor to replace Infraco |  |  |  | 189.4 | 189.4
Section 1 + Section 2 = Infrastructure and Vehicles | 447.4 | 275.4 | 236.8 | 464.8 | 426.2 | 464.8 | 426.2
Section 3
INTC's agreed in full - work done not certified |  | 0.952 | 0.952 | 0.952 | 0.952 | 0.952 | 0.952
INTC's determined through adjudication - work done |  | 0.248 | 0.248 | 0.248 | 0.248 | 0.248 | 0.248
INTC's agreed in principle but disputed quantum |  | 1.583 |  | 1.583 |  | 13.795 | 10.274
INTC's dispute in principle - work done (to be done in case of attrition) |  | 6.337 | 3.366 | 6.337 | 3.366 | 39.332 | 16.013
EOT/Prelims |  | 49.776 | 13.076 | 49.776 | 13.076 | 49.776 | 13.076
tie claims e.g. defects |  | -5.6 | -5.6 | -5.6 | -5.6 | -5.6 | -5.6
Loss of Profits |  | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9
BSC Settlement Premium + Risk |  | 80 | 80 | 80 | 80
Costs of Putting Project on Hold |  | 26 | 26 | 16 | 16
Section 1+2+3 Total Budget "Final Account" | 447.4 | 442.596 | 362.742 | 621.996 | 542.142 | 571.203 | 469.063
Section 4
Primary Risk |  |  |  | 32 | 32 | 32 | 32
Further Risk/Contingencies | 77.5 |  |  | 49 | 49 | 49 | 49
Systems Risk in relation to new contractor using existing materials |  |  |  | 10 | 10
Inflation Risk |  |  |  | 25 | 25
Further Delay | [5 empty] | 86 | 86
Exclusion Risk |  |  |  | 77.5 | 77.5 | 77.5 | 77.5
Litigation, Professional Fees |  | 3 | 3 | 3 | 3 | 60 | 60
Section 4 sub total = Risk Related Items | 77.5 | 3 | 3 | 196.5 | 196.5 | 304.5 | 304.5
Section 5
Non BSC Costs to date (incl design) | 239 | 239 | 239 | 239 | 239 | 239 | 239
Project Management Costs to go | 9 | 3 | 3 | 12 | 12 | 18 | 18
Site Security and Interim Works |  | 20 | 20
Section 5 sub total Non BSC to Date + PM costs to go | 248 | 262 | 262 | 251 | 251 | 257 | 257
Sections 1+2+3+4+5 = Total Costs | 772.9 | 707.596 | 627.742 | 1069.496 | 989.642 | 1132.703 | 1030.563
Notes
1. Includes payments made under MOV4, numbers taken from Dennis Murray on 6th June
1a. As note 1 but includes BSC application total
2. Sum arrived as the difference between the AIR-HAY lump sum and payments to date.
3. Sum arrived at as the difference between the CAF budget plus EOT €5.1m (£4.4m) less payments to date. Undertaking given to CAF we will take trams in ant event, therefore included in all scenarios.
4. Target Price to be firmed up in MOV5 negotiations.
5. Risk and contingency required from Colin Smith and negotiations of MOV5.
6. To be followed up pending new structure.
7. Draft number from Cyril Sweet Report, this requires to be informed by McGrigors exercise. Plus EOT1 and INTC 429
8. MOV4 Impacts, remaining payments to be made under MOV4, primarily in relation to Siemens Materials
9. Cost associated with reinstatements, tram act consequences
10. Initial Reinstatement Costs
11. Taken from section 4 of Cyril Sweett Report
12. Assumes a further £56m premium for BB/S to walk away plus an additional £10m payment for sub contractors
13. Variable risk elements
14. This risk relates to a premium that would be expected to be paid to a new contractor for "bad project risk" and further re-work of the design. There are no time related costs for a new procurement or indeed the costs of running a new procurement.
15. Guestimate
16. A like for like comparision to the current Infraco contract cannot be made without allowing for inflation in any new procurement.
17. An assessment was made of the exclusions related to BSC's PPP. These exclusions are now off the table and included in the GMP, however, under a reprocurement it is possible these exclusions would either be included in the tender price or as risk ite
18. High side view of Infrastructure costs to - go from Deck chair spreadsheet to SAS.
19. 50% of Marhall v's CWP delta, rationale that the current contract would continue to drive delay
20. Continuing Litigation Costs from Deck chair spreadsheet.
21. From tie paper to McGrigors, assessment of WIP
22. Disputed Estimates from tie report to McGrigors delta of certified amount to BSC application.
23. Section 4 from tie response to McGrigors
24. Section 4 from tie response to McGrigors
25. Infraco upper limite less payments to date (£48m - payment to date)
26. Section 2 from tie response to McGrigors

## McG Entitlement Basis
Edinburgh Tram Project
Mar Hall Budget Appraisal
Based on Amounts Certified to Infraco on 6th June 2011
Separation
| Settlement Agreement (High) |  | Mothball/Cancel Project (High) |  | Mothball/Cancel Project (Low) |  | Re-Procure (High) |  | Re-Procure (Low) |  | Unsuccessful Termination |  | Unsuccessful Termination | Continue with Infraco to York Place (High) |  | Continue with Infraco to York Place (Low)
| MOV5 entered into on or before 1.7.11, and subsequently becomes unconditional |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  |  |  |  | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract |  | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract
Section 1
Milestones
Construction Milestones |  |  | 22.205 |  | 20.559 |  | 22.205 |  | 20.559 |  | 22.205 |  | 20.559 | 22.205 |  | 20.559
CAF - Tram Supply Milestones + to go cost |  |  | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 57.3 | 5 | 57.3 | 5
Maintenance Milestones |  |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 | 0.267 |  | 0.267
SDS |  |  | 6.248 |  | 6.032 |  | 6.248 |  | 6.032 |  | 6.248 |  | 6.032 | 6.248 |  | 6.032
MOV4 - Certificate 1 |  |  | 29.06 |  | 27 |  | 29.06 |  | 27 |  | 29.06 |  | 27 | 29.06 |  | 27
MOV4 - Certificate 2 |  |  | 12.095 |  | 9 |  | 12.095 |  | 9 |  | 12.095 |  | 9 | 12.095 |  | 9
Certificate No. 43 |  |  | 7.727 |  | 6.16 |  | 7.727 |  | 6.16 |  | 7.727 |  | 6.16 | 7.727 |  | 6.16
MOV4 - Cerficates 3A, B and C (yet to be certified) |  |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 | 13 |  | 13
Prioritised Works Milestones (excluding prelims) |  |  | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 | 22.817 |  | 22.817
Partially completed Construction Milestones |  |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 | 5.68 |  | 5.68
Milestones to Date | 0 |  | 176.399 | 6 | 167.815 | 6 | 176.399 | 6 | 167.815 | 6 | 176.399 | 6 | 167.815 | 176.399 | 6 | 167.815 | 6
BB/S Airport to Haymarket (under MOV5Infraco) - Fixed Lump Sum | 362.5 | 1
CAF Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 62.9 | 1
Haymarket to St Andrew Sq (Target Cost) | 22.5 | 1
Section 1 sub total | 447.9 |  | 176.399 |  | 167.815 |  | 176.399 |  | 167.815 |  | 176.399 |  | 167.815 | 176.399 |  | 167.815
Section 2
Remaining Infrastructure (Infraco continuation scenario) | [10 empty] | 182.706 | 8 |  | 182.706 | 8 | 182.706 | 8
New Contractor to replace Infraco | [6 empty] | 199.471 | 6 | 199.471 | 6
Section 1 + Section 2 = Infrastructure and Vehicles | 447.9 |  | 176.399 |  | 167.815 |  | 375.87 |  | 367.286 |  | 359.105 |  | 167.815 | 359.105 |  | 350.521
Section 3
INTC's agreed in full - work done |  |  | 5.295 | 6 | 5.295 | 6 | 5.295 | 6 | 5.295 | 6 | 10.375 | 7 | 10.375 | 10.375 | 7 | 10.375 | 7
INTC's agreed in full - WIP |  |  | 5.079 | 6 | 4.127 | 6 | 5.079 | 6 | 4.127 | 6
INTC's determined through adjudication - work done |  |  | 3.087 | 6 | 2.839 | 6 | 3.087 | 6 | 2.839 | 6 | 4.004 | 7 | 4.004 | 4.004 | 7 | 4.004 | 7
INTC's agreed in principle but disputed quantum |  |  | 3.62 | 6 | 2.037 | 6 | 3.62 | 6 | 2.037 | 6 | 15.832 | 7 | 12.311 | 15.832 | 7 | 12.311 | 7
INTC's dispute in principle - work done (to be done in case of attrition) |  |  | 7.381 | 6 | 4.41 | 6 | 7.381 | 6 | 4.41 | 6 | 40.376 | 7 | 21.467 | 40.376 | 7 | 21.467 | 7
EOT/Prelims |  |  | 82.176 | 6 | 54.405 | 6 | 82.176 | 6 | 54.405 | 6 | 82.176 | 6 | 54.405 | 82.176 | 6 | 54.405 | 6
Mobilisation |  |  | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 45.2 | 6 | 45.2 | 6
Additional Consequences |  |  | 5.576 | 6 | 5.576 | 6 | 5.576 | 6 | 5.576 | 6 | 5.6 | 6 | 5.6 | 5.6 | 6 | 5.6 | 6
tie claims e.g. defects |  |  | -4 | 2 | -4 | 2 | -4 | 2 | -4 | 2 | -4 | 2 | -4 | -4 | 2 | -4 | 2
Loss of Profits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 1.9 | 6 | 1.9 | 1.9 | 6 | 1.9 | 6
BSC Settlement Premium + Risk (Demob etc.) + potential further claim items |  |  | 80 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 80
Costs of Putting Project on Hold |  |  | 22.323 | 6 | 22.323 | 6 | 22.323 | 6 | 22.323 | 6 | 4.5 | 6 | 22.3 | 4.5 | 6 | 4.5 | 6
Section 1+2+3 Total Budget "Final Account" | 447.9 |  | 432.136 |  | 390.027 |  | 631.607 |  | 589.498 |  | 645.068 |  | 421.377 | 565.068 |  | 506.283
Section 4
Primary Risk | [6 empty] | 106.59 | 9 | 36.9 | 9 |  |  |  | 106.59 | 9 | 36.9 | 9
Bad Project Risk 15% of works | 77.5 | 2 |  |  |  |  | 40 | 2 | 40 | 2
Systems Risk in relation to new contractor using existing materials | [6 empty] | 10 | 2 | 10 | 2
Inflation Risk | [6 empty] | 25 | 2 | 25 | 2
Further Delay | [13 empty] | 60 | 10 | 60 | 10
Specified & Exclusion Risk | [6 empty] | 77.5 | 2 | 77.5 | 2 |  |  |  | 77.5 | 2 | 77.5 | 2
Litigation, Professional Fees |  |  | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 8 | 6 | 8 | 4 | 6 | 4 | 6
Section 4 sub total = Risk Related Items | 77.5 |  | 3 |  | 3 |  | 262.09 |  | 192.4 |  | 8 |  | 8 | 248.09 |  | 178.4
Section 5
Non BSC Costs to date (incl design) | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 239 | 3 | 239 | 3
Project Management Costs to go | 9 | 4 | 3 | 4 | 3 | 4 | 12 | 4 | 12 | 4 | 18 | 4 | 3 | 3 | 4 | 18 | 4
Site Security and Interim Works |  |  | 10 |  | 10 | [7 empty] | 20
Section 5 sub total Non BSC to Date + PM costs to go | 248 |  | 252 |  | 252 |  | 251 |  | 251 |  | 257 |  | 262 | 242 |  | 257
Sections 1+2+3+4+5 = Total Costs | 773.4 |  | 687.136 |  | 645.027 |  | 1144.697 |  | 1032.898 |  | 910.068 | + | 691.377 | 1055.158 |  | 941.683
50% of the Delta High to Low |  |  | 679.25
Notes
1. Settlement Agreement
2. Independent Certifier assessment
3. Period 2 2011/12 costs to date less Infrastructure and Vehicles
4. Assumed run rate of £3m per annum for Project Management Costs - Settlement assumes opening 2014
5. CAF certified to date from McGrigors sheet plus total to go for original contract sum
6. Source McGrigors report Separation section excluding item in note 1
7. Source McGrigors report Continue with Infraco section excluding item in note 1
8. tie assessment (Dennis Murray email 22-06-11)
9. Risk s identified at mediation from PPP that could still be apparent with a new contractor.
10. Additional Delay of one year as a result of using current contract mechanism

## Entitlement Summary
Edinburgh Tram Project
Budget Appraisal
Based on Amounts Certified to Infraco on 6th June 2011
Separation
| Settlement Agreement (High) | Mothball/Cancel Project (High) | Mothball/Cancel Project (Low) | Re-Procure (High) | Re-Procure (Low) | Unsuccessful Termination | Continue with Infraco to York Place (High) | Continue with Infraco to York Place (Low)
Milestones |  | 176.399 | 167.815 | 176.399 | 167.815 | 176.399 | 176.399 | 167.815
Mediation Heads
BB/S Airport to Haymarket Lump Sum | 362.5
CAF | 62.9
Haymarket to St Andrew Sq | 22.5
Settlement Agreement | 447.9
Remaining Infrastructure (Infraco continuation scenario) | [6 empty] | 182.706 | 182.706
New Contractor to replace Infraco |  |  |  | 199.5 | 199.5
Infrastructure Costs to go (Reprocure of Grind on) |  |  |  | 199.5 | 199.5 | 182.706 | 182.706 | 182.706
Claims |  | 255.737 | 222.212 | 255.737 | 222.212 | 285.963 | 205.963 | 155.762
Risk and Contingency | 77.5 | 3 | 3 | 262.09 | 192.4 | 8 | 248.09 | 178.4
Other Costs/Costs to Date | 248 | 252 | 252 | 251 | 251 | 257 | 242 | 257
Total | 773.4 | 687.136 | 645.027 | 1144.726 | 1032.927 | 910+ | 1055.158 | 941.683
| 773.4 | 687.136 | 645.027 | 1134.626 | 1022.827 | 745.162 | 1059.158 | 945.683
| 0 | 0 | 0 | -10.1 | -10.1 | -164.838 | 4 | 4

## McG Entitlement Basis-BBS (hidden)
Edinburgh Tram Project
Mar Hall Budget Appraisal
Based on Amounts Certified to Infraco on 6th June 2011
Separation
| Settlement Agreement |  | BBS | Mothball/Cancel Project (High) |  | Mothball/Cancel Project (Low) |  | Re-Procure (High) |  | Re-Procure (Low) |  | Unsuccessful Termination |  | Unsuccessful Termination | Continue with Infraco to York Place (High) |  | Continue with Infraco to York Place (Low)
| MOV5 entered into on or before 1.7.11, and subsequently becomes unconditional |  |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  | MOV5 not entered into on or before 1.7.11 for reasons associated with funding: automatic termination |  |  |  |  | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract |  | MOV5 not entered into on or before 1.7.11 for reasons other than funding: continue with Infraco Contract
Section 1
Milestones
Construction Milestones |  |  | 178.932 | 22.205 |  | 20.559 |  | 22.205 |  | 20.559 |  | 22.205 |  | 20.559 | 22.205 |  | 20.559
CAF - Tram Supply Milestones + to go cost |  |  | 57.3 | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 5 | 57.3 | 57.3 | 5 | 57.3 | 5
Maintenance Milestones |  |  |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 |  | 0.267 | 0.267 |  | 0.267
SDS |  |  |  | 6.248 |  | 6.032 |  | 6.248 |  | 6.032 |  | 6.248 |  | 6.032 | 6.248 |  | 6.032
MOV4 - Certificate 1 |  |  |  | 29.06 |  | 27 |  | 29.06 |  | 27 |  | 29.06 |  | 27 | 29.06 |  | 27
MOV4 - Certificate 2 |  |  |  | 12.095 |  | 9 |  | 12.095 |  | 9 |  | 12.095 |  | 9 | 12.095 |  | 9
Certificate No. 43 |  |  |  | 7.727 |  | 6.16 |  | 7.727 |  | 6.16 |  | 7.727 |  | 6.16 | 7.727 |  | 6.16
MOV4 - Cerficates 3A, B and C (yet to be certified) |  |  |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 | 13 |  | 13
Prioritised Works Milestones (excluding prelims) |  |  | 28.297 | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 |  | 22.817 | 22.817 |  | 22.817
Partially completed Construction Milestones |  |  |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 |  | 5.68 | 5.68 |  | 5.68
Milestones to Date | 0 |  | 264.529 | 176.399 | 6 | 167.815 | 6 | 176.399 | 6 | 167.815 | 6 | 176.399 | 6 | 167.815 | 176.399 | 6 | 167.815 | 6
BB/S Airport to Haymarket (under MOV5Infraco) - Fixed Lump Sum | 362.5 | 1
CAF Airport to Haymarket (under MOV5Infraco) - Remaining Costs under Fixed Lump Sum | 62.9 | 1
Haymarket to St Andrew Sq (Target Cost) | 22.5 | 1
Section 1 sub total | 447.9 |  | 264.529 | 176.399 |  | 167.815 |  | 176.399 |  | 167.815 |  | 176.399 |  | 167.815 | 176.399 |  | 167.815
Section 2
Remaining Infrastructure (Infraco continuation scenario) | [14 empty] | 182.706 | 8 | 182.706 | 8
New Contractor to replace Infraco | [7 empty] | 189.4 |  | 189.4
Section 1 + Section 2 = Infrastructure and Vehicles | 447.9 |  | 264.529 | 176.399 |  | 167.815 |  | 365.799 |  | 357.215 |  | 176.399 |  | 167.815 | 359.105 |  | 350.521
Section 3
INTC's agreed in full - work done |  |  |  | 5.295 | 6 | 5.295 | 6 | 5.295 | 6 | 5.295 | 6 | 10.375 | 7 | 10.375 | 10.375 | 7 | 10.375 | 7
INTC's agreed in full - WIP |  |  |  | 5.079 | 6 | 4.127 | 6 | 5.079 | 6 | 4.127 | 6
INTC's determined through adjudication - work done |  |  |  | 3.087 | 6 | 2.839 | 6 | 3.087 | 6 | 2.839 | 6 | 4.004 | 7 | 4.004 | 4.004 | 7 | 4.004 | 7
INTC's agreed in principle but disputed quantum |  |  |  | 3.62 | 6 | 2.037 | 6 | 3.62 | 6 | 2.037 | 6 | 15.832 | 7 | 12.311 | 15.832 | 7 | 12.311 | 7
INTC's dispute in principle - work done (to be done in case of attrition) |  |  |  | 7.381 | 6 | 4.41 | 6 | 7.381 | 6 | 4.41 | 6 | 40.376 | 7 | 21.467 | 40.376 | 7 | 21.467 | 7
EOT/Prelims |  |  |  | 82.176 | 6 | 54.405 | 6 | 82.176 | 6 | 54.405 | 6 | 82.176 | 6 | 54.405 | 82.176 | 6 | 54.405 | 6
Mobilisation |  |  |  | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 6 | 45.2 | 45.2 | 6 | 45.2 | 6
Additional Consequences |  |  | 5.6 | 5.576 | 6 | 5.576 | 6 | 5.576 | 6 | 5.576 | 6 | 5.6 | 6 | 5.6 | 5.6 | 6 | 5.6 | 6
tie claims e.g. defects |  |  | 1.089 | -4 | 2 | -4 | 2 | -4 | 2 | -4 | 2 | -4 | 2 | -4 | -4 | 2 | -4 | 2
Loss of Profits |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 1.9 | 6 | 1.9 | 1.9 | 6 | 1.9 | 6
BSC Settlement Premium + Risk (Demob etc.) + potential further claim items |  |  | 64.026 | 80 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 80
Costs of Putting Project on Hold |  |  | 22.323 | 22.323 | 6 | 22.323 | 6 | 22.323 | 6 | 22.323 | 6 | 22.3 | 6 | 22.3 | 4.5 | 6 | 4.5 | 6
Section 1+2+3 Total Budget "Final Account" | 447.9 |  | 357.567 | 432.136 |  | 390.027 |  | 621.536 |  | 579.427 |  | 480.162 |  | 421.377 | 565.068 |  | 506.283
Section 4
Primary Risk | [7 empty] | 106.59 | 9 | 36.9 | 9 |  |  |  | 106.59 | 9 | 36.9 | 9
Bad Project Risk 15% of works | 77.5 | 2 | [5 empty] | 40 | 2 | 40 | 2
Systems Risk in relation to new contractor using existing materials | [7 empty] | 10 | 2 | 10 | 2
Inflation Risk | [7 empty] | 25 | 2 | 25 | 2
Further Delay | [14 empty] | 60 | 10 | 60 | 10
Specified & Exclusion Risk | [7 empty] | 77.5 | 2 | 77.5 | 2 |  |  |  | 77.5 | 2 | 77.5 | 2
Litigation, Professional Fees BBS |  |  | 1.134 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 8 | 6 | 8 | 8 | 6 | 8 | 6
CEC |  |  | 3
Section 4 sub total = Risk Related Items | 77.5 |  | 4.134 | 3 |  | 3 |  | 262.09 |  | 192.4 |  | 8 |  | 8 | 252.09 |  | 182.4
Section 5
Non BSC Costs to date (incl design) | 239 | 3 | 239 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 3 | 239 | 239 | 3 | 239 | 3
Project Management Costs to go | 9 | 4 | 3 | 3 | 4 | 3 | 4 | 12 | 4 | 12 | 4 | 18 | 4 | 3 | 3 | 4 | 18 | 4
Site Security and Interim Works |  |  | 10 | 10 |  | 10 | [7 empty] | 20
Section 5 sub total Non BSC to Date + PM costs to go | 248 |  | 252 | 252 |  | 252 |  | 251 |  | 251 |  | 257 |  | 262 | 242 |  | 257
Sections 1+2+3+4+5 = Total Costs | 773.4 |  | 613.701 | 687.136 |  | 645.027 |  | 1134.626 |  | 1022.827 |  | 745.162 |  | 691.377 | 1059.158 |  | 945.683
50% of the Delta High to Low |  |  |  | 679.25
Notes
1. Settlement Agreement
2. Independent Certifier assessment
3. Period 2 2011/12 costs to date less Infrastructure and Vehicles
4. Assumed run rate of £3m per annum for Project Management Costs - Settlement assumes opening 2014
5. CAF certified to date from McGrigors sheet plus total to go for original contract sum
6. Source McGrigors report Separation section excluding item in note 1
7. Source McGrigors report Continue with Infraco section excluding item in note 1
8. tie assessment (Dennis Murray email 22-06-11)
9. Risk s identified at mediation from PPP that could still be apparent with a new contractor.
10. Additional Delay of one year as a result of using current contract mechanism

## Summary of Options (hidden)
Financial Comparison of Core Possible Outcomes
| Continue as is w/Silver Bullet |  | Carlisle |  |  | COWD |  | Terminate & Reprocure Now (Separation) | [7 empty] | Infraco Build to HYM | Infraco Build to HYM |  | Terminate & Postpone
| w/Silver Bullet | BSC Obstinacy | Carlisle tie price | Carlisle BSC price |  | to P11 Jan-11 (fcst Cert Feb-11) | Win litigation (Infraco Default) | Win litigation (Infraco Default) | Win litigation (Infraco Default) | Lose litigation (tie Default) | Lose litigation (tie Default) | Lose litigation (tie Default) | Settle out of court | Settle out of court | Settle out of court | Phoenix | Phoenix | Phoenix | Reprocure after winning Litigation | Reprocure after winning Litigation | Reprocure after winning Litigation | Cancel after losing litigation
| (P'fork 3C) | [5 empty] | Low | QS View | High | Low | QS View | High | Low | QS View | High | QS View | QS View | BB 'View' | Low | QS View | High
| B | C | D | E |  | A |  | F |  |  | G |  |  | H |  | Low | High |  |  | I |  | J
Infrastructure ready to operate: |  |  |  |  | Infrastructure ready to operate:
Airport to Haymarket | 2012-10-01 | 2013-12-01 | 2012-10-01 | 2013-06-01 | Airport to Haymarket | n/a | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2014-12-01 | 2014-12-01 | 2014-12-01 | n/a
Haymarket to St A Sq | 2012-10-01 | 2015-12-01 | 2013-12-01 | 2013-12-01 | Haymarket to St A Sq | n/a | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | n/a
St A Sq to FOW | 2012-10-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | St A Sq to FOW | n/a | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | n/a
FOW to Newhaven | 2012-10-01 | 2015-12-01 | 2017-12-01 | 2017-12-01 | FOW to Newhaven | n/a | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2019-12-01 | 2019-12-01 | 2019-12-01 | n/a
BB+S |  |  |  |  | BB+S
Constn Works Price (BB+S) | 239.6 | 239.6 | 180.3 | 333.9 | Constn Works Price (BB+S) | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | 68.1968 | linked
Value Engineering (included) | -6.1 | -6.1 | -11.3 | 0
Existing Change - Princes St | 9 | 9 | 9 |  | Existing Change - Princes St | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | linked
Existing Change - Other | 35.5 | 45.3 | 43.8 |  | Existing Change - Other | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | 13.0657 | linked
Existing Prolongation | 21 | 21 | 3.5
Further on-street change and disruption | 21.1 | 21.1
Further allowance for risks and delay | 20.4 | 150 | 16.5 | 40
Infrastructure (BB+S) | 340.5 | 479.9 | 241.8 | 373.9 | Entitlement for work done (BB+S) | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625 | 90.7625
[5 empty] | Certified in advance of work done (BB+S) | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | 33.2455 | linked
[5 empty] | Certified to Date (BB+S) | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008
-11.039
Infrastructure (BB+S) | 340.5 | 479.9 | 241.8 | 373.9 | Infrastructure (BB+S) Certified | 112.969 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008 | 124.008
[5 empty] | Infraco Build to Haymarket | [10 empty] | 144.763 | 144.763 | 249.892
Vehicles (CAF) | 58.5 | 58.5 | 58.5 | 60.8 | Vehicles (CAF) | 47.458 | 61.5 | 62.5 | 63.5 | 61.5 | 62.5 | 63.5 | 61.5 | 62.5 | 63.5 | 62.5 | 62.5 | 60 | 61.5 | 62.5 | 63.5 | 62.5
Design Cost Post Novation (SDS) | 5 | 14 | 14 | 15.9 | Design Post Novation (SDS) | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | linked
[5 empty] | SDS design risk | 1.029 | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 2 | 8 | 2 | 2 | 6
Total BSC | 404 | 552.4 | 314.3 | 450.6 | Total BSC | 169.456 | 195.508 | 196.508 | 201.508 | 195.508 | 196.508 | 201.508 | 195.508 | 196.508 | 201.508 | 341.271 | 341.271 | 449.9 | 195.508 | 196.508 | 201.508 | 194.508
Interim Works & Reinstatement
[5 empty] | Interim Works during Reprocure |  | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 9.893 | 0 | 0 | 0
[5 empty] | Reinstate/remedials during Reprocure |  | 1.5 | 2.5 | 5 | 1.5 | 2.5 | 5 | 1.5 | 2.5 | 5 | 2.5 | 2.5 | 2.5 | 10 | 10 | 10 | 10
[5 empty] | Reinstatement following cancellation | [16 empty] | 40
[5 empty] | Total |  | 11.393 | 12.393 | 14.893 | 11.393 | 12.393 | 14.893 | 11.393 | 12.393 | 14.893 | 2.5 | 2.5 | 2.5 | 10 | 10 | 10 | 50
New Procurement Costs |  |  |  |  | New Procurement Costs
Infrastructure - to HYM |  |  |  |  | Infrastructure - to HYM |  | 140.816 | 144.763 | 169.215 | 140.816 | 144.763 | 169.215 | 140.816 | 144.763 | 169.215 |  |  |  | 162.7305 | 167.2917 | 195.5491
Infrastructure - to SAS |  |  | 13.9 | 22.9 | Infrastructure - to SAS |  | 17.388 | 19.21 | 20.203 | 17.388 | 19.21 | 20.203 | 17.388 | 19.21 | 20.203 | 19.21 | 19.21 | 19.21 | 20.094 | 22.1996 | 23.3471
Infrastructure - to FOW |  |  | 40 | 40 | Infrastructure - to FOW |  | 30.743 | 35.121 | 36.578 | 30.743 | 35.121 | 36.578 | 30.743 | 35.121 | 36.578 | 35.121 | 35.121 | 35.121 | 35.5274 | 40.5867 | 42.2705
Infrastructure - to NHN |  |  | 20 | 20 | Infrastructure - to NHN |  | 40.297 | 45.915 | 55.991 | 40.297 | 45.915 | 55.991 | 40.297 | 45.915 | 55.991 | 45.915 | 45.915 | 45.915 | 46.5682 | 53.0605 | 64.7046
Risk allowance on new procurement |  |  | 20 | 30 | Further Risk allowance on new procurement | [13 empty] | 29 | 29 | 29
[5 empty] | Value Engineering Opportunities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 3rd Party funded (base allowed) |  | -4.3 | -4.3 | -4.3 | -4.3 | -4.3 | -4.3 | 0 | 0 | 0 | 0 | 0 | 0 | -4.3 | -4.3 | -4.3
Total New Procurement | 0 | 0 | 93.9 | 112.9 | Total New Procurement | 0 | 224.944 | 240.709 | 277.687 | 224.944 | 240.709 | 277.687 | 229.244 | 245.009 | 281.987 | 100.246 | 100.246 | 100.246 | 289.6201 | 307.8385 | 350.5712 | 0
Total Infrastructure & vehicles | 404 | 552.4 | 408.2 | 563.5 | Total Infrastructure & vehicles | 169.456 | 431.845 | 449.61 | 494.088 | 431.845 | 449.61 | 494.088 | 436.145 | 453.91 | 498.388 | 444.017 | 444.017 | 552.646 | 495.1281 | 514.3465 | 562.0792 | 244.508
Termination Costs
[5 empty] | Securing sites |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 2
[5 empty] | Third party costs (Project Termination Scenario) | [16 empty] | 14.8
[5 empty] | Total Termination Costs |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 16.8
Other Costs |  |  |  |  | Other Costs
Ph1b Payment to BSC | 3.2 | 3.2 | 3.2 | 3.2 | Ph1b Payment to BSC | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
Design Pre Nov incl Ph1b and Utilities | 28.7 | 32.3 | 32.3 | 32.3 | Design Pre Nov incl Ph1b and Utilities | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7 | 28.7
Utilties and Other Infrastructure | 78.7 | 89.9 | 89.9 | 89.9 | Utilties and Other Infrastructure | 95.208 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 100.125 | 98.925
Project Costs | 91.5 | 109.5 | 94.2 | 94.2 | Project Costs - to date | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156 | 74.156
Project Costs - Post Termination |  |  |  |  | Project Costs - to go |  | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 28.2 | 23.2 | 23.2 | 23.2 | 27.7 | 27.7 | 27.7 | 8.6
Other Costs - Incl Land | 33.8 | 33.8 | 33.8 | 33.8 | Other Costs - Incl Land | 35.234 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973 | 36.973
Other Costs | 235.9 | 268.7 | 253.4 | 253.4 | Other Costs | 236.498 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 271.354 | 266.354 | 266.354 | 266.354 | 270.854 | 270.854 | 270.854 | 250.554
Gross Outturn Costs | 639.9 | 821.1 | 661.6 | 816.9 | Gross Outturn Costs | 405.954 | 705.199 | 722.964 | 767.442 | 705.199 | 722.964 | 767.442 | 709.499 | 727.264 | 771.742 | 710.371 | 710.371 | 819 | 772.4821 | 791.7005 | 839.4332 | 511.862
Highly Sensitive Variable Elements
Gross Outturn Costs
[5 empty] | General and Specifc Scope Risk + Exclusions | [10 empty] | 39.6 | 106.6
[5 empty] | Infraco Avoidance and Loss of Profit | [12 empty] | -3.9
[5 empty] | Bond call (BB+S) |  | -25 | -25 | -25 | -10 | -10 | -10 | -10 | -10 | -10 | 0 | 0 | 0 | -25 | -25 | -25 | -25
[5 empty] | BSC - Settlement Premium |  | 2017-12-01: 10; 2017-12-01: 10; 2017-12-01: 10 | 0 | 0 | 0
[5 empty] | Vehicles - Lease / Sale recoveries |  | -10.5 | -10.5 | 0 | -10.5 | -10.5 | 0 | -10.5 | -10.5 | 0 | 0 | 0 | 0 | -13.5 | -13.5 | -13.5 | -46.8
[5 empty] | Vehicles - Lease / Sale recoveries - Ops Stripped back out |  | 2017-12-01: 10.5; 2017-12-01: 10.5; 2017-12-01: 0
[5 empty] | Re-Design (risk of SDS not completing) |  | 5 | 10 | 15 | 5 | 10 | 15 | 5 | 10 | 15 | 10 | 10 | 10 | 15 | 15 | 15
[5 empty] | tie litigation & professional costs |  | 30 | 30 | 30 | 30 | 30 | 30 | 2 | 3 | 4 | 3 | 3 | 3 | 30 | 30 | 30 | 30
[5 empty] | BSC Loss of profits in case of tie default |  | 5: 35; 10: 35; 15: 35 | [6 empty] | 35
[5 empty] | BSC Litigation Costs |  | 5: 30; 10: 30; 15: 30 | [6 empty] | 30
[5 empty] | Recovery in case of Infraco Default |  | 5: -67.72; 10: -47.72; 15: -23.86 |  |  |  | -67.72 | -47.72 | -23.86
[5 empty] | Sub-total HS Variable Elements |  | -68.22 | -43.22 | -3.86 | 79.5 | 84.5 | 100 | 7 | 13 | 19 | 52.6 | 119.6 | 9.1 | 6.5 | 6.5 | 6.5 | 23.2
Total Phase 1a | 639.9 | 821.1 | 661.6 | 816.9 | Total Phase 1a | 405.954 | 636.979 | 679.744 | 763.582 | 784.699 | 807.464 | 867.442 | 716.499 | 740.264 | 790.742 | 762.971 | 829.971 | 828.1 | 778.9821 | 798.2005 | 845.9332 | 535.062
Incremental Options |  |  |  |  | Incremental Options
[5 empty] | Summary of Positions |  | Low | QS view | High | Low | QS view | High | Low | QS view | High | QS view | QS view | QS view | Low | QS view | High
[5 empty] | Sub-total - Newhaven |  | 636.979 | 679.744 | 763.582 | 784.699 | 807.464 | 867.442 | 716.499 | 740.264 | 790.742 | 762.971 | 829.971 | 828.1 | 778.9821 | 798.2005 | 845.9332
[5 empty] | Sub-total - Foot of the Walk |  | 596.682 | 633.829 | 707.591 | 744.402 | 761.549 | 811.451 | 676.202 | 694.349 | 734.751 | 717.056 | 784.056 | 782.185 | 732.4139 | 745.14 | 781.2286
[5 empty] | Sub-total - St Andrews Square |  | 565.939 | 598.708 | 671.013 | 713.659 | 726.428 | 774.873 | 645.459 | 659.228 | 698.173 | 681.935 | 748.935 | 747.064 | 696.8865 | 704.5533 | 738.9582
[5 empty] | Sub-total - Haymarket |  | 548.551 | 579.498 | 650.81 | 696.271 | 707.218 | 754.67 | 628.071 | 640.018 | 677.97 | 662.725 | 729.725 | 727.854 | 676.7925 | 682.3537 | 715.6111
Notes:
It is assumed that the ETP will be completed in the incremental options and therefore, for the purpose of optioneering "recovery for Infraco default" is assumed
Note on B13: SMcGarrity: CWP £238.6m Less: Prov Sums 3rd party funded £3.1m Less: Target savings on Prov Sums (Picardy) £3.0m Add: Contingency for non VE delivery £1.2m Add £6.1m VE forecast
Note on B16: SMcGarrity: Design Development £14.1m Ground Conditions £9.9m Cleint & Other changes £11.5m NB All based on QS view of change register as it stood back in March 2010 at time of Pitchfork 1
Note on B17: SMcGarrity: Per DM workings attached to 16/3/ email - includes EOT1 agreed
Note on B18: SMcGarrity: On-street scope changes £9.9m On-street dealy and dusruption £8.2m Risk re OSSA credit £3m Assumes no premium costs which would be associated with doing remaining on-street under an OSSA similar to PSSA See DM email to SMcG of 6/3 and SMcG powerpoint analysis of option 3c
Note on B19: SMcGarrity: 4mth Delay to start on street £4m (see DM workings attached to 16/3 email) Further Delay allowance £12.1m (as above) VE Deliverability £4.3m
Note on B20: SMcGarrity: Pitchfork was based upon the Change Register(s) and QS view extant back in March 2010. I dont think it would move around by more than a few £m +/_ but we need to keep an eye on reconciliation to the current reported QS view!
Note on B57: SMcGarrity: See seprate tab which reconciles what was included in P'fork 3C (£78.7m) compared to whats getting reported as AFC now (£89.9m) - needs watching as MUDFA final account settled.
Note on B58: SMcGarrity: See Project Costs tab - forecast to Feb 12 = £87.5m plus £0.5m per month for prolongation to Oct 2012 = £91.5m.
Note on C19: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years prelims for BSC = £80m plus estimate for on street premium costs £40m plus movement to top end of on-street design = £30m.
Note on C27: SMcGarrity: Assumes we'd end up haing to pay them the £14m design costs as per Carlisle 'Explantory Note'
Note on C58: SMcGarrity: Not capable of being estimated with any certainty but included an additional 3 years at £500k per month on top of the Sillver Bullet scenario. Big factor would be the Commercial/DRP costs associated with toughing it out issue by issue.
Note on E20: SMcGarrity: Recon to tie Carlisle offer for 'Part A' as per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on E42: SMcGarrity: Allowance for market uncertainties in procurement and subsequent retained risk - final amount would be an output from a formal QRA.
Note on E45: SMcGarrity: Recon to Carlisle "Explanatory Note" per my email 'HANDOVER - Cost Estimates - Carlisle tie Price' of 7/11.
Note on E58: SMcGarrity: Aggregate Project Costs assumed materially the same as the term & reprocurement option in aggregate.
Note on F13: SMcGarrity: From BSC revised proposal dated 12/9/10 - BB £215.3m plus Siemens £118.8m to Haymarket only.
Note on F19: SMcGarrity: Draft terms from BSC fall well short of a genuine GMP. Also would need to pick up the pieces on Princes st defects and figure out who is taking responsibility for Princes St. Final amount would be an output from a formal QRA.
Note on F26: SMcGarrity: CAF price including storage costs from BSC revised proposal dated 12/9/10.
Note on I20: SMcGarrity: As estimated by DM at end P8 Cert - see tab included.
Note on I22: SMcGarrity: As certified end P9
Note on I24: SMcGarrity: BB+S per Latest AFC sheet Less Post Novation design £5.7m (see below)
Note on L38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on L70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on L76: Assumption taken currently that 20% of CWP is recoverable with Infraco Default scenario. Legal view to confirm if this is the case or whether or not the full construction cost would apply. If building incrementally is this pro-rata? Low £236.8m CWP + £100m change * 20% Medium £236.8m CWP * 20% High £236.8m/2 * 20%
Note on N57: See Latest AFC reconciliation sheet. Includes £3m contingency and £3m tax
Note on N58: SMcGarrity: See tab for Project Costs
Note on N59: SMcGarrity: See tab for Project Costs
Note on N60: Gregor Roberts: see latest AFC worksheet
Note on O38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on O44: TP cost forecast P8: Fports: BP Rd £0.6m; LRd £2.2m; OT £0.5m; Tow Pl £0.1m & RBS £0.4m
Note on O68: Gregor Roberts: assumes £10m bond call appropriate in lose situation for Princes St defective works
Note on O70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on Q44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on R20: SMcGarrity: As estimated by DM at end P6 Cert - see tab included. Will need to be updated to date of termination but on the basis they stopped work in Oct and we're not paying prelims it should not move a lot?
Note on R32: SMcGarrity: Placemaker - assuming its legal, honest and decent to engage with existing subbies, and CEC are happy with exposure (ie we are not going to canx) - we assume there will be works which it will be good VfM to do works (especially at Depot and other bits off-street) between termination and new procurement. DM updated view is hat this will be no more than £10m maximum. Pricing has now been finalised and any value taken off the "to go" element
Note on R33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on R38: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on R44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on R69: SMcGarrity: Highly uncertain what BSC would walk away for - assume here they'd want the bond call back plus something for their trouble. Very hard to prove VfM except against what it avoids (uncertain litigation, protracted uncertainty as to financial outcome) . Additional £10m included, which would take our assessment of value premium to c£45m
Note on R70: SMcGarrity: Assumes best option is we take CAF contract back then lease surplus vehicles (with maintenance) we dont need for Apt to SAS (10 of) for 10 yrs at a yield of 7.5% pa ie £150k per tram per year for 7 years. Take the trams back after 7 years to operate to Newhaven. Pricing subject to proper professional advice and negotiation. Option to sell also a possibility. Both need TS endorsement.
Note on R73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on S44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on U25: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on U32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on U33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on U38: Assumed that BB are able to build in-line with CWP+Changes+EoT+Escalation
Note on U44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on U50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on U70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on U73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on V25: Figures for all scenarios taken from DM ranging documents "Cost of Completion" sheets as at 02/12/10. Incremental differences to totals noted on sheets. Key to note is that for infrastructure we have included 10% risk against IFC drawings, plus an additional 5% view for risk. To be confirmed with Engineering if this is an appropriate allowance. Prelims allowed within the ranges are: 22.5% (low); 27.5% (medium); 35% (high) of direct build costs. Advice from Cyril Sweet suggested that a circa15-20% allowance was adequate. We have taken the mid-range as Infraco prelims allowances are 30% systems and 35%
Note on V32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on V33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on V38: Assumed that BB are able to build in-line with CWP+Changes+EoT+Escalation
Note on V44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on V50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on V70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on V73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on W25: Includes Infraco Price £333.9m (Infraco Carlisle Offer) +£40m further risk for behaviour and lack of change in contract less Value certified to Date
Note on W32: no cost for Interim works as assumption that Infraco progress works and make good any works partially completed as part of Phoenix
Note on W33: Remedial Works current range £1.5-5m. £2.42m as being the most reasonable. DM suggestion for prudency we show a range of 1.5 – 2.5 – 5m
Note on W44: Phoenix position is that 3P funding currently at risk, so omitted from overall cost view, The £4.3m 3rd party funding element has been excluded from the cost calculations
Note on W50: site security costs not required for Phoenix as works will progress as soon as there is a mediated agreement
Note on W70: assumed no leasing recoveries. Reclassified as operational rather than Capital Build
Note on W73: additional professional fees resource to complete factual matrix and preparing for litiagation
Note on Y59: SMcGarrity: Additional 2 yrs prolongation and escalation - say £5m
Note on Z33: SMcGarrity: Assumes that if we are doing nothing till litigation is over the cost of required interim reinstatement will be considerably higher.
Note on Z38: Gregor Roberts: DM view of new procurement costs with 7.5% compound interest for 2 years
Note on Z50: Assumed securing sites cost will be £2m per annum for 3 yrs
Note on Z51: TP cost forecast P8: Fports: BP Rd £0.6m; LRd £2.2m; OT £0.5m; Tow Pl £0.1m & RBS £0.4m (contingency range £-,£1m or £2m
Note on Z59: SMcGarrity: Additional 2 yrs prolongation and escalation - say £5m
Note on Z70: SMcGarrity: Additional 2 year lease income - this assumes 17 trams doing nothing for a considerable preiod of time.
Note on Z76: Assumption taken currently that 20% of CWP is recoverable with Infraco Default scenario. Legal view to confirm if this is the case or whether or not the full construction cost would apply. If building incrementally is this pro-rata? Low £236.8m CWP + £100m change * 20% Medium £236.8m CWP * 20% High £236.8m/2 * 20%
Note on AB34: SMcGarrity: Very uncertain - placemarker only.
Note on AB51: 3rd party costs higher in this instance due to blight claims (+£10m)
Note on AB57: SMcGarrity: Wouldnt do the utilities at Baltic street if you're Canx
Note on AB70: SMcGarrity: Assumes 80% recovery on cost

## Separation (hidden)
Options Considered | tie Separation Position £m | Likely BSC Separation offer
Non-BSC Costs to Date (a) | 236.5
SDS (Post Novation Design) Costs to Date (b) | 9
CAF (b) | 47.5
BB+S Spend to Date (b) | 113
BB+S COWD accounting adjustment ‘to go’ (f) | 11
Sub-total Spend to Date (P11 2010/11) | 417
Non BSC Project Costs ‘to Go’ (c) | 34.9
Non BSC Construction Costs to Haymarket (d) | 123.8
Non BSC Construction Costs ‘to Go’ (HYM to SAS) (d) | 19.2
Non BSC ‘Other Costs ‘to Go’ (e) | 14.4
Other highly variable costs (g) | 13
Sub-total-Non BSC Costs ‘to Go’ | 205.3
CAF, SDS Cost ‘to Go’ (f) | 16
Add Back Differential of Evaluation vs. Cash | -33.2
Other Entitlements | 19
Settlement Premium
Total | 624.1

## Optioneering (hidden)
COMMERCIALLY SENSITIVE - FOISA EXEMPT
Airport to St Andrews Square
Risk
| Base Cost | Notes | Low | High | Description
Phoenix | 635.3 | 1
|  |  | 62 |  | High side Risk and Exclusions
|  |  | 4.8 |  | GHP HAY to SAS additional
|  |  | 702.1 | 817.4
| Base Cost | Notes | Low | High | Description
Phoenix (BSC Only) | 377.4 | 1
|  |  | 77 |  | High side Risk and Exclusions
454.4
Separation | 624.1 |  | Low | High
|  |  | 43.2 | 33.2 | Add Back Premium (+ 10 for subbies)
|  |  |  | 50 | Settlement Risk
|  |  | 6 | 6 | High Side Design and Professional Costs
|  |  | 22 | 43 | Bad Project Risk (High Side Risk c30% of AIR - SAS Reprocure) low view (15%)
|  |  | 10 | 25 | Siemens Risk on Systems Reprocurement
|  |  | 15 | 25 | Inflation Risk (5% of contract value of work to do over 3 years)
|  |  | 720.3 | 806.3
Attrition | 867 | 2 |  |  | There is an "x" number on this scenario that is very hard to quantify as a result of on going dispute, legal and delay costs.
867
1. tie low side view as base point
2. Deck chair tie default scenario (High)
Agreed In Principle
Area of disagreement
Agree to Agree, the numbers are highly variable