## P80 Risk Allocation 1A+1B
EDINBURGH TRAM PROJECT | [106 empty] | 2026-07-29
P80 Risk Allocation Report
Current Period End | 2008-03-01 | [52 empty] | Total Allocation | £k
[50 empty] | Risk Mean Sum |  |  |  | Phase 1A | Phase 1B
Sim Run P80 1A+1B | 28596 | £k | [47 empty] | 21407.3799 | £k |  |  | 25927.2097 | 2668.7903 | £k
WBS Item | Allocated Risks |  |  |  | Impact Assessment 08 Feb 2008 |  |  |  | Exposure Period | [39 empty] | No of Periods | Sim Run Risk Mean | P80 Risk Allocation |  | Proportion allocated to 1A | P80 Risk Allocation 1A | P80 Risk Allocation 1B | P80 Value Per Period | total P80 | [38 empty] | Utilised for Risk Exposure
| Risk ID | Cause | Risk Event | Effect | Prob | Current Impact Assessment £k |  |  | Start | End | [37 empty] | Construction End | [11 empty] | 2008/09 | [12 empty] | 2009/10 | [12 empty] | 2010/11 | [8 empty] | Construction Programme End |  | QUANTITATIVE RISK CALCULATIONS
[5 empty] | % | Min | Most Likely | Max |  |  | 2008-03-01 | 2008-03-31 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 |  | £k | £k |  |  |  |  | £k |  | 2008-03-01 | 2008-03-31 | 2008-04-26 | 2008-05-24 | 2008-06-21 | 2008-07-19 | 2008-08-16 | 2008-09-13 | 2008-10-11 | 2008-11-08 | 2008-12-06 | 2009-01-03 | 2009-01-31 | 2009-02-28 | 2009-03-31 | 2009-04-25 | 2009-05-23 | 2009-06-20 | 2009-07-18 | 2009-08-15 | 2009-09-12 | 2009-10-10 | 2009-11-07 | 2009-12-05 | 2010-01-02 | 2010-01-30 | 2010-02-27 | 2010-03-31 | 2010-05-01 | 2010-05-29 | 2010-06-26 | 2010-07-24 | 2010-08-21 | 2010-09-18 | 2010-10-16 | 2010-11-13 | 2010-12-11 | 2011-01-08 | £k | Risk Distribution | Sim Run Risk Mean | Probability | Reverse Probability | Most Likely | No Impact | Cost @Risk | No Impact | Overall Contingency
11.1 Construction | 994 | The design for the lighting has yet to be approved by CECs Street Lighting section | Additional time or cost could be incurred in relation to the street lighting works | Compliance with their requirements may incur abortive works resulting in additional cost and delay to programme | 17.5 |  | 12.5 |  | 2007-08-29 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2.1875 | 2.9221 |  | 80 | 2.3377 | 0.58441 | 0.25974 | 2.3377 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0.25974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.175 | 0.825 | 12.5 | 0 | #NAME? | 0 | #NAME? | Design & Consents
2 PROCUREMENT CONSULTANT | 44 | SDS contractor does not deliver the required prior approval consents before novation | Late prior approval consents | Delay to programme with additional resource costs and delay to Infraco. procurement. Impact upon risk balance. | 50 | 900 | 1800 | 2700 | 2006-06-30 | 2008-11-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 902.4433 | 1205.4846 |  | 90 | 1084.9362 | 120.5485 | 108.4936 | 1084.9362 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 108.4936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.5 | 0.5 | 1800 | 0 | #NAME? | 0 | #NAME? | Design & Consents
3 DESIGN | 336 | Adequate scope and extent of noise and vibration prevention measures/requirements are not provided to SDS; Specifications relating o Tram noise provided by Tramco are optimistic. | Design assumptions lead to Tram noise and vibration measures being inadequate during operation | Tram design requires to be re-worked; Post construction elements need to be adjusted or re-constructed or additional noise and vibration measures need to be incorporated. | 10 | 100 |  | 1000 | 2007-01-01 | 2011-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38 | 55.94 | 74.7247 |  | 80 | 59.7797 | 14.9449 | 1.5732 | 59.7797 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 | 1.5732 |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME? | Design & Consents
5 PARLIAMENTARY PROCESS/ APPROVALS | 271 | Inadequate quality of submission of approval. Partial submission of package. Programme compression. Lack of CEC resources. | Failure to process prior approvals applications within 8 weeks | Delay and disruption to Infraco programme | 80 | 750 | 750 | 1000 | 2006-01-03 | 2008-08-29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 666.6743 | 890.5443 |  | 100 | 890.5443 | 0 | 127.2206 | 890.5443 | 127.2206 | 127.2206 | 127.2206 | 127.2206 | 127.2206 | 127.2206 | 127.2206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.8 | 0.2 | 750 | 0 | #NAME? | 0 | #NAME? | Design & Consents
5 PARLIAMENTARY PROCESS/ APPROVALS | 990 | SDS are behind programme with design review certificates and tie have decided not to extend programme period to account for this. | CEC carry financial impact of uncertified designs provided to Infraco | Modifications required to the designs post-contract award resulting in additional costs | 50 | 500 | 750 | 1000 | 2007-08-13 | 2008-05-31 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 376.3107 | 502.6763 |  | 80 | 402.141 | 100.5353 | 100.5353 | 402.141 | 100.5353 | 100.5353 | 100.5353 | 100.5353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.5 | 0.5 | 750 | 0 | #NAME? | 0 | #NAME? | Design & Consents
7.3 Infraco | 279 |  | Third party consents including Network Rail, CEC Planning, CEC Roads Department, Historic Scotland, Building Fixing Owner consent is denied or delayed | Delay to programme; Risk transfer response by bidders is to return risk to tie; Increased out-turn cost if transferred and also as a result of any delay due to inflation. | 50 |  | 1250 |  | 2006-07-03 | 2009-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 625 | 834.8756 |  | 90 | 751.3881 | 83.4876 | 31.3078 | 751.3881 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 31.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.5 | 0.5 | 1250 | 0 | #NAME? | 0 | #NAME? | Design & Consents
1 GENERAL/OVERALL | 169 | Concurrent major projects in Edinburgh | Other major projects in Edinburgh interface with Tram | Delay in sequence in certain areas, Additional interface project management costs. | 50 | 100 | 300 | 500 | 2007-03-01 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 37 | 149.9927 | 200.3604 |  | 80 | 160.2883 | 40.0721 | 4.3321 | 160.2883 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 4.3321 | 0 |  | TRIANG | #NAME? | 0.5 | 0.5 | 300 | 0 | #NAME? | 0 | #NAME? | General Programme Delay
1.7 Miscellaneous | 343 | General delay to programme with various causes e.g. failure to obtain approvals on time; parliamentary processes, delays due to lack of prioritisation of BAA agreement with new owners | Delay to completion of project | Inflation at 5% causes increased out-turn cost due to delay plus revenue loss | 40 | 6000 | 12000 | 18000 | 2010-12-31 | 2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4921.4109 | 6574.0257 |  | 80 | 5259.2205 | 1314.8051 | 5259.2205 | 5259.2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5259.2205 |  | TRIANG | #NAME? | 0.4 | 0.6 | 12000 | 0 | #NAME? | 0 | #NAME? | General Programme Delay
7.1.3 Depot | 974 | Inaccurate Topo Survey results | Increase in levels of Spoil Excavation | Increased Cost & Programme extension | 25 | 100 | 300 | 500 | 2007-05-14 | 2008-08-24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 74.2774 | 99.2198 |  | 100 | 99.2198 | 0 | 14.1743 | 99.2198 | 14.1743 | 14.1743 | 14.1743 | 14.1743 | 14.1743 | 14.1743 | 14.1743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.25 | 0.75 | 300 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.1.3 Depot | 981 | Existing Spoil Site Unable to accept future spoil | Increase in the Lothian Valuation Joint Board rateable value of the spoil site | New Landfill site will have to be found and agreements reached. Possibility of increased costs | 80 | 0 | 25 | 50 | 2007-07-19 | 2008-03-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20.0521 | 26.7856 |  | 100 | 26.7856 | 0 | 13.3928 | 26.7856 | 13.3928 | 13.3928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.8 | 0.2 | 25 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.1.3 Depot | 876 | Agreement with SEPA to use Gravity Drain Proposal | Gravity Drain Proposal | Cost & time saving | 79.5 | 12.5 | 12.5 | 12.5 | 2008-03-19 | 2008-07-08 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9.9375 | 13.2745 |  | 100 | 13.2745 | 0 | 3.3186 | 13.2745 | 0 | 3.3186 | 3.3186 | 3.3186 | 3.3186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.795 | 0.205 | 12.5 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 952 | Scope of works relating to Wide Area Modelling (WAM) have not been agreed with SDS because they consider this to be out with the scope of their contract. | Uncertainty about extent of construction works required on road network relating to Wide Area Modelling issues. | Potential claim from SDS to deal with additional design work; Potential construction costs to deal with WAM issues (difficult to quantify without design) over and above those already included. | 95 | 0 |  | 3000 | 2006-07-03 | 2008-09-24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1431.2919 | 1911.9211 |  | 100 | 1911.9211 | 0 | 238.9901 | 1911.9211 | 238.9901 | 238.9901 | 238.9901 | 238.9901 | 238.9901 | 238.9901 | 238.9901 | 238.9901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.95 | 0.05 | 0 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 931 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; known redundant utilities; unknown live utilities; unknown redundant utilities. | Unknown or abandoned assets impacts scope of Infraco work | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 90 | 500 |  | 1000 | 2007-10-01 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 675.2304 | 901.9734 |  | 80 | 721.5787 | 180.3947 | 22.5493 | 721.5787 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 22.5493 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 172 | Area of possible contamination and unstable ground (unlicensed tip) has been highlighted during desk study immediately to east of Gogar Burn - investigation for CERT project indicates that this consists of building rubble and domestic waste. | Tramway runs through area of possible contamination and special foundation is required to cope with unstable ground | Increase in costs to provide special foundation solution | 95 | 100 | 200 | 300 | 2007-01-01 | 2008-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 189.837 | 253.5845 |  | 100 | 253.5845 | 0 | 42.2641 | 253.5845 | 42.2641 | 42.2641 | 42.2641 | 42.2641 | 42.2641 | 42.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.95 | 0.05 | 200 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 105 | Encountering archaeological finds/burials/munitions during construction | Exhumation of archaeological finds/burials | Delay in construction programme | 85 | 0 | 150 | 500 | 2007-09-28 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 184.5265 | 246.4906 |  | 90 | 221.8416 | 24.6491 | 6.9325 | 221.8416 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 6.9325 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.85 | 0.15 | 150 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 318 | Failure to make arrangements with Utilities for the phasing of necessary connections; Utility Company operational constraints | Utility connections cannot proceed as planned | Potential delay to start of Infraco works in certain sections | 50 | 100 |  | 500 | 2007-04-04 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 149.731 | 200.0108 |  | 80 | 160.0087 | 40.0022 | 12.3084 | 160.0087 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 12.3084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.5 | 0.5 | 0 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 173 | Uncertainty over extent of contaminated land/hazardous materials on route | Tramway runs through area of previously unidentified contamination/hazardous materials and material requires to be removed and replaced (dig and dump). | Increase in costs to remove material to special and other tip. | 50 | 1500 | 6000 | 8000 | 2006-09-29 | 2010-07-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2585.6117 | 3453.8628 |  | 90 | 3108.4765 | 345.3863 | 97.1399 | 3108.4765 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 97.1399 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.5 | 0.5 | 6000 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
7.3 Infraco | 865 | Buildings contain asbestos that was not uncovered during surveys | Asbestos found during demolition works and excavations for construction | Cost and delay during investigation and removal | 90 | 60 |  | 150 | 2008-01-01 | 2009-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 94.5328 | 126.2771 |  | 80 | 101.0216 | 25.2554 | 6.7348 | 101.0216 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 6.7348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.9 | 0.1 | 0 | 0 | #NAME? | 0 | #NAME? | Infraco Delivery
1.1 Land & Property | 352 | Increase in land values | Higher land compensation claims than anticipated | Additional uplift on compensation claims | 30 | 0 |  | 4500 | 2007-03-05 | 2010-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 37 | 688.4925 | 919.689 |  | 100 | 919.689 | 0 | 24.8565 | 919.689 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 24.8565 | 0 |  | UNIFORM | #NAME? | 0.3 | 0.7 | 0 | 0 | #NAME? | 0 | #NAME? | Land compensation
1.1 Land & Property | 10 | Costs of obtaining access rights are unknown | Cost associated with obtaining wayleaves | Increased legal costs relating to obtaining wayleaves | 40 | 50 | 200 | 500 | 2007-04-02 | 2008-10-25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 99.8032 | 133.3172 |  | 100 | 133.3172 | 0 | 14.813 | 133.3172 | 14.813 | 14.813 | 14.813 | 14.813 | 14.813 | 14.813 | 14.813 | 14.813 | 14.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.4 | 0.6 | 200 | 0 | #NAME? | 0 | #NAME? | Land compensation
7.2 MUDFA/Utilities | 164 | Utilities assets uncovered during construction that were not previously accounted for; unidentified abandoned utilities assets; asbestos found in excavation for utilities diversion; unknown cellars and basements intrude into works area; other physical job | Unknown or abandoned assets or unforeseen/contaminated ground conditions affect scope of MUDFA work. | Re-design and delay as investigation takes place and solution implemented; Increase in Capex cost as a result of additional works. | 95 | 1000 | 3000 | 6000 | 2007-04-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 3163.8819 | 4226.3166 |  | 95 | 4015.0008 | 211.3158 | 365.0001 | 4015.0008 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 365.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.95 | 0.05 | 3000 | 0 | #NAME? | 0 | #NAME? | MUDFA
7.2 MUDFA/Utilities | 139 | Utilities diversion outline specification only from plans | Uncertainty of Utilities location and consequently required diversion work/ unforeseen utility services within LoD | Increase in MUDFA costs or delays as a result of carrying out more diversions than estimated | 90 | 0 | 1200 | 2400 | 2007-04-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1082.1482 | 1445.5346 |  | 95 | 1373.2579 | 72.2767 | 124.8416 | 1373.2579 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 124.8416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.9 | 0.1 | 1200 | 0 | #NAME? | 0 | #NAME? | MUDFA
7.2 MUDFA/Utilities | 342 | Tram alignment at A8 crossing at Gogar co-incides BT data nests/cable (main coms link between Glasgow and Edinburgh) and sewer | A8 crossing tunnel requires special design or BT data nest/cables require to be moved or solution to sewer to be engineered |  | 80 | 1000 | 1250 | 1500 | 2007-04-04 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 999.4555 | 1335.0737 |  | 100 | 1335.0737 | 0 | 166.8842 | 1335.0737 | 166.8842 | 166.8842 | 166.8842 | 166.8842 | 166.8842 | 166.8842 | 166.8842 | 166.8842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.8 | 0.2 | 1250 | 0 | #NAME? | 0 | #NAME? | MUDFA
7.2 MUDFA/Utilities | 914 | Required approval/acceptance turnaround time does not reflect SUC standard practice; SUCs do not have enough resource or process capability to achieve 20 day turnaround | Statutory Utility Companies unable to meet design approval/acceptance turnaround time to meet programme | Additional period required for design approval/acceptance turnaround | 95 |  | 880 |  | 2007-03-02 | 2008-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 836 | 1116.7297 |  | 95 | 1060.8932 | 55.8365 | 96.4448 | 1060.8932 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 96.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.95 | 0.05 | 880 | 0 | #NAME? | 0 | #NAME? | MUDFA
7.2 MUDFA/Utilities | 911 | Scottish Power own and maintain a cable tunnel in the vicinity of Leith Walk that may or may not interfere with Tram construction and operation; exact location and depth of tunnel is unknown; condition of tunnel is unknown. | Presence of Scottish Power tunnel in Leith Walk requires radical solution | Tunnel may have to be decommissioned and re-laid in a more suitable location; tram alignment may require to be adjusted; special foundation solution e.g. cantilever may be required; increased capex; potential for tunnel collapse during operation and | 80 | 400 | 500 | 600 | 2007-04-02 | 2008-10-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 400.0259 | 534.355 |  | 100 | 534.355 | 0 | 59.3728 | 534.355 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 59.3728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.8 | 0.2 | 500 | 0 | #NAME? | 0 | #NAME? | MUDFA
1.3.1 NR Immunisation Project | 932 | Information handed over in draft format as part of continual design development; Downstream Tram design change that impacts on requirements; Zone of interference not defined adequately. | SDS gives wrong or insufficient information to Network Rail | Network Rail design their works inappropriately for final Tram requirements; Network Rail are unable to complete their design in time to meet programme; Cost to change design; Delay during redesign; Final works are not suitable and consequently Tram canno | 5 | 100 | 300 | 500 | 2007-04-02 | 2009-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15.0599 | 20.1171 |  | 100 | 20.1171 | 0 | 0.91441 | 20.1171 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0.91441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.05 | 0.95 | 300 | 0 | #NAME? | 0 | #NAME? | Network Rail
7.3 Infraco | 134 | Network Rail possessions over and above that estimate are required | Compensation paid to Train Operating Companies | Increased compensation paid to Train Operating Companies | 5 | 500 | 2000 | 4000 | 2007-10-01 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 111.3972 | 148.8045 |  | 100 | 148.8045 | 0 | 11.4465 | 148.8045 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 11.4465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.05 | 0.95 | 2000 | 0 | #NAME? | 0 | #NAME? | Network Rail
7.3 Infraco | 115 | Network Rail cancels planned possessions | Planned work at interface with Network Rail is delayed | Time delay and resulting cost increase | 10 | 350 | 750 | 2000 | 2007-10-01 | 2009-01-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 102.4166 | 136.8082 |  | 100 | 136.8082 | 0 | 10.5237 | 136.8082 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 10.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.1 | 0.9 | 750 | 0 | #NAME? | 0 | #NAME? | Network Rail
11.1 Construction | 993 | Due to a terrorism event relating to Edinburgh Airport or due to the mitigation of the risk of such an event occurring traffic restrictions introduced in the vicinity of the airport cause unacceptable delays for vehicles accessing and exiting from the sit | Free access cannot be guaranteed to the P&R site | Delays to construction vehicles could have impact on completion date and cost of construction, delays for car park users or buses could detract from usefulness and viability of facility | 2.5 |  | 12.5 |  | 2007-10-01 | 2009-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.3125 | 0.41744 |  | 100 | 0.41744 | 0 | 0.027829 | 0.41744 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0.027829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.025 | 0.975 | 12.5 | 0 | #NAME? | 0 | #NAME? | Other
2 PROCUREMENT CONSULTANT | 337 | Unsuccessful tenderer challenges procurement process (Tramco or Infraco) | OJEU procurement process is challenged | Possible retender; Delays; Legals costs to deal with challenge | 5 | 0 |  | 100 | 2007-01-12 | 2008-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2.6633 | 3.5577 |  | 100 | 3.5577 | 0 | 0.3953 | 3.5577 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0.3953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME? | Other
2 PROCUREMENT CONSULTANT | 76 | Introduction of TEL as client | Change of client during works | Delay and cost during re-negotiation of DPOF contract and additional approvals process | 5 | 12.5 |  | 12.5 | 2006-07-03 | 2008-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.625 | 0.83488 |  | 80 | 0.6679 | 0.16698 | 0.074211 | 0.6679 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0.074211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.05 | 0.95 | 0 | 0 | #NAME? | 0 | #NAME? | Other
2.1 tie Resources | 58 | Poor performance (quality) by Infraco during construction; poor materials; latent defects | Infraco fails to deliver construction quality; latent defects occur during or after Infraco maintenance period | Rework, stakeholder criticism, negative PR, programme delay if quality issue occurs during construction, operations affected by rework, project management costs to deal with issues | 10 | 25 | 62.5 | 100 | 2010-12-31 | 2016-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6.2115 | 8.2974 |  | 80 | 6.6379 | 1.6595 | 6.6379 | 6.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6379 |  | TRIANG | #NAME? | 0.1 | 0.9 | 62.5 | 0 | #NAME? | 0 | #NAME? | Other
2.2 Transdev | 888 | Design, construction and/or testing does not meet Transdev requirements and gain approval from the ROGS Competent Person | Transdev refuse to operate system on safety ground or apply overly restrictive procedures that are not directly the responsibility of Infraco (ROGS Competent Person agrees with this) | Delay to commencement of service, additional cost both for delay and rectification of the issue | 2 | 3000 | 4500 | 6000 | 2009-06-30 | 2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 19 | 91.2031 | 121.8292 |  | 80 | 97.4634 | 24.3658 | 5.1297 | 97.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 5.1297 | 0 |  | TRIANG | #NAME? | 0.02 | 0.98 | 4500 | 0 | #NAME? | 0 | #NAME? | Other
2.9 TEL | 889 | Unsuccessful negotiation. TEL believes costs inflated too much. | Target operating costs for Phase D are not agreed. | TEL Business Case becomes undeliverable. Potential to undertake Dispute Resolution to gain agreement. | 1 |  | 300 |  | 2010-01-04 | 2019-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 3 | 4.0074 |  | 80 | 3.2059 | 0.80148 | 0.24661 | 3.2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 | 0.24661 |  | DISCRETE | #NAME? | 0.01 | 0.99 | 300 | 0 | #NAME? | 0 | #NAME? | Other
3 DESIGN | 104 | Delay in design information release from specialist tram manufacturer | Delay in detailing of stops, trackway, OLE etc for Phase 1B | Time delay and consequent costs | 15 | 0 | 25 | 83 | 2007-01-01 | 2008-09-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5.3153 | 7.1001 |  | 0 | 0 | 7.1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.15 | 0.85 | 25 | 0 | #NAME? | 0 | #NAME? | Other
3 DESIGN | 162 | Land is not acquired yet | Gaining access to land prior to purchase for advanced works | Increased management costs and delays to design | 10 | 0 |  | 30 | 2007-04-02 | 2008-09-28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.4699 | 1.9636 |  | 80 | 1.5708 | 0.39271 | 0.19636 | 1.5708 | 0.19636 | 0.19636 | 0.19636 | 0.19636 | 0.19636 | 0.19636 | 0.19636 | 0.19636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UNIFORM | #NAME? | 0.1 | 0.9 | 0 | 0 | #NAME? | 0 | #NAME? | Other
7.1.1 Invasive Species | 869 | Surveying team unable to obtain access to Network Rail, BAA and other privately owned land because they were not cleared to access this land (including PTS). | Extent of Invasive Species Area Exceeds Estimate from Survey | Underestimating the extent of works; leads to an increase in cost | 17.5 |  | 20 |  | 2007-04-17 | 2009-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 3.5 | 4.6753 |  | 100 | 4.6753 | 0 | 0.31169 | 4.6753 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0.31169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.175 | 0.825 | 20 | 0 | #NAME? | 0 | #NAME? | Other
7.1.1 Invasive Species | 879 | Contractor is unable to get access to worksite due to access route being outside LOD and owned by others | Access to land to eradicate invasive species is not available when required | Programme Delay; contractor refuses to take ownership of risk 869 or includes high contingency in tender to allow for. | 10 | 0 | 10 | 20 | 2007-03-12 | 2009-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1.0042 | 1.3414 |  | 3 | 0.040243 | 1.3012 | 0.0026829 | 0.040243 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0.0026829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.1 | 0.9 | 10 | 0 | #NAME? | 0 | #NAME? | Other
7.1.2 Badger Relocation | 894 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Roseburn Badger Proposals for closure of old setts not approved by SNH | Delay in accessing land to construct Tram works and hence in Programme | 17.5 | 0 | 12.5 | 25 | 2008-10-01 | 2008-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.1769 | 2.908 |  | 0 | 0 | 2.908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.175 | 0.825 | 12.5 | 0 | #NAME? | 0 | #NAME? | Other
7.1.2 Badger Relocation | 883 | Ineffective/Inappropriate Proposals; new setts must be built before old ones can be closed and licenses will not be issued until nearer time of closure; animals must have settled in new home before closure of old one can take place | Gogarburn Badger/Otter Proposals for closure of old setts not approved by SNH/SEERAD | Delay in accessing land to construct Tram works and hence in Programme | 10 | 0 | 12.5 | 25 | 2007-10-01 | 2008-10-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2295 | 1.6424 |  | 100 | 1.6424 | 0 | 0.18248 | 1.6424 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0.18248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRIANG | #NAME? | 0.1 | 0.9 | 12.5 | 0 | #NAME? | 0 | #NAME? | Other
5 PARLIAMENTARY PROCESS/ APPROVALS | 977 | Legal challenge. Extension of statutory consultation process. Large number of objections. TRO process is subject to a public hearing process. | Delay in achievement of TROs) due to a large number of public objections and/or a legal challenge to using a TTRO to construct Infraco. | Requirement to start construction using TTROs | 90 |  | 750 |  | 2007-06-18 | 2009-12-31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 675 | 901.6657 |  | 100 | 901.6657 | 0 | 37.5694 | 901.6657 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 37.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DISCRETE | #NAME? | 0.9 | 0.1 | 750 | 0 | #NAME? | 0 | #NAME? | TROs
[97 empty] | TOTALS | #NAME? | [6 empty] | #NAME?
25927.2097
[50 empty] | 21407.3799 |  |  |  | 25927.2097 |  |  | 2333.38 | 1742.0661 | 1745.3847 | 1731.9919 | 1731.9919 | 1631.4567 | 1628.1381 | 1585.874 | 1444.4791 | 1038.4084 | 963.3108 | 854.8172 | 268.5307 | 268.5307 | 234.2521 | 234.2521 | 227.1752 | 227.1752 | 227.1752 | 232.3048 | 232.3048 | 232.3048 | 232.3048 | 231.3904 | 231.3904 | 162.5132 | 162.7598 | 162.7598 | 162.7598 | 162.7598 | 162.7598 | 162.7598 | 162.7598 | 36.138 | 36.138 | 36.138 | 36.138 | 36.138 | 5267.6782
Mean Sum = p50
[50 empty] | 5415.0283 |  | 0 | 170 | 6617.7127 | [51 empty] | Infraco Delivery
[50 empty] | 2628.5558 |  | 0 | 160 | 3191.1269 | [51 empty] | Design & Consents
[50 empty] | 6481.5114 |  | 0 | 0 | 8318.5806 | [51 empty] | MUDFA
[50 empty] | 5071.4036 |  | 0 | 80 | 5419.5089 | [51 empty] | General Programme Delay
[50 empty] | 788.2958 |  | 0 | 200 | 1053.0063 | [51 empty] | Land compensation
[50 empty] | 675 |  | 0 | 100 | 901.6657 | [51 empty] | TROs
[50 empty] | 228.8737 |  | 0 | 0 | 305.7298 | [51 empty] | Network Rail
[50 empty] | 118.7113 |  | 0 | 200 | 119.879 | [51 empty] | Other
[50 empty] | 0 |  | 0 | -810 | 0 | [51 empty] | Unspecified Risks (Contingency)
[50 empty] | 21407.3799 |  | 0 | 0 | 25927.2097