## Sheet1
Appendix 1
Tram - Final Business Case (FBC)
Outline Actionplan
Action | Start | Finish | Comment
Establish working group & governance | May | May | see note 1
Proposal for working group & governance to May TPB |  | 2007-05-18
Seek clarification on Transport Scotland comments on DFBC | June | June | see items identified in the response to Transport Scotland comments
Seek clarification of approval requirements for the FBC from Stakeholders | June | June
Seek clarification of approval timescales for the FBC from Stakeholders | June | June
Agree outline structure for FBC with Stakeholders | June | July
Prepare programme for preparation | June | July | note 2
Establish specialists skills requirements and resource plan | June | July
Review existing documents / section and update as appropriate | June | submission of FBC draft
Further develop sections on stakeholder / programme and risk management | June | submission of FBC draft
Clarify requirements for updates of DFBC appendices | June | submission of FBC draft
Develop audit trail for key assumptions and proposals from DFBC to FBC | July | submission of FBC draft
Update/Confirm FBC with Final Infraco/Tramco negotiations results | tba | tba
Submit FBC-draft for review to Stakeholders (Transport Scotland and CEC) | tba | tba
Present FBC for approval to TPB | tba | tba
Submit final FBC for approval to Transport Scotland / CEC | tba | tba
Notes
Note 1 - Suggested membership for FBC working group:
- Duncan Fraser (CEC)
- Rebecca Andrew (CEC)
- John Ramsay/Matthew Spence (Transport Scotland)
- Lorna Davis (Transport Scotland)
- Steward McGarrity (tie)
- Miriam Thorne (tie)
- Alasdair Sim (tie)
- Geoff Gilbert (tie)
- Alastair Richards (TEL)
Note 2 - The programme for preparation of the FBC is highly
dependent on the project master programme and specifically on
the specific programmes for Procurement, Design completion and
Traffic Management. Timetables for the completion of individual
sections of the FBC can be prepared following presentation
of the current programme review to the May TBP.